## All Projects
SECOND KENYA DEVOLUTION SUPPORT PROGRAM (KDSP II)
COUNTY PROJECT STOCK-TAKING TEMPLATE ¦ Sector: ALL SECTORS
1. Project Details | [6 empty] | 2. Project Location |  |  | 3. Implementation Details | [6 empty] | 4. Financial Information | [11 empty] | 5. Project Status | [10 empty] | 6. Climate & Disaster Risk Screening |  | 7. Environmental, Social, Occupational Health, Safety and Gender Screening |  | 8. Technical, Financial and Economic Viability Screening |  | 9. Additional Remarks
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget Line) | Budget Item Name | Sub-County | Ward | Geographic Location (Lat & Lng) | Sector/Vote Name | Department/Directorate/Unit | Implementing Dept/Agency | Date of Approval | Project Start Date | Expected Completion Date | Actual Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost (Kshs.) | Funds Available in FY (Kshs.) | Project Funding Source | Development Partner (specify) | County Govt Component (Kshs.) | Dev Partner Component (Kshs.) | Total Disbursed Funds (Kshs.) | % Disbursed (Disbursed/Approved) | Expenditure to Date (Kshs.) | Pending Bills/Outstanding (Kshs.) | Project Balance (Kshs.) | Project Status | % Completion (Ongoing/Stalled) | % Completion at Stalling | Reasons for Stalling | Year Stalled | Time to Complete (months) | Est. Cost to Complete (Kshs.) | Still in Budget? (Yes/No) | Recommendation (Complete/Cancel/Defer) | Associated Risks | Climate & Disaster Risk Screening (Yes/No) | Climate & Disaster Mitigation Actions | ESHSG Screening (Yes/No) | ESHSG Mitigation Actions | Technical/Financial Viability Screening (Yes/No) | Technical Viability Details/Plans | Remarks
1 | French beans and marketing project | Provide production inputs and improve market access for french beans | Develop the french beans value chain to boost households income | 250 MT of fresh beans produced per week |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2014-01-01 | 2014-01-01 | [5 empty] | MCG |  |  |  |  | 1% |  |  |  | PLANNED | 1% | [14 empty] | Implemented by Directorate of Agribusiness and marketing
2 | Kenyatta Agriculture Farmers Training Centre (Mariira farm ). Staff and farmers capacity building | Capacity building of staff and farmers on agricultural technologies |  |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-07-01 | 2014-07-01 |  |  |  |  | MCG |  |  |  |  | 1% |  |  |  | ONGOING | [15 empty] | Training based on need basis
3 | Gikindu (Thailand) Farmers Dry land Training Centre project | Project to develop support infrastructure for stakeholders training | Establish a centre for training agricultural stakeholders on recommended agricultural technlogies and practically demonstratethe same | Develop modern hostels for stakeholders accomodation |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2014-01-01 | 2014-06-01 | 2014-06-01 |  |  |  |  | MCG |  |  |  |  | 0.5% |  |  |  | STALLED | 0.5% | [12 empty] | YES |  | 100M required to complete ground floor hostels rooms and another 1st floor to make 30 room capacity The FTC is stalled and un operational
4 | Gikindu (Thailand) Farmers Dry land Training Centre project | Project to develop support infrastructure for stakeholders training | Establish a centre for training agricultural stakeholders on recommended agricultural technlogies and practically demonstratethe same | Develop modern hostels for stakeholders accomodation |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2014-01-01 | 2014-06-01 | 2015-06-01 |  |  |  |  | MCG | No |  |  |  | 0.5% |  |  |  | STALLED | 0.5% | [12 empty] | YES |  | 100M required to complete ground floor hostels rooms and another 1st floor to make 30 room capacity The FTC is stalled and un operational
5 | Ajibika Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture and efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANDARA | ITHIRU, RUCHU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | MCG | No |  |  |  | 0.45% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
6 | Kanyenyaini Irrigation project |  | Develop irrigation infrastucture and efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANGEMA | KANYENYAINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | National Government | No |  |  |  | 0.58% |  |  |  | STALLED | 0.58% | [14 empty] | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
7 | Kimathi Githuri irrigation project-Food security programme (rice and Vegetables) | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Support fhouseholds to improve food and nutrition security through irrigated agriculture | Improve food and nutrition security through irrigated agriculture covering 1000 small holder farms /households |  |  | KIHARU | GATURI, MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  | 10M |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
8 | Food nd nutrition security -Ria Komu- Thika Ridge irrigation Project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Support fhouseholds to improve food and nutrition security through irrigated agriculture | improve food and nutrition security through irrigated agriculture covering 1000 small holder farms /households |  |  | GATANGA | KIHUMBUINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD |  |  |  | 0.52% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
9 | Agriculture Sector Development Support Programme Phase one | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | mixed | DP |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
10 | Murang’a Dairy Coolers procurement under Murang’a Cooperative Creameries Union (MCCU) | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 0.5% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 35 Installed by County Government 10 Installed by National Government
11 | Dairy Cow Ownership Program(Cows and shed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.33% |  |  |  | COMPLETED | 100% | [14 empty] | Included construction of Mariira zero grazing unit and distribution of 385 cows
12 | French beans marketing & pack house project | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 1% |  |  |  | PLANNED | [15 empty] | Implemented by Directorate of Agribusiness and marketing
13 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2015-03-01 | [5 empty] | MCG | No | [7 empty] | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
14 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2015-06-01 | [5 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
15 | Food security programmme-Gikindu irrigation scheme | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Promote irrigated agriculture to boost food security |  |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-13 | [5 empty] | DP | IFAD |  |  | 341.13 | 0.8% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 1500 HH have access to irrigation water. Have 3 blocks, over 600 farmers in block 1 have access to irrigation water.
16 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.42% |  |  |  | COMPLETED | 100% | [12 empty] | YES
17 | Murang’a Dairy Coolers procurement under Murang’a Cooperative Creameries Union (MCCU) | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 0.5% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 35 Installed by County Government 10 Installed by National Government
18 | Dairy Cow Ownership Program(Cows and shed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.33% |  |  |  | COMPLETED | 100% | [14 empty] | Included construction of Mariira zero grazing unit and distribution of 385 cows
19 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 |  |  |  |  | 22.75 | MCG |  | 22.75 |  | 22.75 | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
20 | Aquaculture development programme-Capture Fisheries (Dams and river ) & Fisheries extension support |  | ongoing |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [7 empty] | 9.2 | MCG | [8 empty] | PLANNED | [15 empty] | ongoing project
21 | Coffee Revitalization Project | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | World Bank |  |  |  | 0.72% | 2022 |  |  | ONGOING
22 | ARABIKA | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | ITALIAN AGENCY for Development cooperation (AICS) |  |  |  | 0.17% |  |  |  | PLANNED
23 | Kinogerama fcs processing water conservation | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | GIZ |  |  |  | 0.3% |  |  |  | PLANNED | [15 empty] | completed
24 | Murang’a County Coffee Mill | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
25 | French beans marketing & pack house project | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED | [15 empty] | Implemented by Directorate of Agribusiness and marketing
26 | Coffee roaster for Murang’a coffee farmers cooperative union | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 1% |  |  |  | PLANNED | [15 empty] | complete project
27 | Livestock Sheds | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | [9 empty] | MCG |  |  |  |  | 1% |  |  |  | COMPLETED | 100%
28 | Mbombo Marketing shed | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 | [5 empty] | MCG | no |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | completed and in use
29 | Market access project. Avocado value chain | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | no |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Completed
30 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-03-01 | [5 empty] | MCG | No | [5 empty] | 100 |  | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
31 | Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | Establishment of Two (2) Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | KANDARA, KIGUMO | ITHIRU, KIGUMO |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.8% |  |  |  | COMPLETED | 100% | [14 empty] | Export of French beans and snow peas irrigated project stalled. Alongside makuyu pack house under Agribusiness and marketing directorate. Lack of market &financing for inputs
32 | Ajibika Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture and efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANDARA | ITHIRU, RUCHU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | MCG | No |  |  |  | 0.45% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
33 | Nyanjigi Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANGEMA | MUGURU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | National Government | No |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
34 | Kimathi Githuri irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure covering 1000 small holder farms /households |  |  | KIHARU | GATURI, MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG | No |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
35 | Ria Komu- Thika Ridge irrigation Project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure for n covering 1000 small holder farms /households |  |  | GATANGA | KIHUMBUINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | Mixed | IFAD |  |  |  | 0.52% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
36 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-11 | [5 empty] | mixed | SIDA |  | 13M, National government |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
37 | Upper Tana Natural Resource Management Program | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD, Spanish Trust Fund, GOK, COMM |  |  |  | 0.6% |  |  |  | COMPLETED | 100% | [14 empty] | Contract Value covered activities in 5 project components (Rural livelihood, Community Empowerment, Natural resource management, Agribusiness and project Coordination in 6 Counties Allocation of funds done by Project Coordination Team. - 735 funded Common Interest Groups in Murang’a County received directly
38 | Upper Tana Nairobi Water Fund | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | Yes |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
39 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2015-07-07 | [5 empty] | MCG |  |  |  |  | 0.42% |  |  |  | COMPLETED | 100% | [12 empty] | YES
40 | Murang’a Dairy Coolers procurement under Murang’a Cooperative Creameries Union (MCCU) | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [5 empty] | 0 | 0 | 0 | MCG |  |  |  | 0 | 0% | 0 |  |  | PLANNED | [13 empty] | YES |  | 35 Installed by County Government 10 Installed by National Government
41 | Dairy Cow Ownership Program(Cows and shed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-08 |  |  | 0 | 0 | 0 | MCG |  |  |  | 0 | 0% | 0 |  |  | PLANNED | [15 empty] | Included construction of Mariira zero grazing unit and distribution of 385 cows
42 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-08 | [5 empty] | MCG |  |  |  |  | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
43 | Aquaculture development programme-Capture Fisheries (Dams and river ) & Fisheries extension support |  | ongoing |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [7 empty] | 9.2 | MCG | [8 empty] | PLANNED | [15 empty] | ongoing project
44 | French beans marketing & pack house project | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED | [15 empty] | Implemented by Directorate of Agribusiness and marketing
45 | Coffee roaster for Murang’a coffee farmers cooperative union | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 1% |  |  |  | PLANNED | [15 empty] | complete project
46 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2017-07-01 | [5 empty] | MCG | No | [7 empty] | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
47 | Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | Establishment of Two (2) Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | KANDARA, KIGUMO | ITHIRU, KIGUMO |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.8% |  |  |  | COMPLETED | 100% | [14 empty] | Export of French beans and snow peas irrigated project stalled. Alongside makuyu pack house under Agribusiness and marketing directorate. Lack of market &financing for inputs
48 | Ititu Ikundu Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-06 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
49 | National Agricultural and Rural Inclusive Growth Project (NARIGP) | Project linked rural smallholder farmers’ CIGs and VMGs organized along selected priority VCs to markets | To increase agricultural productivity and profitability of targeted rural communities in selected Counties, and in the event of an Eligible Crisis or Emergency, to provide immediate and effective response |  |  |  | KANDARA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANGARI, KIGUMO, KINYONA, MUTHITHI, MUGOIRI, MURARANDIA, WANGU, ICHAGAKI, KAMAHUHA, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2018-07-01 | [5 empty] | Mixed | World bank |  |  |  | 0.9% |  |  |  | COMPLETED | 100% | [14 empty] | project completed and succeded by NAVCDP
50 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2018-07-11 | [5 empty] | 21M | SIDA |  | SIDA, National government |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
51 | Upper Tana Natural Resource Management Program | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD, Spanish Trust Fund, GOK, COMM |  |  |  | 0.6% |  |  |  | COMPLETED | 100% | [14 empty] | Contract Value covered activities in 5 project components (Rural livelihood, Community Empowerment, Natural resource management, Agribusiness and project Coordination in 6 Counties Allocation of funds done by Project Coordination Team. - 735 funded Common Interest Groups in Murang’a County received directly
52 | Upper Tana Nairobi Water Fund | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | Yes |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
53 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2015-07-01 | [5 empty] | MCG |  |  |  |  | 0.57% |  |  |  | COMPLETED | 100% | [12 empty] | YES
54 | Murang’a Dairy Coolers procurement under Murang’a Cooperative Creameries Union (MCCU) | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 0.5% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 35 Installed by County Government 10 Installed by National Government
55 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
56 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-03-01 | [5 empty] | MCG | No | [7 empty] | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
57 | National Agricultural and Rural Inclusive Growth Project (NARIGP) | Project linked rural smallholder farmers’ CIGs and VMGs organized along selected priority VCs to markets | To increase agricultural productivity and profitability of targeted rural communities in selected Counties, and in the event of an Eligible Crisis or Emergency, to provide immediate and effective response |  |  |  | KANDARA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANGARI, KIGUMO, KINYONA, MUTHITHI, MUGOIRI, MURARANDIA, WANGU, ICHAGAKI, KAMAHUHA, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2108-07-01 | [5 empty] | Mixed | World bank |  |  |  | 0.9% |  |  |  | COMPLETED | 100% | [14 empty] | project completed and succeded by NAVCDP
58 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-11 | [5 empty] | mixed | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
59 | Upper Tana Natural Resource Management Program | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD, Spanish Trust Fund, GOK, COMM |  |  |  | 0.6% |  |  |  | COMPLETED | 100% | [14 empty] | Contract Value covered activities in 5 project components (Rural livelihood, Community Empowerment, Natural resource management, Agribusiness and project Coordination in 6 Counties Allocation of funds done by Project Coordination Team. - 735 funded Common Interest Groups in Murang’a County received directly
60 | Upper Tana Nairobi Water Fund | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | Yes |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
61 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2014-01-07 | 2014-01-07 | [5 empty] | MCG |  |  |  |  | 0.42% |  |  |  | COMPLETED | 100% | [12 empty] | YES
62 | Murang’a Dairy Coolers procurement under Murang’a Cooperative Creameries Union (MCCU) | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [5 empty] | 0 | 0 | 0 | MCG |  |  |  | 0 | 0% | 0 |  |  | COMPLETED | 100% | [12 empty] | YES |  | 35 Installed by County Government 10 Installed by National Government
63 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-01-06 | [5 empty] | MCG |  |  |  |  | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
64 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-03-01 |  |  | 0 | 0 | 0 | MCG | No | 0 |  | 0 |  |  |  |  | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
65 | Ititu Ikundu Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-06 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
66 | National Agricultural and Rural Inclusive Growth Project (NARIGP) | Project linked rural smallholder farmers’ CIGs and VMGs organized along selected priority VCs to markets | To increase agricultural productivity and profitability of targeted rural communities in selected Counties, and in the event of an Eligible Crisis or Emergency, to provide immediate and effective response |  |  |  | KANDARA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANGARI, KIGUMO, KINYONA, MUTHITHI, MUGOIRI, MURARANDIA, WANGU, ICHAGAKI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 | [5 empty] | Mixed | World bank |  |  |  | 0.9% |  |  |  | COMPLETED | 100% | [14 empty] | project completed and succeded by NAVCDP
67 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-11 | [5 empty] | mixed | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
68 | Upper Tana Natural Resource Management Program | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD, Spanish Trust Fund, GOK, COMM |  |  |  | 0.6% |  |  |  | COMPLETED | 100% | [14 empty] | Contract Value covered activities in 5 project components (Rural livelihood, Community Empowerment, Natural resource management, Agribusiness and project Coordination in 6 Counties Allocation of funds done by Project Coordination Team. - 735 funded Common Interest Groups in Murang’a County received directly
69 | Upper Tana Nairobi Water Fund | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | Yes |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
70 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | xtension and Follow up activities
71 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
72 | Aquaculture development programme-Capture Fisheries (Dams and river ) & Fisheries extension support |  | ongoing |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [7 empty] | 9.2 | MCG | [8 empty] | PLANNED | [15 empty] | ongoing project
73 | Kenyatta Agriculture Farmers Training Centre (Mariira farm ). Staff and farmers capacity building | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | No |  |  |  | 1% |  |  |  | ONGOING | [15 empty] | ongoing
74 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-03-01 | [5 empty] | MCG | No | [7 empty] | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
75 | Ititu Ikundu Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-06 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
76 | Kimathi Githuri irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure covering 1000 small holder farms /households |  |  | KIHARU | GATURI, MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG | No |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
77 | National Agricultural and Rural Inclusive Growth Project (NARIGP) | Project linked rural smallholder farmers’ CIGs and VMGs organized along selected priority VCs to markets | To increase agricultural productivity and profitability of targeted rural communities in selected Counties, and in the event of an Eligible Crisis or Emergency, to provide immediate and effective response |  |  |  | KANDARA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANGARI, KIGUMO, KINYONA, MUTHITHI, MUGOIRI, MURARANDIA, WANGU, ICHAGAKI, KAMAHUHA, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 |  |  |  | 639865699 | 639865699 | Mixed | World bank |  | 211M | 639865699 | 100% |  |  | 0 | COMPLETED | 100% | [14 empty] | project completed and succeded by NAVCDP
78 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-11 | [5 empty] | mixed | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
79 | Upper Tana Natural Resource Management Program | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD, Spanish Trust Fund, GOK, COMM |  |  |  | 0.6% |  |  |  | COMPLETED | 100% | [14 empty] | Contract Value covered activities in 5 project components (Rural livelihood, Community Empowerment, Natural resource management, Agribusiness and project Coordination in 6 Counties Allocation of funds done by Project Coordination Team. - 735 funded Common Interest Groups in Murang’a County received directly
80 | Upper Tana Nairobi Water Fund | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | Yes |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
81 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.42% |  |  |  | COMPLETED | 100% | [12 empty] | YES
82 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
83 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-03-01 | [5 empty] | MCG | No | [7 empty] | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
84 | Ititu Ikundu Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-06 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
85 | National Agricultural and Rural Inclusive Growth Project (NARIGP) | Project linked rural smallholder farmers’ CIGs and VMGs organized along selected priority VCs to markets | To increase agricultural productivity and profitability of targeted rural communities in selected Counties, and in the event of an Eligible Crisis or Emergency, to provide immediate and effective response |  |  |  | KANDARA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANGARI, KIGUMO, KINYONA, MUTHITHI, MUGOIRI, MURARANDIA, WANGU, ICHAGAKI, KAMAHUHA, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 | [5 empty] | Mixed | World bank |  |  |  | 0.9% |  |  |  | COMPLETED | 100% | [14 empty] | project completed and succeded by NAVCDP
86 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-11 | [5 empty] | mixed | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
87 | Upper Tana Natural Resource Management Program | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD, Spanish Trust Fund, GOK, COMM |  |  |  | 0.6% |  |  |  | COMPLETED | 100% | [14 empty] | Contract Value covered activities in 5 project components (Rural livelihood, Community Empowerment, Natural resource management, Agribusiness and project Coordination in 6 Counties Allocation of funds done by Project Coordination Team. - 735 funded Common Interest Groups in Murang’a County received directly
88 | Upper Tana Nairobi Water Fund | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | Yes |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
89 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 |  |  | 2023 |  |  | MCG |  |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES
90 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-11 | [5 empty] | mixed | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
91 | Kangari United Dairy Cooperative union-fodder chopper and Silage baller project |  | Contibute to Increased dairy Value chain productivity through fodder presevation | Complete silage baler ( includes Chopper nd Power Source) |  |  | KIGUMO | KANGARI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-13 | [5 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and utilized for fodder preservation for increased dairy value chain productity
92 | Kigoro Dairy cooperative union- milk pastulizer and solar powered milk pre-chiller |  | Contribute to Increased dairy Value chain productivity through value adddition | hybrid milk pastulizer and milk cooler mounted on a tuk tuk |  |  | GATANGA | KARIARA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-14 | [5 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and utilized for milk value addition r increased dairy value chain productity
93 | Eco friendly water pumps-solar powered ,Low pressure water pumps and storage tanks |  | Contribute to Increased french beans Value chain productivity through efficient water and energy utilization technologies | Solar powered ,Low pressure water pumps and storage tanks |  |  | GATANGA, KIHARU | KAKUZI/MITUMBIRI, MBIRI, WANGU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCOs-Gacharu Irrigation Water self help group ,MwanaWikio Greens Self help group among others
94 | Banana micro propagation Chambers |  |  | Four (4) Banana micro propagation Chambers |  |  | KANDARA, KIHARU, MARAGUA, MATHIOYA | GAICHANJIRU, GATURI, NGINDA, GITUGI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Four banana VCOs benefitted
95 | Banana carrier tuktuk |  | Improve market access for banana through proper transportation | one (1) Banana carrier tuktuk |  |  | GATANGA | GATANGA, KIHUMBUINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCO-Kigachu Banana farmers SHG
96 | Banana solar driers,Mini bakery equipment & Hammer mill |  | Contribute to Increased banana Value chain productivity through value addition | 1 Banana solar driers,1Mini bakery equipment & 1 Hammer mill |  |  | KANDARA, MARAGUA | GAICHANJIRU, KAMAHUHA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCOs-Gikama & Sabasaba Agribusiness cooperative societies
97 | Gikindu irrigation scheme | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-13 | [5 empty] | DP | IFAD |  |  | 341.13 | 0.8% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 1500 HH have access to irrigation water. Have 3 blocks, over 600 farmers in block 1 have access to irrigation water.
98 | Rubiru irrigation scheme | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | DP | AfDB |  |  |  | 0.95% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 496 HH have access to irrigation water covering 340 ha.
99 | Rubiru irrigation scheme borehole | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | GATANGA | ITHANGA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | facility supplies clean water to Rubiru grading and marketing shed as well as households within its neighbourhood
100 | Rubiru livestock sale Yard | [5 empty] | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | yard already in used
101 | Gikindu Honey refinery | [5 empty] | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Farmers trained on operation of honey processing equipment May 2025
102 | Value addition of African vegetables- assorted equipments | [5 empty] | GATANGA | GATANGA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Young farmers producing indeginous vegetables, herb and spices dry and sell. Access to solar dryier helped them in boosting the production.
103 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
104 | Aquaculture development programme-Capture Fisheries (Dams and river ) & Fisheries extension support |  | ongoing |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [7 empty] | 9.2 | MCG | [8 empty] | PLANNED | [15 empty] | ongoing project
105 | National Agricultyral Value Chains Development Project (NAVCDP) |  | To increase market participation for targeted farmers in select value chains in project areas | [6 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | Mixed | World bank | [7 empty] | PLANNED
106 | Milk and Mango e-voucher subsidy progrmme | Farmers wallet quarterly credited Ksh 2400 |  |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2023-01-01 | [5 empty] | MCG |  |  |  | 156 |  |  |  |  | PLANNED | [15 empty] | Programme benefitting 22,015 farmers
107 | Certified maize seeds and fertilizer subsidy programme | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
108 | Disease control and Survelilance | Ring vaccinations againist Anthrax and LSD |  |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
109 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-03-01 | [5 empty] | MCG | No | [7 empty] | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
110 | Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | Establishment of Two (2) Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | KANDARA, KIGUMO | ITHIRU, KIGUMO |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.8% |  |  |  | COMPLETED | 100% | [14 empty] | Export of French beans and snow peas irrigated project stalled. Alongside makuyu pack house under Agribusiness and marketing directorate. Lack of market &financing for inputs
111 | Gikindu (Thailand) Farmers Dry land Training Centre project | Project to develop support infrastructure for stakeholders training | Establish a centre for training agricultural stakeholders on recommended agricultural technlogies and practically demonstratethe same | Develop modern hostels for stakeholders accomodation |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 1905-07-06 | 2014-06-01 | [5 empty] | MCG | No |  |  |  | 0.5% |  |  |  | STALLED | 0.5% | [12 empty] | YES |  | 100M required to complete ground floor hostels rooms and another 1st floor to make 30 room capacity The FTC is stalled and un operational
112 | Agriculture materials supplies and small equipment | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Support farming community with materails and equipment |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2017-06-01 | [5 empty] | MCG | No |  |  |  | 0.53% |  |  |  | COMPLETED | 100%
113 | Ajibika Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture and efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANDARA | ITHIRU, RUCHU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | MCG | No |  |  |  | 0.45% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
114 | Kanyenyaini Irrigation project |  | Develop irrigation infrastucture and efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANGEMA | KANYENYAINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | National Government | No |  |  |  | 0.58% |  |  |  | STALLED | 0.58% | [14 empty] | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
115 | Nyanjigi Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANGEMA | MUGURU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | National Government | No |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
116 | Ititu Ikundu Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-06 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
117 | Kaihi Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure for n covering 1000 small holder farms /households |  |  | KANGEMA | MUGURU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | National Government | No | 0 | [6 empty] | ONGOING | 0.8% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
118 | Kimathi Githuri irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure covering 1000 small holder farms /households |  |  | KIHARU | GATURI, MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG | No |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
119 | Ria Komu- Thika Ridge irrigation Project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure for n covering 1000 small holder farms /households |  |  | GATANGA | KIHUMBUINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | Mixed | IFAD |  |  |  | 0.52% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
120 | National Agricultural and Rural Inclusive Growth Project (NARIGP) | Project linked rural smallholder farmers’ CIGs and VMGs organized along selected priority VCs to markets | To increase agricultural productivity and profitability of targeted rural communities in selected Counties, and in the event of an Eligible Crisis or Emergency, to provide immediate and effective response |  |  |  | GATANGA, KANDARA, KIGUMO, KIHARU, MARAGUA, MATHIOYA |  |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 |  |  | 1056310000 | 639865699 | 639865699 | Mixed | World bank | 100000000 |  | 625397213 | 0.9% |  |  | 14468486 | COMPLETED | 100% | [14 empty] | project completed and succeded by NAVCDP
121 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-11 | [5 empty] | mixed | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
122 | Upper Tana Natural Resource Management Program | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD, Spanish Trust Fund, GOK, COMM |  |  |  | 0.6% |  |  |  | COMPLETED | 100% | [14 empty] | Contract Value covered activities in 5 project components (Rural livelihood, Community Empowerment, Natural resource management, Agribusiness and project Coordination in 6 Counties Allocation of funds done by Project Coordination Team. - 735 funded Common Interest Groups in Murang’a County received directly
123 | Upper Tana Nairobi Water Fund | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | Yes |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
124 | Muranga Avocado Cooperative Union(MAVOC)-Avocado Grading line | [5 empty] | KANDARA | NGARARIA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | avocadograding facility with a capacity of 23 metric tonnesper day a cold room .
125 | Kangari United Dairy Cooperative union-fodder chopper and Silage baller project |  | Contibute to Increased dairy Value chain productivity through fodder presevation | Complete silage baler ( includes Chopper nd Power Source) |  |  | KIGUMO | KANGARI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-13 | [5 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and utilized for fodder preservation for increased dairy value chain productity
126 | Kigoro Dairy cooperative union- milk pastulizer and solar powered milk pre-chiller |  | Contribute to Increased dairy Value chain productivity through value adddition | hybrid milk pastulizer and milk cooler mounted on a tuk tuk |  |  | GATANGA | KARIARA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-14 | [5 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and utilized for milk value addition r increased dairy value chain productity
127 | Eco friendly water pumps-solar powered ,Low pressure water pumps and storage tanks |  | Contribute to Increased french beans Value chain productivity through efficient water and energy utilization technologies | Solar powered ,Low pressure water pumps and storage tanks |  |  | GATANGA, KIHARU | KAKUZI/MITUMBIRI, MBIRI, WANGU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCOs-Gacharu Irrigation Water self help group ,MwanaWikio Greens Self help group among others
128 | Banana micro propagation Chambers |  |  | Four (4) Banana micro propagation Chambers |  |  | KANDARA, KIHARU, MARAGUA, MATHIOYA | GAICHANJIRU, GATURI, NGINDA, GITUGI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Four banana VCOs benefitted
129 | Banana carrier tuktuk |  | Improve market access for banana through proper transportation | one (1) Banana carrier tuktuk |  |  | GATANGA | GATANGA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCO-Kigachu Banana farmers SHG
130 | Banana solar driers,Mini bakery equipment & Hammer mill |  | Contribute to Increased banana Value chain productivity through value addition | 1 Banana solar driers,1Mini bakery equipment & 1 Hammer mill |  |  | KANDARA, MARAGUA | GAICHANJIRU, KAMAHUHA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCOs-Gikama & Sabasaba Agribusiness cooperative societies
131 | Gikindu irrigation scheme | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-13 | [5 empty] | DP | IFAD |  |  | 341.13 | 0.8% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 1500 HH have access to irrigation water. Have 3 blocks, over 600 farmers in block 1 have access to irrigation water.
132 | Rubiru irrigation scheme | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | DP | AfDB |  |  |  | 0.95% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 496 HH have access to irrigation water covering 340 ha.
133 | Rubiru irrigation scheme borehole | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | facility supplies clean water to Rubiru grading and marketing shed as well as households within its neighbourhood
134 | Rubiru livestock sale Yard | [5 empty] | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | yard already in used
135 | Gikindu Honey refinery | [5 empty] | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Farmers trained on operation of honey processing equipment May 2025
136 | Value addition of African vegetables- assorted equipments | [5 empty] | GATANGA | GATANGA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Young farmers producing indeginous vegetables, herb and spices dry and sell. Access to solar dryier helped them in boosting the production.
137 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.42% |  |  |  | COMPLETED | 100% | [12 empty] | YES
138 | Murang’a Dairy Coolers procurement under Murang’a Cooperative Creameries Union (MCCU) | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 0.5% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 35 Installed by County Government 10 Installed by National Government
139 | Dairy Cow Ownership Program(Cows and shed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.33% |  |  |  | COMPLETED | 100% | [14 empty] | Included construction of Mariira zero grazing unit and distribution of 385 cows
140 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
141 | Aquaculture development programme-Capture Fisheries (Dams and river ) & Fisheries extension support |  | ongoing |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [7 empty] | 9.2 | MCG | [8 empty] | PLANNED | [15 empty] | ongoing project
142 | Coffee Revitalization Project | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | World Bank |  |  |  | 0.72% | 2022 |  |  | ONGOING
143 | ARABIKA | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | ITALIAN AGENCY for Development cooperation (AICS) |  |  |  | 0.17% |  |  |  | PLANNED
144 | Kinogerama fcs processing water conservation | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | GIZ |  |  |  | 0.3% |  |  |  | PLANNED | [15 empty] | completed
145 | Murang’a County Coffee Mill | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
146 | French beans marketing & pack house project | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED | [15 empty] | Implemented by Directorate of Agribusiness and marketing
147 | Coffee roaster for Murang’a coffee farmers cooperative union | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 1% |  |  |  | PLANNED | [15 empty] | complete project
148 | Livestock Sheds | [8 empty] | AGRICULTURE | [9 empty] | MCG |  |  |  |  | 1% |  |  |  | COMPLETED | 100%
149 | Mbombo Marketing shed | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 | [5 empty] | MCG | no |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | completed and in use
150 | Market access project. Avocado value chain | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | no |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Completed
151 | Kenyatta Agriculture Farmers Training Centre (Mariira farm ). Staff and farmers capacity building | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | No |  |  |  | 1% |  |  |  | ONGOING | [15 empty] | ongoing
152 | National Agricultyral Value Chains Development Project (NAVCDP) |  | To increase market participation for targeted farmers in select value chains in project areas | [6 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | Mixed | World bank | [7 empty] | PLANNED
153 | Milk and Mango e-voucher subsidy progrmme | Farmers wallet quarterly credited Ksh 2400 |  |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2023-01-01 | [5 empty] | MCG |  |  |  | 156 |  |  |  |  | PLANNED | [15 empty] | Programme benefitting 22,015 farmers
154 | Certified maize seeds and fertilizer subsidy programme | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
155 | Disease control and Survelilance | Ring vaccinations againist Anthrax and LSD | [7 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
156 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-03-01 | [5 empty] | MCG | No | [7 empty] | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
157 | Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | Establishment of Two (2) Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | KANDARA, KIGUMO | ITHIRU, KIGUMO |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.8% |  |  |  | COMPLETED | 100% | [14 empty] | Export of French beans and snow peas irrigated project stalled. Alongside makuyu pack house under Agribusiness and marketing directorate. Lack of market &financing for inputs
158 | Gikindu (Thailand) Farmers Dry land Training Centre project | Project to develop support infrastructure for stakeholders training | Establish a centre for training agricultural stakeholders on recommended agricultural technlogies and practically demonstratethe same | Develop modern hostels for stakeholders accomodation |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 1905-07-06 | 2014-06-01 | [5 empty] | MCG | No |  |  |  | 0.5% |  |  |  | STALLED | 0.5% | [12 empty] | YES |  | 100M required to complete ground floor hostels rooms and another 1st floor to make 30 room capacity The FTC is stalled and un operational
159 | Agriculture materials supplies and small equipment | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Support farming community with materails and equipment |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2017-06-01 | [5 empty] | MCG | No |  |  |  | 0.53% |  |  |  | COMPLETED | 100%
160 | Ajibika Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture and efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANDARA | ITHIRU, RUCHU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | MCG | No |  |  |  | 0.45% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
161 | Kanyenyaini Irrigation project |  | Develop irrigation infrastucture and efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANGEMA | KANYENYAINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | National Government | No |  |  |  | 0.58% |  |  |  | STALLED | 0.58% | [14 empty] | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
162 | Nyanjigi Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANGEMA | MUGURU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | National Government | No |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
163 | Ititu Ikundu Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-06 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
164 | Kaihi Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure for n covering 1000 small holder farms /households |  |  | KANGEMA | MUGURU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | National Government | No | 0 | [6 empty] | ONGOING | 0.8% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
165 | Kimathi Githuri irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure covering 1000 small holder farms /households |  |  | KIHARU | GATURI, MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG | No |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
166 | Ria Komu- Thika Ridge irrigation Project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure for n covering 1000 small holder farms /households |  |  | GATANGA | KIHUMBUINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | Mixed | IFAD |  |  |  | 0.52% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
167 | National Agricultural and Rural Inclusive Growth Project (NARIGP) | Project linked rural smallholder farmers’ CIGs and VMGs organized along selected priority VCs to markets | To increase agricultural productivity and profitability of targeted rural communities in selected Counties, and in the event of an Eligible Crisis or Emergency, to provide immediate and effective response |  |  |  | GATANGA, KANDARA, KIGUMO, MARAGUA, MATHIOYA |  |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 |  |  | 1056310000 | 639865699 | 639865699 | Mixed | World bank | 100000000 |  | 625397213 | 0.9% |  |  | 14468486 | COMPLETED | 100% | [14 empty] | project completed and succeded by NAVCDP
168 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-11 | [5 empty] | mixed | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
169 | Upper Tana Natural Resource Management Program | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD, Spanish Trust Fund, GOK, COMM |  |  |  | 0.6% |  |  |  | COMPLETED | 100% | [14 empty] | Contract Value covered activities in 5 project components (Rural livelihood, Community Empowerment, Natural resource management, Agribusiness and project Coordination in 6 Counties Allocation of funds done by Project Coordination Team. - 735 funded Common Interest Groups in Murang’a County received directly
170 | Upper Tana Nairobi Water Fund | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | Yes |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
171 | Muranga Avocado Cooperative Union(MAVOC)-Avocado Grading line | [5 empty] | KANDARA | NGARARIA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | avocadograding facility with a capacity of 23 metric tonnesper day a cold room .
172 | Kangari United Dairy Cooperative union-fodder chopper and Silage baller project |  | Contibute to Increased dairy Value chain productivity through fodder presevation | Complete silage baler ( includes Chopper nd Power Source) |  |  | KIGUMO | KANGARI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-13 | [5 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and utilized for fodder preservation for increased dairy value chain productity
173 | Kigoro Dairy cooperative union- milk pastulizer and solar powered milk pre-chiller |  | Contribute to Increased dairy Value chain productivity through value adddition | hybrid milk pastulizer and milk cooler mounted on a tuk tuk |  |  | GATANGA | KARIARA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-14 | [5 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and utilized for milk value addition r increased dairy value chain productity
174 | Eco friendly water pumps-solar powered ,Low pressure water pumps and storage tanks |  | Contribute to Increased french beans Value chain productivity through efficient water and energy utilization technologies | Solar powered ,Low pressure water pumps and storage tanks |  |  | GATANGA, KIHARU | KAKUZI/MITUMBIRI, MBIRI, WANGU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCOs-Gacharu Irrigation Water self help group ,MwanaWikio Greens Self help group among others
175 | Banana micro propagation Chambers |  |  | Four (4) Banana micro propagation Chambers |  |  | KANDARA, KIHARU, MARAGUA, MATHIOYA | GAICHANJIRU, GATURI, NGINDA, GITUGI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Four banana VCOs benefitted
176 | Banana carrier tuktuk |  | Improve market access for banana through proper transportation | one (1) Banana carrier tuktuk |  |  | GATANGA | GATANGA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCO-Kigachu Banana farmers SHG
177 | Banana solar driers,Mini bakery equipment & Hammer mill |  | Contribute to Increased banana Value chain productivity through value addition | 1 Banana solar driers,1Mini bakery equipment & 1 Hammer mill |  |  | KANDARA, MARAGUA | GAICHANJIRU, KAMAHUHA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCOs-Gikama & Sabasaba Agribusiness cooperative societies
178 | Gikindu irrigation scheme | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-13 | [5 empty] | DP | IFAD |  |  | 341.13 | 0.8% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 1500 HH have access to irrigation water. Have 3 blocks, over 600 farmers in block 1 have access to irrigation water.
179 | Rubiru irrigation scheme | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | DP | AfDB |  |  |  | 0.95% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 496 HH have access to irrigation water covering 340 ha.
180 | Rubiru irrigation scheme borehole | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | facility supplies clean water to Rubiru grading and marketing shed as well as households within its neighbourhood
181 | Rubiru livestock sale Yard | [5 empty] | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | yard already in used
182 | Gikindu Honey refinery | [5 empty] | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Farmers trained on operation of honey processing equipment May 2025
183 | Value addition of African vegetables- assorted equipments | [5 empty] | GATANGA | GATANGA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Young farmers producing indeginous vegetables, herb and spices dry and sell. Access to solar dryier helped them in boosting the production.
184 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.42% |  |  |  | COMPLETED | 100% | [12 empty] | YES
185 | Murang’a Dairy Coolers procurement under Murang’a Cooperative Creameries Union (MCCU) | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 0.5% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 35 Installed by County Government 10 Installed by National Government
186 | Dairy Cow Ownership Program(Cows and shed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.33% |  |  |  | COMPLETED | 100% | [14 empty] | Included construction of Mariira zero grazing unit and distribution of 385 cows
187 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
188 | Aquaculture development programme-Capture Fisheries (Dams and river ) & Fisheries extension support |  | ongoing |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [7 empty] | 9.2 | MCG | [8 empty] | PLANNED | [15 empty] | ongoing project
189 | Coffee Revitalization Project | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | World Bank |  |  |  | 0.72% | 2022 |  |  | ONGOING
190 | ARABIKA | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | ITALIAN AGENCY for Development cooperation (AICS) |  |  |  | 0.17% |  |  |  | PLANNED
191 | Kinogerama fcs processing water conservation | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | GIZ |  |  |  | 0.3% |  |  |  | PLANNED | [15 empty] | completed
192 | Murang’a County Coffee Mill | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
193 | French beans marketing & pack house project | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED | [15 empty] | Implemented by Directorate of Agribusiness and marketing
194 | Coffee roaster for Murang’a coffee farmers cooperative union | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 1% |  |  |  | PLANNED | [15 empty] | complete project
195 | Livestock Sheds | [8 empty] | AGRICULTURE | [9 empty] | MCG |  |  |  |  | 1% |  |  |  | COMPLETED | 100%
196 | Mbombo Marketing shed | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 | [5 empty] | MCG | no |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | completed and in use
197 | Market access project. Avocado value chain | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | no |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Completed
198 | Kenyatta Agriculture Farmers Training Centre (Mariira farm ). Staff and farmers capacity building | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | No |  |  |  | 1% |  |  |  | ONGOING | [15 empty] | ongoing
199 | National Agricultyral Value Chains Development Project (NAVCDP) |  | To increase market participation for targeted farmers in select value chains in project areas | [6 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | Mixed | World bank | [7 empty] | PLANNED
200 | Milk and Mango e-voucher subsidy progrmme | Farmers wallet quarterly credited Ksh 2400 |  |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2023-01-01 | [5 empty] | MCG |  |  |  | 156 |  |  |  |  | PLANNED | [15 empty] | Programme benefitting 22,015 farmers
201 | Certified maize seeds and fertilizer subsidy programme | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
202 | Disease control and Survelilance | Ring vaccinations againist Anthrax and LSD | [7 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
203 | Tree seeds and seedlings project | Project supported farmers with Avocado , Mango , Banana , Coffee seeds and seedlings, Tree tomato, Sweet potatoes plantlets, sorghum, French beans and Traditional High Value Crops | To support farmers with quality crops planting materials nd promote commercially oriented enterprises that ensure increased farm incomes and sustainable food and nutrition security. | Increased productivity and incomes of Cash crops (Coffee, Banana, Macadamia, Avocado, Mango and Vegetables) by at least 100% |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-03-01 | [5 empty] | MCG | No | [7 empty] | COMPLETED | 100% | [14 empty] | Projected is and acheiving the intended objective. Surplus produce aggregated and local and export market access ensured
204 | Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | Establishment of Two (2) Semi-permanent French beans collection centres in Kigumo and Kandara |  |  | KANDARA, KIGUMO | ITHIRU, KIGUMO |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.8% |  |  |  | COMPLETED | 100% | [14 empty] | Export of French beans and snow peas irrigated project stalled. Alongside makuyu pack house under Agribusiness and marketing directorate. Lack of market &financing for inputs
205 | Gikindu (Thailand) Farmers Dry land Training Centre project | Project to develop support infrastructure for stakeholders training | Establish a centre for training agricultural stakeholders on recommended agricultural technlogies and practically demonstratethe same | Develop modern hostels for stakeholders accomodation |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 1905-07-06 | 2014-06-01 | [5 empty] | MCG | No |  |  |  | 0.5% |  |  |  | STALLED | 0.5% | [12 empty] | YES |  | 100M required to complete ground floor hostels rooms and another 1st floor to make 30 room capacity The FTC is stalled and un operational
206 | Agriculture materials supplies and small equipment | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Support farming community with materails and equipment |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2017-06-01 | [5 empty] | MCG | No |  |  |  | 0.53% |  |  |  | COMPLETED | 100%
207 | Ajibika Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture and efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANDARA | ITHIRU, RUCHU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | MCG | No |  |  |  | 0.45% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
208 | Kanyenyaini Irrigation project |  | Develop irrigation infrastucture and efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANGEMA | KANYENYAINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | National Government | No |  |  |  | 0.58% |  |  |  | STALLED | 0.58% | [14 empty] | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
209 | Nyanjigi Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | KANGEMA | MUGURU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2014-06-01 | [5 empty] | National Government | No |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
210 | Ititu Ikundu Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Irrigation infrasture established-intake and conveyance |  |  | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-06 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | Project completed and beneficiaries practising irrigated agriculture to alleviate food and nutrition security and further increase household incomes
211 | Kaihi Irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure for n covering 1000 small holder farms /households |  |  | KANGEMA | MUGURU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | National Government | No | 0 | [6 empty] | ONGOING | 0.8% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
212 | Kimathi Githuri irrigation project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure covering 1000 small holder farms /households |  |  | KIHARU | GATURI, MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG | No |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
213 | Ria Komu- Thika Ridge irrigation Project | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production | Develop irrigation infrastructure for n covering 1000 small holder farms /households |  |  | GATANGA | KIHUMBUINI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | Mixed | IFAD |  |  |  | 0.52% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Main irrigation infrastructure complete. Water connections to the beneficiaries farms ongoing
214 | National Agricultural and Rural Inclusive Growth Project (NARIGP) | Project linked rural smallholder farmers’ CIGs and VMGs organized along selected priority VCs to markets | To increase agricultural productivity and profitability of targeted rural communities in selected Counties, and in the event of an Eligible Crisis or Emergency, to provide immediate and effective response |  |  |  | GATANGA, KANDARA, KIGUMO, MARAGUA, MATHIOYA |  |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 |  |  | 1056310000 | 639865699 | 639865699 | Mixed | World bank | 100000000 |  | 625397213 | 0.9% |  |  | 14468486 | COMPLETED | 100% | [14 empty] | project completed and succeded by NAVCDP
215 | Agriculture Sector Development Support Programme Phase Two | Project contributed to transformation of Dairy ,French Beans and Banana Value chains to commercially oriented enterprises that ensure sustainable food and nutrition security. | To contribute to transformation of crop, livestock and fishery production into commercially oriented enterprises that ensure sustainable food and nutrition security. | Sustainable priority value chains for improved income, employment, food and nutrition security |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-11 | [5 empty] | mixed | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
216 | Upper Tana Natural Resource Management Program | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | Mixed | IFAD, Spanish Trust Fund, GOK, COMM |  |  |  | 0.6% |  |  |  | COMPLETED | 100% | [14 empty] | Contract Value covered activities in 5 project components (Rural livelihood, Community Empowerment, Natural resource management, Agribusiness and project Coordination in 6 Counties Allocation of funds done by Project Coordination Team. - 735 funded Common Interest Groups in Murang’a County received directly
217 | Upper Tana Nairobi Water Fund | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | Yes |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Project completed
218 | Muranga Avocado Cooperative Union(MAVOC)-Avocado Grading line | [5 empty] | KANDARA | NGARARIA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | Mixed | World bank | [7 empty] | COMPLETED | 100% | [12 empty] | YES |  | avocadograding facility with a capacity of 23 metric tonnesper day a cold room .
219 | Kangari United Dairy Cooperative union-fodder chopper and Silage baller project |  | Contibute to Increased dairy Value chain productivity through fodder presevation | Complete silage baler ( includes Chopper nd Power Source) |  |  | KIGUMO | KANGARI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-13 | [5 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and utilized for fodder preservation for increased dairy value chain productity
220 | Kigoro Dairy cooperative union- milk pastulizer and solar powered milk pre-chiller |  | Contribute to Increased dairy Value chain productivity through value adddition | hybrid milk pastulizer and milk cooler mounted on a tuk tuk |  |  | GATANGA | KARIARA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-14 | [5 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Project completed and utilized for milk value addition r increased dairy value chain productity
221 | Eco friendly water pumps-solar powered ,Low pressure water pumps and storage tanks |  | Contribute to Increased french beans Value chain productivity through efficient water and energy utilization technologies | Solar powered ,Low pressure water pumps and storage tanks |  |  | GATANGA, KIHARU | KAKUZI/MITUMBIRI, MBIRI, WANGU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCOs-Gacharu Irrigation Water self help group ,MwanaWikio Greens Self help group among others
222 | Banana micro propagation Chambers |  |  | Four (4) Banana micro propagation Chambers |  |  | KANDARA, KIHARU, MARAGUA, MATHIOYA | GAICHANJIRU, GATURI, NGINDA, GITUGI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Four banana VCOs benefitted
223 | Banana carrier tuktuk |  | Improve market access for banana through proper transportation | one (1) Banana carrier tuktuk |  |  | GATANGA | GATANGA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCO-Kigachu Banana farmers SHG
224 | Banana solar driers,Mini bakery equipment & Hammer mill |  | Contribute to Increased banana Value chain productivity through value addition | 1 Banana solar driers,1Mini bakery equipment & 1 Hammer mill |  |  | KANDARA, MARAGUA | GAICHANJIRU, KAMAHUHA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | SIDA |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Benefitting VCOs-Gikama & Sabasaba Agribusiness cooperative societies
225 | Gikindu irrigation scheme | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-13 | [5 empty] | DP | IFAD |  |  | 341.13 | 0.8% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 1500 HH have access to irrigation water. Have 3 blocks, over 600 farmers in block 1 have access to irrigation water.
226 | Rubiru irrigation scheme | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-12 | [5 empty] | DP | AfDB |  |  |  | 0.95% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 496 HH have access to irrigation water covering 340 ha.
227 | Rubiru irrigation scheme borehole | An initiative designed to convey water to small holder farms to boost food and nutrition security. | Develop irrigation infrastucture ad efficiently manage water for crop production |  |  |  | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | facility supplies clean water to Rubiru grading and marketing shed as well as households within its neighbourhood
228 | Rubiru livestock sale Yard | [5 empty] | GATANGA | KAKUZI/MITUMBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | yard already in used
229 | Gikindu Honey refinery | [5 empty] | KIHARU | MBIRI |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Farmers trained on operation of honey processing equipment May 2025
230 | Value addition of African vegetables- assorted equipments | [5 empty] | GATANGA | GATANGA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | AfDB |  |  |  | 1% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | Young farmers producing indeginous vegetables, herb and spices dry and sell. Access to solar dryier helped them in boosting the production.
231 | Livestock development-Fodder development, Milk coolers procurement, installing and follow-up, extension services, egg hatcheries, cow feed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.42% |  |  |  | COMPLETED | 100% | [12 empty] | YES
232 | Murang’a Dairy Coolers procurement under Murang’a Cooperative Creameries Union (MCCU) | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 0.5% |  |  |  | COMPLETED | 100% | [12 empty] | YES |  | 35 Installed by County Government 10 Installed by National Government
233 | Dairy Cow Ownership Program(Cows and shed | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.33% |  |  |  | COMPLETED | 100% | [14 empty] | Included construction of Mariira zero grazing unit and distribution of 385 cows
234 | Veterinary services development sub program (Animal Breeding Project=(Artificial Insemination Program, Disease ControlProject=( (Vaccination and surveillance, Public Health Project (Meat Inspectorate Services, Hides/Skins Improvement and Leather Development Services, Extension servi | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | MCG |  |  |  |  | 0.7% |  |  |  | PLANNED | [15 empty] | ongoing project
235 | Aquaculture development programme-Capture Fisheries (Dams and river ) & Fisheries extension support |  | ongoing |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [7 empty] | 9.2 | MCG | [8 empty] | PLANNED | [15 empty] | ongoing project
236 | Coffee Revitalization Project | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | World Bank |  |  |  | 0.72% | 2022 |  |  | ONGOING
237 | ARABIKA | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | ITALIAN AGENCY for Development cooperation (AICS) |  |  |  | 0.17% |  |  |  | PLANNED
238 | Kinogerama fcs processing water conservation | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | DP | GIZ |  |  |  | 0.3% |  |  |  | PLANNED | [15 empty] | completed
239 | Murang’a County Coffee Mill | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
240 | French beans marketing & pack house project | [8 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED | [15 empty] | Implemented by Directorate of Agribusiness and marketing
241 | Coffee roaster for Murang’a coffee farmers cooperative union | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG |  |  |  |  | 1% |  |  |  | PLANNED | [15 empty] | complete project
242 | Livestock Sheds | [8 empty] | AGRICULTURE | [9 empty] | MCG |  |  |  |  | 1% |  |  |  | COMPLETED | 100%
243 | Mbombo Marketing shed | [5 empty] | MARAGUA | NGINDA |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-09 | [5 empty] | MCG | no |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | completed and in use
244 | Market access project. Avocado value chain | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | no |  |  |  | 1% |  |  |  | COMPLETED | 100% | [14 empty] | Completed
245 | Kenyatta Agriculture Farmers Training Centre (Mariira farm ). Staff and farmers capacity building | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | No |  |  |  | 1% |  |  |  | ONGOING | [15 empty] | ongoing
246 | National Agricultyral Value Chains Development Project (NAVCDP) |  | To increase market participation for targeted farmers in select value chains in project areas | [6 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 1905-07-07 | [5 empty] | Mixed | World bank | [7 empty] | PLANNED
247 | Milk and Mango e-voucher subsidy progrmme | Farmers wallet quarterly credited Ksh 2400 |  |  |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  |  | 2023-01-01 | [5 empty] | MCG |  |  |  | 156 |  |  |  |  | PLANNED | [15 empty] | Programme benefitting 22,015 farmers
248 | Certified maize seeds and fertilizer subsidy programme | [5 empty] | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
249 | Disease control and Survelilance | Ring vaccinations againist Anthrax and LSD | [7 empty] | AGRICULTURE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries | [8 empty] | MCG | [8 empty] | PLANNED
251 | Kaganda V.T.C | 2 no shed & landscaping, workshop renovation | Improve perfomance | Conducive learning environment |  |  | KIHARU | MUGOIRI |  | EDUCATION | Education and Technical Training |  | 2021-10-08 | 2021-12-09 |  |  | 2650000 | 2650000 | 2650000 | GOK Subsidy |  |  | 100 | 2650000 | 100% | 2650000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
252 | Kaguku V.T.C | 2 no shed construction | Improve perfomance | Conducive learning environment |  |  | GATANGA | ITHANGA |  | EDUCATION | Education and Technical Training |  | 2021-10-08 |  |  |  | 2650000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
253 | Kahuti V.T.C | Workshop renovation, school gate, fencing, ablution block | Improve perfomance | Conducive learning environment |  |  | KIHARU | WANGU |  | EDUCATION | Education and Technical Training |  | 2021-10-08 | 2021-12-09 |  |  | 2500000 | 2500000 | 2500000 | GOK Subsidy |  |  | 100 | 2500000 | 100% | 2500000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
254 | Kambirwa V.T.C | Shed construction for training | Improve perfomance | Conducive learning environment |  |  | KIHARU | MBIRI |  | EDUCATION | Education and Technical Training |  | 2021-10-08 |  |  |  | 600000 | 600000 | 600000 | GOK Subsidy |  |  | 100 | 600000 | 100% | 600000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
255 | Kabiti V.T.C | shed construction & workshop renovation | Improve perfomance | Conducive learning environment |  |  | MARAGUA | KAMBITI |  | EDUCATION | Education and Technical Training |  | 2021-10-08 | 2021-10-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
256 | Kamukabi V.T.C | 2no; ablution block, shed, computer lab, workshop renovation | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KINYONA |  | EDUCATION | Education and Technical Training |  | 2021-10-08 |  |  |  | 2600000 | 2600000 | 2600000 | GOK Subsidy |  |  | 100 | 2600000 | 100% | 2600000 |  | 0 | ONGOING | 60% | 40% | underfunding | 2022
257 | Kamune V.T.C | Fencing and school gate construction | Improve security, health and sanitation | Conducive learning environment |  |  | KIHARU | MBIRI |  | EDUCATION | Education and Technical Training |  | 2021-10-08 |  |  |  | 1500000 | 1500000 | 1500000 | GOK Subsidy |  |  | 100 | 1500000 | 100% | 1500000 |  | 0 | PLANNED | 65% | 35% | underfunding | 2022
258 | Kiiriangoro V.T.C | shed construction & workshop renovation | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KIGUMO |  | EDUCATION | Education and Technical Training |  | 2021-10-08 |  |  |  | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
259 | Kimororo V.T.C | construction of 2 new sheds and workshop renovation | Improve perfomance | Conducive learning environment |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Education and Technical Training |  | 2021-10-08 |  |  |  | 2500000 | 2500000 | 2500000 | GOK Subsidy |  |  | 100 | 2500000 | 100% | 2500000 |  | 0 | COMPLETED | 100%
260 | Kirwara V.T.C | School gate, workshop renovation, institution cafeteria | Improve perfomance | Conducive learning environment |  |  | GATANGA | GATANGA |  | EDUCATION | Education and Technical Training |  | 2021-10-08 |  |  | 2022-12-05 | 2200000 | 2200000 | 2200000 | GOK Subsidy |  |  | 100 | 2200000 | 100% | 2200000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
261 | Michuki V.T.C | workshop renovation | Improve perfomance | Conducive learning environment |  |  | KANGEMA | MUGURU |  | EDUCATION | Education and Technical Training |  | 2021-10-08 | 2021-07-09 |  | 2022-03-05 | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
262 | Gatara V.T.C | Renovation & repair of workshops, painting | Improve perfomance | Conducive learning environment |  |  | KIHARU | MURARANDIA |  | EDUCATION | Education and Technical Training |  |  | 2019-10-09 |  |  | 1300000 | 1300000 | 1300000 | GOK Subsidy |  |  | 100 | 1300000 | 100% | 1300000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
263 | Giathanini V.T.C | Renovation & repair of workshops, painting | Improve perfomance | Conducive learning environment |  |  | GATANGA | ITHANGA |  | EDUCATION | Education and Technical Training |  |  | 2019-12-09 |  |  | 1000000 | 1000000 | 1000000 | GOK Subsidy |  |  | 100 | 1000000 | 100% | 1000000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
264 | Gikindu V.T.C | Administration block renovation | Improve perfomance | Conducive learning environment |  |  | MARAGUA | NGINDA |  | EDUCATION | Education and Technical Training |  |  | 2019-08-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
265 | Gikomora V.T.C | Renovation & repair of workshops, | Improve perfomance | Conducive learning environment |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Education and Technical Training |  |  | 2019-10-09 |  |  | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
266 | Ichagaki V.T.C | Renovation & repair of workshops,and classrroms | Improve perfomance | Conducive learning environment |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Education and Technical Training |  |  | 2019-10-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
267 | Kagandai V.T.C | Renovation of workshops and classrooms | Improve perfomance | Conducive learning environment |  |  | KIHARU | MURARANDIA |  | EDUCATION | Education and Technical Training |  |  | 2019-12-09 |  |  | 1187035 | 1187035 | 1187035 | GOK Subsidy |  |  | 100 | 1187035 | 100% | 1187035 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
268 | Kahuti V.T.C | Renovation of workshops and painting | Improve perfomance | Conducive learning environment |  |  | KIHARU | WANGU |  | EDUCATION | Education and Technical Training |  |  | 2019-12-09 |  |  | 1500000 | 1500000 | 1500000 | GOK Subsidy |  |  | 100 | 1500000 | 100% | 1500000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
269 | Kamahuha V.T.C | Renovation & repair of workshops, painting | Improve perfomance | Conducive learning environment |  |  | MARAGUA | KAMAHUHA |  | EDUCATION | Education and Technical Training |  |  | 2019-11-09 |  |  | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
270 | Kambirwa V.T.C | Renovation of workshops and classroom | Improve perfomance | Conducive learning environment |  |  | KIHARU | MBIRI |  | EDUCATION | Education and Technical Training |  |  | 2019-07-09 |  |  | 1000000 | 1000000 | 1000000 | GOK Subsidy |  |  | 100 | 1000000 | 100% | 1000000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
271 | Kabiti V.T.C | Renovation & repair of workshops, | Improve perfomance | Conducive learning environment |  |  | MARAGUA | KAMBITI |  | EDUCATION | Education and Technical Training |  |  | 2019-10-09 |  |  | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
272 | Kamukabi V.T.C | Administration block renovation | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KINYONA |  | EDUCATION | Education and Technical Training | [5 empty] | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
273 | Kamune V.T.C | Renovation & repair of workshops,and classrroms | Improve perfomance | Conducive learning environment |  |  | MATHIOYA | KAMACHARIA |  | EDUCATION | Education and Technical Training |  |  | 2019-10-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
274 | Kangari V.T.C | Renovation & repair of workshops. | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KANGARI |  | EDUCATION | Education and Technical Training | [5 empty] | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
275 | Kagunduini V.T.C. | Renovation & repair of workshops. | Improve perfomance | Conducive learning environment |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Education and Technical Training | [5 empty] | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
276 | Kanyuira V.T.C | Renovation of workshops and classroom | Improve perfomance | Conducive learning environment |  |  | KANGEMA | RWATHIA |  | EDUCATION | Education and Technical Training | [5 empty] | 1000000 | 1000000 | 1000000 | GOK Subsidy |  |  | 100 | 1000000 | 100% | 1000000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
277 | Karugia V.T.C | Renovation & repair of workshops, | Improve perfomance | Conducive learning environment |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Education and Technical Training |  |  | 2019-10-09 |  |  | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
278 | Kibaaka V.T.C | Renovation & repair of workshops. | Improve perfomance | Conducive learning environment |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Education and Technical Training |  |  | 2019-08-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
279 | Kigumo V.T.C | Renovation of workshops and classrooms | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KIGUMO |  | EDUCATION | Education and Technical Training |  |  | 2019-12-09 |  |  | 1500000 | 1500000 | 1500000 | GOK Subsidy |  |  | 100 | 1500000 | 100% | 1500000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
280 | KiiriangoroV.T.C | Renovation of workshops and classroom | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KIGUMO |  | EDUCATION | Education and Technical Training |  |  | 2019-07-09 |  |  | 850000 | 850000 | 850000 | GOK Subsidy |  |  | 100 | 850000 | 100% | 850000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
281 | Kimorori V.T.C | Renovation & repair of workshops | Improve perfomance | Conducive learning environment |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Education and Technical Training |  |  | 2019-11-09 |  |  | 500000 | 500000 | 500000 | GOK Subsidy |  |  | 100 | 500000 | 100% | 500000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
282 | Makombi V.T.C | Renovation & repair of workshops,and classrroms | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KANGARI |  | EDUCATION | Education and Technical Training |  |  | 2019-10-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
283 | Makuyu V.T.C | Renovation & repair of workshops | Improve perfomance | Conducive learning environment |  |  | MARAGUA | MAKUYU |  | EDUCATION | Education and Technical Training |  |  | 2019-11-09 |  |  | 500000 | 500000 | 500000 | GOK Subsidy |  |  | 100 | 500000 | 100% | 500000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
284 | Michuki V.T.C | Renovation & repair of workshops,and classrroms | Improve perfomance | Conducive learning environment |  |  | KANGEMA | MUGURU |  | EDUCATION | Education and Technical Training | [5 empty] | 900000 | 900000 | 900000 | GOK Subsidy |  |  | 100 | 900000 | 100% | 900000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
285 | Giathanini V.T.C | Construction of gate/chain link fencing | Improve security | Conducive learning environment |  |  | GATANGA | ITHANGA |  | EDUCATION | Education and Technical Training |  |  | 2020-10-09 |  |  | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
286 | Gikindu V.T.C | Workshop repairs & renovation | Improve perfomance | Conducive learning environment |  |  | MARAGUA | NGINDA |  | EDUCATION | Education and Technical Training |  |  | 2020-08-09 |  |  | 600000 | 600000 | 600000 | GOK Subsidy |  |  | 100 | 600000 | 100% | 600000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
287 | Gituamba V.T.C | Renovation & repair of workshops, painting | Improve perfomance | Conducive learning environment |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Education and Technical Training |  |  | 2020-10-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
288 | Gituamba V.T.C | Construction of toilets and classroom repairs | Improve perfomance | Conducive learning environment |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Education and Technical Training |  |  | 2020-10-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
289 | Ithiru V.T.C | Roofing of workshop, renovation of mvm workshop | Improve perfomance | Conducive learning environment |  |  | KANDARA | ITHIRU |  | EDUCATION | Education and Technical Training | [5 empty] | 900000 | 900000 | 900000 | GOK Subsidy |  |  | 100 | 900000 | 100% | 900000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
290 | Kagandai V.T.C | Construction of gate and chain link fencing | Improve perfomance | Conducive learning environment |  |  | KIHARU | MURARANDIA |  | EDUCATION | Education and Technical Training |  |  | 2020-12-09 |  |  | 1200000 | 1200000 | 1200000 | GOK Subsidy |  |  | 100 | 1200000 | 100% | 1200000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
291 | Kahumbu V.T.C | Renovation & repair of workshops, painting | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Education and Technical Training |  |  | 2020-10-09 |  | 2021-11-04 | 1000000 | 1000000 | 1000000 | GOK Subsidy |  |  | 100 | 1000000 | 100% | 1000000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
292 | Kahuro V.T.C | Construction of training shades | Improve perfomance | Conducive learning environment |  |  | KIHARU | MUGOIRI |  | EDUCATION | Education and Technical Training |  |  | 2020-08-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
293 | Kahuti V.T.C | Renovation of workshop and construction of training shades | Improve perfomance | Conducive learning environment |  |  | KIHARU | WANGU |  | EDUCATION | Education and Technical Training |  |  | 2020-12-09 |  |  | 1500000 | 1500000 | 1500000 | GOK Subsidy |  |  | 100 | 1500000 | 100% | 1500000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
294 | Kambirwa V.T.C | Renovation of workshops and classroom | Improve perfomance | Conducive learning environment |  |  | KIHARU | MBIRI |  | EDUCATION | Education and Technical Training | [5 empty] | 1000000 | 1000000 | 1000000 | GOK Subsidy |  |  | 100 | 1000000 | 100% | 1000000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
295 | Kabiti V.T.C | Renovation & repair of workshops, painting | Improve perfomance | Conducive learning environment |  |  | MARAGUA | KAMBITI |  | EDUCATION | Education and Technical Training |  |  | 2020-10-09 |  | 2021-11-04 | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
296 | Kamukabi V.T.C | Renovation & repair of workshops, painting | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KINYONA |  | EDUCATION | Education and Technical Training |  |  | 2020-10-09 |  |  | 1500000 | 1500000 | 1500000 | GOK Subsidy |  |  | 100 | 1500000 | 100% | 1500000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
297 | Kamune V.T.C | Stone pinching and renovation of workshops | Improve perfomance | Conducive learning environment |  |  | MATHIOYA | KAMACHARIA |  | EDUCATION | Education and Technical Training | [5 empty] | 1000000 | 1000000 | 1000000 | GOK Subsidy |  |  | 100 | 1000000 | 100% | 1000000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
298 | Kagunduini V.T.C | Construction of gate and trainees toilets | Improve perfomance | Conducive learning environment |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Education and Technical Training |  |  | 2020-10-09 |  | 2021-11-04 | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
299 | Kanyuira V.T.C | Renovation & repair of workshops. | Improve perfomance | Conducive learning environment |  |  | KANGEMA | RWATHIA |  | EDUCATION | Education and Technical Training | [5 empty] | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
300 | Karugia V.T.C | Renovation & repair of workshops. | Improve perfomance | Conducive learning environment |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Education and Technical Training | [5 empty] | 800000 | 800000 | 800000 | GOK Subsidy |  |  | 100 | 800000 | 100% | 800000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
301 | Kibaaka V.T.C | Construction of toilets and classroom repairs | Improve perfomance | Conducive learning environment |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Education and Technical Training |  |  | 2020-10-09 |  |  | 700000 | 700000 | 700000 | GOK Subsidy |  |  | 100 | 700000 | 100% | 700000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
302 | Kigumo V.T.C | Renovation & repair of workshops. | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KIGUMO |  | EDUCATION | Education and Technical Training |  |  | 2020-10-09 |  |  | 1300000 | 1300000 | 1300000 | GOK Subsidy |  |  | 100 | 1300000 | 100% | 1300000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
303 | Kiiriangoro V.T.C | Renovation & repair of workshops. | Improve perfomance | Conducive learning environment |  |  | KIGUMO | KIGUMO |  | EDUCATION | Education and Technical Training | [5 empty] | 850000 | 850000 | 850000 | GOK Subsidy |  |  | 100 | 850000 | 100% | 850000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
304 | Kimorori V.T.C | Renovation & repair of workshops. | Improve perfomance | Conducive learning environment |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Education and Technical Training | [5 empty] | 500000 | 500000 | 500000 | GOK Subsidy |  |  | 100 | 500000 | 100% | 500000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
305 | Makuyu V.T.C | Office renovation and portioning of ict workshop | Improve perfomance | Conducive learning environment |  |  | MARAGUA | MAKUYU |  | EDUCATION | Education and Technical Training | [5 empty] | 500000 | 500000 | 500000 | GOK Subsidy |  |  | 100 | 500000 | 100% | 500000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
306 | Michuki V.T.C | Construction of gate/ chain link fencing/toilets repair | Improve perfomance | Conducive learning environment |  |  | KANGEMA | MUGURU |  | EDUCATION | Education and Technical Training | [5 empty] | 900000 | 900000 | 900000 | GOK Subsidy |  |  | 100 | 900000 | 100% | 900000 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
307 | RUBIRU ECDE | Constraction of 2No. Classrooms | Improve perfomance | Conducive learning environment |  |  | GATANGA | ITHANGA |  | EDUCATION | Education and Technical Training |  | 2016-12-08 |  |  |  | 2917653 | 2917653 | 2917653 | MCG |  |  |  | 2917653 | 100% | 2917653 |  | 0 | COMPLETED | 100% | [12 empty] | YES |  | In use
308 | Maragua Hospital- Construction of Youth Friendly Centre and Waiting Bay | Construction of youth friendly centre and waiting bay at Maragua Hospital | Youth friendly centre and waiting bay at Maragua Hospital | Youth friendly centre and waiting bay at Maragua Hospital | Dev | Construction of youth friendly centre and waiting bay at Maragua Hospital | MARAGUA | NGINDA |  | HEALTH | Health and Sanitation | Maragua Hospital |  | 2015-06-16 | 2015-12-10 | 2015-11-12 | 1200000 | 1200000 |  | World Bank | World bank |  |  | 1200000 | 100% | 1200000 |  | 0 | COMPLETED | 100% |  |  |  |  | 1200000 | NO |  |  | YES |  | YES |  | YES
309 | Murang’a County - Referral Hosp Cancer centre | Establishment of a referral Cancer Centre | Treat Cancer patients in Murang'a | Functional Cancer Centre | Dev | Construction of Muranga MCRH Cancer centre | KIHARU | TOWNSHIP |  | HEALTH | Health and Sanitation |  |  | 2016-01-01 | 2017-12-12 |  | 50000000 | 50000000 | 50000000 | MCG | [8 empty] | STALLED | 0.1% | 10% | Insufficient funding | 2019 |  | 50000000 | NO |  |  | NO |  | NO |  | YES |  | Repurposed to Mother & Child Block
310 | Muriranjas Hospital - New Casualty | Construction of a New Casualty Unit at Muriranjas Hospital | Efficient Casualty and Emergency Services Unit | New Spacious Casualty Unit | Dev | New casualty Unit at Muriranjas Hospital | KIHARU | MUGOIRI |  | HEALTH | Health and Sanitation |  | 2016-05-10 | 2016-07-10 | 2017-05-04 | 2017-02-03 | 15000000 |  |  | MCG |  | 100 | [6 empty] | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO |  | Unit without equipment, Converted to computer garage in 2024
311 | Muriranjas Hospital - Renovation of gates | Renovation of 3 gates and Entrances at Muriranjas Hospital | Facelift of Hospital entrances | Renovated and Painted gates | Dev | Renovation of Gates and Roadside Signage at Muriranjas Hospital | KIHARU | MUGOIRI |  | HEALTH | Health and Sanitation |  | 2017-05-10 | 2017-07-10 | 2018-05-04 | 2018-02-03 | 150000 |  |  | MCG |  | 100 | [6 empty] | COMPLETED | 100% | [5 empty] | NO |  |  | YES |  | YES |  | YES |  | Completed & Functional gates with repainting and signage
312 | Murang’a C.R.H - Renal Unit | Establishment of a Renal Unit | Offer dialysis services to manage chronic kidney diseases | Fully equiped and functional Renal Unit | Dev | Construction of Muranga MCRH Renal Unit | KIHARU | TOWNSHIP |  | HEALTH | Health and Sanitation |  | 2018-02-01 | 2018-03-02 | 2019-06-01 | 2019-06-01 | 40000000 |  | 40000000 | MCG; Partners |  |  |  |  | 100% |  | 0 | 0 | COMPLETED | 100% | [8 empty] | YES | Waste disposal mechanism in Muranga | YES | Charges levied for maintenance & improvement | YES | Evaluation of project feasibility for community | Services expanded by new aimilar projects
313 | Murang’a C.R.H- Laboratory Extension | Laboratory Extension works | Expand Laboratory space | Expanded laboratory | Dev | Construction of Muranga Laboratory block extension | KIHARU | TOWNSHIP |  | HEALTH | Health and Sanitation |  | 2020-05-14 | 2020-07-16 | 2021-06-06 | 2025-06-13 |  | 2700000 |  | MCG |  | 1 |  | 2700000 | 100% |  | 0 | 0 | COMPLETED | 100% |  |  |  |  | 2700000 | NO |  |  | YES | Waste disposal mechanisms in place | YES |  | YES
314 | Murang’a C.R.H - I.C.U | Establishment of an I.C.U | Offer life support and manage life threatening conditions | Fully equiped and functional ICU | Dev | Construction of Muranga MCRH ICU | KIHARU | TOWNSHIP |  | HEALTH | Health and Sanitation |  | 2020-07-15 | 2020-09-10 | 2021-06-30 | 2020-12-30 | 134000000 | 134000000 | 134000000 | MCG |  |  |  | 134000000 | 100% |  |  | 0 | COMPLETED | 100% |  |  |  |  | 134000000 |  |  |  | YES | Waste disposal mechanism in Muranga | YES | Charges levied for maintenance & improvement | YES | Evaluation of project feasibility for community | Equipment maintenance necessary to run full capacity
315 | Kangema Hospital facelift | Facelift of Kangema Hospital | Renovation of Kangema Hospital |  | Dev | Renovation of Kangema Hospital | KANGEMA | MUGURU |  | HEALTH | Health and Sanitation |  | 2022-09-09 | 2022-11-10 | 2023-04-13 | 2022-12-12 | 10000000 |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO |  |  | YES |  | YES |  | YES
316 | Murang’a County- Blood Satelite Centre | Establishment of a Blood Satelite centre | Avail blood products in Murang'a County | Blood satellite centre | Dev | Construction of Murang'a County Blood Satellite Centre | KIHARU | TOWNSHIP |  | HEALTH | Health and Sanitation |  | 2022-10-13 | 2022-12-10 | 2023-06-14 | 2023-06-14 |  | 4900000 |  | MCG |  |  |  | 4900000 | 100% |  | 0 | 0 | COMPLETED | 100% |  |  |  |  | 4900000 | NO |  |  | YES | Waste disposal mechanisms in place | YES |  | YES
318 | Proposed Construction of Gakuyu & Gakarati ECDE Classrooms & Toilet Block - Kahumbu Ward | Proposed Construction of Gakuyu & Gakarati ECDE Classrooms & Toilet Block - Kahumbu Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
319 | Proposed Construction of Kahariro ECDE Class, Construction of St John the Baptist & Fencing of mwara ECDE Centres - Kahumbu Ward | Proposed Construction of Kahariro ECDE Class, Construction of St John the Baptist & Fencing of mwara ECDE Centres - Kahumbu Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
320 | Proposed Construction of 1No. Classroom ,Ablution Block to Kariciungu ECDE Centre - Kanyenya-ini Ward | Proposed Construction of 1No. Classroom ,Ablution Block to Kariciungu ECDE Centre - Kanyenya-ini Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
321 | Proposed Construction of 1No. Classroom ,Ablution Block at St John ECDE Centre - Kanyenya-ini Ward | Proposed Construction of 1No. Classroom ,Ablution Block at St John ECDE Centre - Kanyenya-ini Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
322 | Proposed Construction of Classroom & Toilet block at Kiburunjui ECDE Centre - Kimorori Ward. | Proposed Construction of Classroom & Toilet block at Kiburunjui ECDE Centre - Kimorori Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
323 | Proposed Construction of Classroom at Kamakuni ECDE Centre - Kimorori Wempa Ward. | Proposed Construction of Classroom at Kamakuni ECDE Centre - Kimorori Wempa Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
324 | Proposed Renovation of 2No. Classrooms for Thangira ECDE Centre - Kimorori Ward. | Proposed Renovation of 2No. Classrooms for Thangira ECDE Centre - Kimorori Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
325 | Proposed Construction of St. Teresa Pry ,Kanduri Pry & Thungururu Pry ECDE Centres - Ithanga Ward | Proposed Construction of St. Teresa Pry ,Kanduri Pry & Thungururu Pry ECDE Centres - Ithanga Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | GATANGA | ITHANGA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
326 | Proposed Construction of 1No. Classroom at Kirigu-ini ECDE centre & Renovation of 2No. Classrooms at Gakui & Kirunguru ECDE Centres - Kiru Ward | Proposed Construction of 1No. Classroom at Kirigu-ini ECDE centre & Renovation of 2No. Classrooms at Gakui & Kirunguru ECDE Centres - Kiru Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
327 | Proposed construction of Toilet Blocks at gaichanjiru ECDE,Kawanjeru ECDE,Kariua Playground, Githigi ECDE, & Karugia ECDE - Gaichanjiru Ward. | Proposed construction of Toilet Blocks at gaichanjiru ECDE,Kawanjeru ECDE,Kariua Playground, Githigi ECDE, & Karugia ECDE - Gaichanjiru Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
328 | Proposed construction of Kari ECDE centre & Renovation of Mwara ECDE Centre - Mugoiri Ward | Proposed construction of Kari ECDE centre & Renovation of Mwara ECDE Centre - Mugoiri Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
329 | Proposed construction of Gikigie ECDE Centre & Renovation of Matu ECDE Centre -Kinyona Ward. | Proposed construction of Gikigie ECDE Centre & Renovation of Matu ECDE Centre -Kinyona Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
330 | Proposed Construction of Wanjerere ECDE Classroom - Rwathia Ward | Proposed Construction of Wanjerere ECDE Classroom - Rwathia Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KANGEMA | RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
331 | Proposed renovation of Kairichi & Murarandia ECDE Centres - Murarandia Ward | Proposed renovation of Kairichi & Murarandia ECDE Centres - Murarandia Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
332 | Proposed Fabrication and installation of Swings at Gaitega, Gakunya & Muchungucha ECDE Centres - Mbiri Ward. | Proposed Fabrication and installation of Swings at Gaitega, Gakunya & Muchungucha ECDE Centres - Mbiri Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
333 | Proposed Fabrication and installation of Swings at Gikuu,Gikandu & Thangathi ECDE Centres - Mbiri Ward. | Proposed Fabrication and installation of Swings at Gikuu,Gikandu & Thangathi ECDE Centres - Mbiri Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
334 | Proposed Construction of Kirima ,Kigongo ,Gatitu & Kiambugi ECDE Centres -Gaturi Ward | Proposed Construction of Kirima ,Kigongo ,Gatitu & Kiambugi ECDE Centres -Gaturi Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
335 | Proposed Construction of 1No. Classroom at Kiruru ECDE centre,Renovation of Mioro ECDE Centre, Construction of Mirere-ini ECDE & Kiruru ECDE Ablution Block & Renovation of Kianyingi ECDE Centre - Kiru Ward. | Proposed Construction of 1No. Classroom at Kiruru ECDE centre,Renovation of Mioro ECDE Centre, Construction of Mirere-ini ECDE & Kiruru ECDE Ablution Block & Renovation of Kianyingi ECDE Centre - Kiru Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
336 | Proposed renovation of 1No. Classroom at Iregi ECDE & Construction of 1No. Classroom at Gakoigo Pry ECDE Centre - Nginda Ward. | Proposed renovation of 1No. Classroom at Iregi ECDE & Construction of 1No. Classroom at Gakoigo Pry ECDE Centre - Nginda Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | MARAGUA | NGINDA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
337 | Proposed construction of Boda Boda Sheds at Maragua Town, Nginda Jct & Kiangoma Jct & Construction of Ablution Blocks at Gikindu ECDE Centre & Irembu Shopping Centre - Nginda Ward. | Proposed construction of Boda Boda Sheds at Maragua Town, Nginda Jct & Kiangoma Jct & Construction of Ablution Blocks at Gikindu ECDE Centre & Irembu Shopping Centre - Nginda Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | MARAGUA | NGINDA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
338 | Proposed construction of Kibaaka ECDE centre | Proposed construction of Kibaaka ECDE centre | provide learners with conducive learning enviroment . | No.of classroom done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
339 | Proposed renovation of Mukarara and Thuita Pry ECDE centres | Proposed renovation of Mukarara and Thuita Pry ECDE centres | provide learners with conducive learning enviroment . | No.of classroom done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
340 | Proposed Renovation of Kiunyu A & Nyaga ECDE Centre | Proposed Renovation of Kiunyu A & Nyaga ECDE Centre | provide learners with conducive learning enviroment . | No.of classroom done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
341 | Proposed renovation and construction of classrooms at Kihumbu-ini Pry ECDE centre | Proposed renovation and construction of classrooms at Kihumbu-ini Pry ECDE centre | provide learners with conducive learning enviroment . | No.of classroom done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
342 | Proposed Construction of classroom at Ngatho Pry ECDE centre & Renovation of Swani Pry ECDE Centre - Kakuzi Ward | Proposed Construction of classroom at Ngatho Pry ECDE centre & Renovation of Swani Pry ECDE Centre - Kakuzi Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
343 | Proposed renovation of 2No. Classrooms for Marriira Pry & Ikumbi Pry ECDE Centres - Kangari WARD | Proposed renovation of 2No. Classrooms for Marriira Pry & Ikumbi Pry ECDE Centres - Kangari WARD | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIGUMO | KANGARI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
344 | Proposed Renovation for 2No. Classrooms for Mwarano Pry & Ngurwe-ini ECDE Centres - Kangari Ward. | Proposed Renovation for 2No. Classrooms for Mwarano Pry & Ngurwe-ini ECDE Centres - Kangari Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIGUMO | KANGARI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
345 | Proposed Construction & Renovation of 2No. Classrooms for Gatimu Pry Aberdare peak Pry & Mairi Pry School ECDE Centres - Kangari Ward. | Proposed Construction & Renovation of 2No. Classrooms for Gatimu Pry Aberdare peak Pry & Mairi Pry School ECDE Centres - Kangari Ward. | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIGUMO | KANGARI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
346 | Proposed Construction of 2No. Classroooms ,AblutionBlock & fencing of Karuri ECDE Centre - Muthithi Ward | Proposed Construction of 2No. Classroooms ,AblutionBlock & fencing of Karuri ECDE Centre - Muthithi Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIGUMO | MUTHITHI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
347 | Proposed Construction of 2No. Classroooms at Thamara ECDE Centre - Muthithi Ward | Proposed Construction of 2No. Classroooms at Thamara ECDE Centre - Muthithi Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KIGUMO | MUTHITHI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
348 | Proposed Construction of 1No. Classroom at Ngurunga ECDE - Makuyu Ward | Proposed Construction of 1No. Classroom at Ngurunga ECDE - Makuyu Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | MARAGUA | MAKUYU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
349 | Proposed Renovation of 2No. Classrooms for Kiairathe Pry & Kangema Pry ECDE Centres -Muguru Ward | Proposed Renovation of 2No. Classrooms for Kiairathe Pry & Kangema Pry ECDE Centres -Muguru Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
350 | Proposed Construction of Ablution block at Naaro ECDE Centre - Ngararia Ward | Proposed Construction of Ablution block at Naaro ECDE Centre - Ngararia Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
351 | Proposed Construction of 1No. Class at Muirii-ini ECDE Centre - Ngararia Ward | Proposed Construction of 1No. Class at Muirii-ini ECDE Centre - Ngararia Ward | provide learners with conducive learning enviroment . | No.of classroom done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
352 | Proposed Improvement of Parking area to Ngoe-ini Dispensary - Kanyenya-ini Ward | Proposed Improvement of Parking area to Ngoe-ini Dispensary - Kanyenya-ini Ward | To improve healthcare | No.of health centers done |  |  | KANGEMA | KANYENYAINI |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
353 | Proposed Construction of perimeter Wall & Ablution Block to Gatangara Dispensary - Kanyenya-ini Ward | Proposed Construction of perimeter Wall & Ablution Block to Gatangara Dispensary - Kanyenya-ini Ward | To improve healthcare | No.of health centers done |  |  | KANGEMA | KANYENYAINI |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
354 | Proposed Construction of Mwania Mbogo Dispensary - Ithanga Ward | Proposed Construction of Mwania Mbogo Dispensary - Ithanga Ward | To improve healthcare | No.of health centers done |  |  | GATANGA | ITHANGA |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
355 | Proposed Construction of a Perimeter wall for Mukerenju dispensary - Kagundu-ini Ward | Proposed Construction of a Perimeter wall for Mukerenju dispensary - Kagundu-ini Ward | To improve healthcare | No.of health centers done |  |  | KANDARA | KAGUNDUINI |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
356 | Proposed Fencing of Kagumo-ini Grading Shed & Kariua Dispensary - Gaichanjiru Ward | Proposed Fencing of Kagumo-ini Grading Shed & Kariua Dispensary - Gaichanjiru Ward | To improve healthcare | No.of health centers done |  |  | KANDARA | GAICHANJIRU |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
357 | Proposed Conversion of Classrooms to Dispensary at Kahuro - Mugoiri Ward | Proposed Conversion of Classrooms to Dispensary at Kahuro - Mugoiri Ward | To improve healthcare | No.of health centers done |  |  | KIHARU | MUGOIRI |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
358 | Proposed Renovations of Gitaro Dispensary - Mugoiri Ward | Proposed Renovations of Gitaro Dispensary - Mugoiri Ward | To improve healthcare | No.of health centers done |  |  | KIHARU | MUGOIRI |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
359 | Proposed Construction of Kiria-ini Dispensary -Phase 1 & Refurbishment of Chomo Market -Gatanga Ward | Proposed Construction of Kiria-ini Dispensary -Phase 1 & Refurbishment of Chomo Market -Gatanga Ward | To improve healthcare | No.of health centers done |  |  | GATANGA | GATANGA |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
360 | Proposed Construction of Gaichangere & Theri Dispensaries - Phase 1 - Murarandia Ward | Proposed Construction of Gaichangere & Theri Dispensaries - Phase 1 - Murarandia Ward | To improve healthcare | No.of health centers done |  |  | KIHARU | MURARANDIA |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
361 | Proposed Renovation of Kihari Dispensary - Kiru Ward. | Proposed Renovation of Kihari Dispensary - Kiru Ward. | To improve healthcare | No.of health centers done |  |  | MATHIOYA | KIRU |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
362 | Proposed Construction of Gathunya laboratory,X-ray, Pharmacy, & Theartre - Kamacharia Ward | Proposed Construction of Gathunya laboratory,X-ray, Pharmacy, & Theartre - Kamacharia Ward | To improve healthcare | No.of health centers done |  |  | MATHIOYA | KAMACHARIA |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
363 | Proposed Construction of Waiting Bay at Kangema Hospital Mortuary - Muguru Ward | Proposed Construction of Waiting Bay at Kangema Hospital Mortuary - Muguru Ward | To improve healthcare | No.of health centers done |  |  | KANGEMA | MUGURU |  | HEALTH | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
364 | Proposed roadworks of Kigio - Chania -Laini Access roads - Mugumo-ini Ward | Proposed roadworks of Kigio - Chania -Laini Access roads - Mugumo-ini Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
365 | Proposed roadworks of Gichagi -Matinga Access roads - Mugumo-ini Ward | Proposed roadworks of Gichagi -Matinga Access roads - Mugumo-ini Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
366 | Proposed roadworks of Kigo - Gichagi JCT Access roads - Mugumo-ini Ward | Proposed roadworks of Kigo - Gichagi JCT Access roads - Mugumo-ini Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
367 | Proposed Opening of Access roads - Kahumbu Ward | Proposed Opening of Access roads - Kahumbu Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
368 | Proposed road Works of Mugumo-ini Mbari Ya Kiongo - Kwa Mototo - Kianda Kia Mbui - Karinga Access roads - Kahumbu Ward. | Proposed road Works of Mugumo-ini Mbari Ya Kiongo - Kwa Mototo - Kianda Kia Mbui - Karinga Access roads - Kahumbu Ward. | To improve accessibility | No. of KMs done |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
369 | Proposed road Works of Mwati Access roads - Kahumbu Ward. | Proposed road Works of Mwati Access roads - Kahumbu Ward. | To improve accessibility | No. of KMs done |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
370 | Proposed road Works of Kiawathuya Access roads - Kahumbu Ward. | Proposed road Works of Kiawathuya Access roads - Kahumbu Ward. | To improve accessibility | No. of KMs done |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
371 | Proposed road Works of Gati - Iguru Access roads - Kahumbu Ward. | Proposed road Works of Gati - Iguru Access roads - Kahumbu Ward. | To improve accessibility | No. of KMs done |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
372 | Proposed Grading with Compaction of Kanyenya-ini Ward Access Roads - Kanyenya-ini Ward | Proposed Grading with Compaction of Kanyenya-ini Ward Access Roads - Kanyenya-ini Ward | To improve accessibility | No. of KMs done |  |  | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
373 | Proposed Supply Spreading & Compaction of laterite Gravel to Varoius access roads - Kanyenya-ini Ward -125 Lorries | Proposed Supply Spreading & Compaction of laterite Gravel to Varoius access roads - Kanyenya-ini Ward -125 Lorries | To improve accessibility | No. of KMs done |  |  | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
374 | Proposed road works of Kanjiru Access roads - Ngararia Ward | Proposed road works of Kanjiru Access roads - Ngararia Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
375 | Proposed road works of Kamutungi Access roads - Ngararia Ward | Proposed road works of Kamutungi Access roads - Ngararia Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
376 | Proposed road works of Waitua Access roads - Ngararia Ward | Proposed road works of Waitua Access roads - Ngararia Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
377 | Proposed road works of Kibereke - Kariko Access road -Ngararia ward | Proposed road works of Kibereke - Kariko Access road -Ngararia ward | To improve accessibility | No. of KMs done |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
378 | Proposed Opening of Access roads - Gitugi Ward. | Proposed Opening of Access roads - Gitugi Ward. | To improve accessibility | No. of KMs done |  |  | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
379 | Proposed road works of Gitugi -Murera Access road -2.5Km - Gitugi Ward | Proposed road works of Gitugi -Murera Access road -2.5Km - Gitugi Ward | To improve accessibility | No. of KMs done |  |  | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
380 | Proposed roadworks of Gatui- Mihuti Access roads - Gitugi Ward | Proposed roadworks of Gatui- Mihuti Access roads - Gitugi Ward | To improve accessibility | No. of KMs done |  |  | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
381 | Proposed road works oof Kigurumo - Murera Access roads- Gitugi Ward | Proposed road works oof Kigurumo - Murera Access roads- Gitugi Ward | To improve accessibility | No. of KMs done |  |  | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
382 | Proposed road works of Ruiru Pry Access road - Gitugi Ward | Proposed road works of Ruiru Pry Access road - Gitugi Ward | To improve accessibility | No. of KMs done |  |  | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
383 | Proposed road works of Karumu - Riairo - Kiranga Coffee Factory Access road - 5.5 Km - Muruka Ward | Proposed road works of Karumu - Riairo - Kiranga Coffee Factory Access road - 5.5 Km - Muruka Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
384 | Proposed road Works of Kiranga Shopping Centre - Kwa Francis - Ngirima - Nganga-ini - Muruka Coffee Factory Access road - Muruka Ward | Proposed road Works of Kiranga Shopping Centre - Kwa Francis - Ngirima - Nganga-ini - Muruka Coffee Factory Access road - Muruka Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
385 | Proposed road works of Nguthuru Catholic - Gatumbu Shoppping Centre Access road - Muruka Ward | Proposed road works of Nguthuru Catholic - Gatumbu Shoppping Centre Access road - Muruka Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
386 | Proposed road works of Githama - Gathangari & Kabuku Nguthuru Secondary Access road - Muruka Ward | Proposed road works of Githama - Gathangari & Kabuku Nguthuru Secondary Access road - Muruka Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
387 | Proposed roadworks of Mangoto B,Karungangi access road & Gikono - Kahuri-Kangangu & Thangira - Kihunguro Access roads - Kimorori Wempa Ward. | Proposed roadworks of Mangoto B,Karungangi access road & Gikono - Kahuri-Kangangu & Thangira - Kihunguro Access roads - Kimorori Wempa Ward. | To improve accessibility | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
388 | Proposed roadworks of Wempa Access roads - Kimorori Ward | Proposed roadworks of Wempa Access roads - Kimorori Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
389 | Proposed roadworks of PCEA Church -Railway ,PEFA Kangangu Shopping Centre -Demote , Kameigua access roads - Kimorori Ward. | Proposed roadworks of PCEA Church -Railway ,PEFA Kangangu Shopping Centre -Demote , Kameigua access roads - Kimorori Ward. | To improve accessibility | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
390 | Proposed roadworks of Senior Chief - ACC & S - Chief Camp & White house mingungugo Highway - Slaughter Access roads - Kimorori Wempa Ward. | Proposed roadworks of Senior Chief - ACC & S - Chief Camp & White house mingungugo Highway - Slaughter Access roads - Kimorori Wempa Ward. | To improve accessibility | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
391 | Proposed roadworks of Katika river road Section,& Mwania Mbogo road Section -Ithanga Ward | Proposed roadworks of Katika river road Section,& Mwania Mbogo road Section -Ithanga Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | ITHANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
392 | Proposed opening of Access roads - Ithanga Ward. | Proposed opening of Access roads - Ithanga Ward. | To improve accessibility | No. of KMs done |  |  | GATANGA | ITHANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
393 | Proposed road Works of Kamoro Nursery ,Haguru By pass & Kiiri - Gakui Access road - Ithiru Wrad | Proposed road Works of Kamoro Nursery ,Haguru By pass & Kiiri - Gakui Access road - Ithiru Wrad | To improve accessibility | No. of KMs done |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
394 | Proposed road Works of Gathingira -Boboti, Kiguoya Pry - Gathamba , & Charagu - Kandara Access road - Ithiru Wrad | Proposed road Works of Gathingira -Boboti, Kiguoya Pry - Gathamba , & Charagu - Kandara Access road - Ithiru Wrad | To improve accessibility | No. of KMs done |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
395 | Proposed road Works of Ndiara , Kirunguru & Kirungu redeemed Church Access road - Ithiru Wrad | Proposed road Works of Ndiara , Kirunguru & Kirungu redeemed Church Access road - Ithiru Wrad | To improve accessibility | No. of KMs done |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
396 | Proposed roadworks of Riandegwa - Mureba Access roads - Kagundu-ini Ward | Proposed roadworks of Riandegwa - Mureba Access roads - Kagundu-ini Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
397 | Proposed road works of Gambu - Githunguri Access roads - Kagundu-ini Ward | Proposed road works of Gambu - Githunguri Access roads - Kagundu-ini Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
398 | Proposed roaworks of Karigu-ini - Kamwangi Acess roads - Kagundu-ini Ward | Proposed roaworks of Karigu-ini - Kamwangi Acess roads - Kagundu-ini Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
399 | Proposed roadworks of Mahuti-ini - Gaci Access road - Kagundu-ini Ward | Proposed roadworks of Mahuti-ini - Gaci Access road - Kagundu-ini Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
400 | Proposed Opening & Grading of access roads - Gaichanjiru Ward | Proposed Opening & Grading of access roads - Gaichanjiru Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
401 | Proposed Supply & Installation of Culverts & Gabions Across Gaichanjiru Ward | Proposed Supply & Installation of Culverts & Gabions Across Gaichanjiru Ward | To improve accessibility | No. of culverts and gabions done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
402 | Proposed roadworks of Kaburi & Kwa Mariu & Kamae - Ndonga Access roads - Gaichanjiru Ward. | Proposed roadworks of Kaburi & Kwa Mariu & Kamae - Ndonga Access roads - Gaichanjiru Ward. | To improve accessibility | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
403 | Proposed roadworks of Kagira By-Pass,Thangari Sodom & Kibiku & Gatitu-ini - Gitiye Access roads - Gaichanjiru Ward | Proposed roadworks of Kagira By-Pass,Thangari Sodom & Kibiku & Gatitu-ini - Gitiye Access roads - Gaichanjiru Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
404 | Proposed road works of Githagara Access roads - Mugoiri Ward | Proposed road works of Githagara Access roads - Mugoiri Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
405 | Proposed road works of Munyutha Access roads - Mugoiri Ward | Proposed road works of Munyutha Access roads - Mugoiri Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
406 | Proposed road works of Gitiri Access roads - Mugoiri Ward | Proposed road works of Gitiri Access roads - Mugoiri Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
407 | Proposed road works of Kari Access roads - Mugoiri Ward | Proposed road works of Kari Access roads - Mugoiri Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
408 | Proposed road works of Gatuikira -Mukangu Coffee Factory , AIC Kiru - ACC&S Gaturi ,Ngurumo cia Thika Kwa Asili -Gachau ,Gikuru -Mbari ya Ngatho -Mugumo-ini JCT Access roads 4.2Km -Ruchu Ward | Proposed road works of Gatuikira -Mukangu Coffee Factory , AIC Kiru - ACC&S Gaturi ,Ngurumo cia Thika Kwa Asili -Gachau ,Gikuru -Mbari ya Ngatho -Mugumo-ini JCT Access roads 4.2Km | To improve accessibility | No. of KMs done |  |  | KANDARA | RUCHU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
409 | Proposed roadworks of Ngoe -Kangunu & Gacharage dispensary access road - Ruchu Ward | Proposed roadworks of Ngoe -Kangunu & Gacharage dispensary access road - Ruchu Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | RUCHU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
410 | Proposed roadworks of Kiganjo Sabastian 83 Mwalimu , Mwihoko & Kai-rini -Utugi Factory Access roads - Ruchu Ward | Proposed roadworks of Kiganjo Sabastian 83 Mwalimu , Mwihoko & Kai-rini -Utugi Factory Access roads - Ruchu Ward | To improve accessibility | No. of KMs done |  |  | KANDARA | RUCHU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
411 | Proposed road Woks of Kahunyo - Gikurai , Gathuthu, & Gathuthu Pry Loop Access Road - Gatanga Ward. | Proposed road Woks of Kahunyo - Gikurai , Gathuthu, & Gathuthu Pry Loop Access Road - Gatanga Ward. | To improve accessibility | No. of KMs done |  |  | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
412 | Proposed road Works of Gathanji-Kiriti ,Nagara- Kagongo & Kagiri - Ndiara Access road - Gatanga Ward | Proposed road Works of Gathanji-Kiriti ,Nagara- Kagongo & Kagiri - Ndiara Access road - Gatanga Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
413 | Proposed Road Works of Mabanda -Gachonde , Gwa Kimatu - Gathungururu & Kiaruguru -Mburu - Kimata Access road - Gatanga Ward | Proposed Road Works of Mabanda -Gachonde , Gwa Kimatu - Gathungururu & Kiaruguru -Mburu - Kimata Access road - Gatanga Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
414 | Proposed road works of Kaninia ,Rwegetha Pry Loop , Rwegetha Kwa Amos & Kagongo Access Road - Gatanga Ward | Proposed road works of Kaninia ,Rwegetha Pry Loop , Rwegetha Kwa Amos & Kagongo Access Road - Gatanga Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
415 | Proposed roadworks of Nguku -Karia-ini -Kamae-& Kiini Access roads - Kigumo Ward | Proposed roadworks of Nguku -Karia-ini -Kamae-& Kiini Access roads - Kigumo Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
416 | Proposed roadworks of Miigu-ini Access road - Kigumo Ward | Proposed roadworks of Miigu-ini Access road - Kigumo Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
417 | Proposed roadworks of Miigu-ini Access road - Kigumo Ward | Proposed roadworks of Miigu-ini Access road - Kigumo Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
418 | Proposed roadworks of Kanjuhiu & Mutiria Access road - Kigumo Ward | Proposed roadworks of Kanjuhiu & Mutiria Access road - Kigumo Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
419 | Proposed roadworks of Mutinia ,Kiroro-ini Karega - Suta, Kihoto Kigumo pry stairs & Waruhiti Stairs Access road - Kigumo Ward | Proposed roadworks of Mutinia ,Kiroro-ini Karega - Suta, Kihoto Kigumo pry stairs & Waruhiti Stairs Access road | To improve accessibility | No. of KMs done |  |  | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
420 | Proposed roadworks of Kiara Kamuchara Access road - Kigumo Ward | Proposed roadworks of Kiara Kamuchara Access road - Kigumo Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
421 | Proposed Buying ,Excavation & loading of Laterite Gravel for road Construction - Kariara Ward | Proposed Buying ,Excavation & loading of Laterite Gravel for road Construction - Kariara Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
422 | Proposed Grading of Access roads (200Hrs) - Kariara ward | Proposed Grading of Access roads (200Hrs) - Kariara ward | To improve accessibility | No. of KMs done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
423 | Proposed supply & Installation of Cabro Paving Slabs at Gatura Shopping Centre - Kariara Ward | Proposed supply & Installation of Cabro Paving Slabs at Gatura Shopping Centre - Kariara Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
424 | Proposed supply & Installation of Cabro Paving Slabs at Kanunga Shopping Centre - Kariara Ward | Proposed supply & Installation of Cabro Paving Slabs at Kanunga Shopping Centre - Kariara Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
425 | Proposed Road Works of Gatumbi - Kandegwa Access road - Kinyona Ward | Proposed Road Works of Gatumbi - Kandegwa Access road - Kinyona Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
426 | Proposed road works of Gachocho - Gathama access road | Proposed road works of Gachocho - Gathama access road | To improve accessibility | No. of KMs done | [5 empty] | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
427 | Proposed Road works of Kaana - Bani - Maragwa - Ngurunga Access road - Kinyona Ward | Proposed Road works of Kaana - Bani - Maragwa - Ngurunga Access road - Kinyona Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
428 | Proposed road works of Ngurunga - Ngorogoco access road | Proposed road works of Ngurunga - Ngorogoco access road | To improve accessibility | No. of KMs done | [5 empty] | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
429 | Proposed roadworks of Wathani Acess road - Rwathia Ward | Proposed roadworks of Wathani Acess road - Rwathia Ward | To improve accessibility | No. of KMs done |  |  | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
430 | Proposed Opening of Rwathia Access roads - Rwathia Ward. | Proposed Opening of Rwathia Access roads - Rwathia Ward. | To improve accessibility | No. of KMs done |  |  | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
431 | Proposed roadworks of Kahari access roads - Rwathia Ward. | Proposed roadworks of Kahari access roads - Rwathia Ward. | To improve accessibility | No. of KMs done |  |  | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
432 | Proposed road works of Thangathi Access roads - Rwathia Ward. | Proposed road works of Thangathi Access roads - Rwathia Ward. | To improve accessibility | No. of KMs done |  |  | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
433 | Proposed road works of Gatuya - Kiriko access roads - Murarandia Ward | Proposed road works of Gatuya - Kiriko access roads - Murarandia Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
434 | Proposed Grading Access Roads - Murarandia Ward | Proposed Grading Access Roads - Murarandia Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
435 | Proposed road works of Kiawanyungu - Kariara Access road - Township ward | Proposed road works of Kiawanyungu - Kariara Access road - Township ward | To improve accessibility | No. of KMs done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
436 | Proposed road works of access roads at Kongo-ini ,Karugos ,kandundu & Kabwe Access roads -Township Ward | Proposed road works of access roads at Kongo-ini ,Karugos ,kandundu & Kabwe Access roads -Township Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
437 | Proposed road Works of Gitige - Kiamwohe Acess road - Ichagaki Ward | Proposed road Works of Gitige - Kiamwohe Acess road - Ichagaki Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
438 | Proposed road Works of Kibura - kamuraya Acess road - Ichagaki Ward | Proposed road Works of Kibura - kamuraya Acess road - Ichagaki Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
439 | Proposed road Works of Mugumo-ini - Ikuyu Acess road - Ichagaki Ward | Proposed road Works of Mugumo-ini - Ikuyu Acess road - Ichagaki Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
440 | Proposed road Works of Karira - Kaweru - Yatta Access road - Ichagaki Ward | Proposed road Works of Karira - Kaweru - Yatta Access road - Ichagaki Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
441 | Proposed Road Works of Githigi - Gichugu - Kiamakumi Access road - Ichagaki Ward. | Proposed Road Works of Githigi - Gichugu - Kiamakumi Access road - Ichagaki Ward. | To improve accessibility | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
442 | Proposed road Works of Mima Gardens - Mariki -Sofla Access road - Ichagaki Ward | Proposed road Works of Mima Gardens - Mariki -Sofla Access road - Ichagaki Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
443 | Proposed road Works of Kamucheru - Gwa Kangethe - Kianjiru-ini Access road - Ichagaki Ward | Proposed road Works of Kamucheru - Gwa Kangethe - Kianjiru-ini Access road - Ichagaki Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
444 | Proposed Opening of Access road - Ichagaki Ward | Proposed Opening of Access road - Ichagaki Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
445 | Proposed Grading of Mbiri Ward Access roads(100 hrs) - Mbiri Ward | Proposed Grading of Mbiri Ward Access roads(100 hrs) - Mbiri Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
446 | Proposed road works of Ndikwe - Gaitega - Gikandu Access roads - Mbiri Ward | Proposed road works of Ndikwe - Gaitega - Gikandu Access roads - Mbiri Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
447 | Proposed road works of Gitungano -Gikuu - Kambirwa- - Matithi Access roads - Mbiri Ward | Proposed road works of Gitungano -Gikuu - Kambirwa- - Matithi Access roads - Mbiri Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
448 | Proposed roadworks of Kau - Kiamuri Access roads - Gaturi Ward. | Proposed roadworks of Kau - Kiamuri Access roads - Gaturi Ward. | To improve accessibility | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
449 | Proposed Opening & Grading of Access roads - Gaturi Ward | Proposed Opening & Grading of Access roads - Gaturi Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
450 | Proposed roadworks of Gaturi -Kimio Access road - Gaturi ward | Proposed roadworks of Gaturi -Kimio Access road - Gaturi ward | To improve accessibility | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
451 | Proposed Supply & Installation of Cabro Paving Slabs at Gacharage-ini Shopping Centre - Kiru Ward. | Proposed Supply & Installation of Cabro Paving Slabs at Gacharage-ini Shopping Centre - Kiru Ward. | To improve accessibility | No. of KMs done |  |  | MATHIOYA | KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
452 | Proposed road Works of Kagumoi-ini Dispensary & feeder roads,Gachanja - Kiamuturi, kanjama - Mathare,Kiruru - Rwarae & umbui - Gikoe Access roads - Kiru Ward. | Proposed road Works of Kagumoi-ini Dispensary & feeder roads,Gachanja - Kiamuturi, kanjama - Mathare,Kiruru - Rwarae & umbui - Gikoe Access roads | To improve accessibility | No. of KMs done |  |  | MATHIOYA | KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
453 | Proposed road Works of Kiambuthia Access road - Kiru Ward. | Proposed road Works of Kiambuthia Access road - Kiru Ward. | To improve accessibility | No. of KMs done |  |  | MATHIOYA | KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
454 | Proposed opening of Access roads - Kamahuha Ward | Proposed opening of Access roads - Kamahuha Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
455 | Proposed Road Works of Iganjo Access roads - Kamahuha Ward | Proposed Road Works of Iganjo Access roads - Kamahuha Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
456 | Proposed Road Works of Kamahuha Access roads - Kamahuha Ward | Proposed Road Works of Kamahuha Access roads - Kamahuha Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
457 | Proposed Road Works of Sabasaba Access roads - Kamahuha Ward | Proposed Road Works of Sabasaba Access roads - Kamahuha Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
458 | Proposed Road Works of Wathia-ni Access roads - Kamahuha Ward | Proposed Road Works of Wathia-ni Access roads - Kamahuha Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
459 | Proposed Road Works of Kaharati Access roads - Kamahuha Ward | Proposed Road Works of Kaharati Access roads - Kamahuha Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
460 | Proposed Road Works of Nyati -Kiha & Kiamwenye Access roads - Kamahuha Ward | Proposed Road Works of Nyati -Kiha & Kiamwenye Access roads - Kamahuha Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
461 | Proposed opening & Grading of Access roads - Nginda Ward | Proposed opening & Grading of Access roads - Nginda Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
462 | Proposed road works of Gathera -Kiangoma ,Gitumbi & Iregi Access roads - Nginda Ward | Proposed road works of Gathera -Kiangoma ,Gitumbi & Iregi Access roads - Nginda Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
463 | Proposed road works of Lamek, Rukui, Kamoni, Gikunguru -Ihiga, Kanae & Gakoigo -Gikindu Access roads -Nginda Ward | Proposed road works of Lamek, Rukui, Kamoni, Gikunguru -Ihiga, Kanae & Gakoigo -Gikindu Access roads -Nginda Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
464 | Proposed road Works of Kiangoma - Kiringiti, Ititu - Maragua Pry Access, Ruchu - Kaweru, Kwamucumbi, Gikindu -Kianda & Gakoigo B Access Roads - Nginda Ward. | Proposed road Works of Kiangoma - Kiringiti, Ititu - Maragua Pry Access, Ruchu - Kaweru, Kwamucumbi, Gikindu -Kianda & Gakoigo B Access Roads - Nginda Ward. | To improve accessibility | No. of KMs done |  |  | MARAGUA | NGINDA |  |  | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
465 | Proposed road works of Gathama- Thuita access and Rurii- Kiunyu access road | Proposed road works of Gathama- Thuita access and Rurii- Kiunyu access road | To improve accessibility | No. of KMs done |  |  | GATANGA | KIHUMBUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
466 | Proposed Supply & Installation of Cabro Paving Slabs at Mukarara Shopping Centre | Proposed Supply & Installation of Cabro Paving Slabs at Mukarara Shopping Centre | To improve accessibility | No. of KMs done |  |  | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
467 | Proposed Road Works of Mitubiri Access roads - Kakuzi Ward | Proposed Road Works of Mitubiri Access roads - Kakuzi Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
468 | Proposed Road Works of Kakuzi Access roads - Kakuzi Ward | Proposed Road Works of Kakuzi Access roads - Kakuzi Ward | To improve accessibility | No. of KMs done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
469 | Proposed roadworks of Kahuho - Gathanga Access roads - Kambiti Ward | Proposed roadworks of Kahuho - Gathanga Access roads - Kambiti Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMBITI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
470 | Proposed roadworks of Turiru Co-operative Access road - Kambiti Ward | Proposed roadworks of Turiru Co-operative Access road - Kambiti Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMBITI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
471 | Proposed roadworks of Muchagara Bypass access road - Kambiti Ward | Proposed roadworks of Muchagara Bypass access road - Kambiti Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMBITI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
472 | Proposed roadworks of Kaseve - Ndifu Access roads - Kambiti Ward | Proposed roadworks of Kaseve - Ndifu Access roads - Kambiti Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | KAMBITI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
473 | Proposed road works of Kangari Ward - Kangari Ward | Proposed road works of Kangari Ward - Kangari Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | KANGARI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
474 | Proposed roadworks for kamacharia Access roads - Kamacharia Ward | Proposed roadworks for kamacharia Access roads - Kamacharia Ward | To improve accessibility | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
475 | Proposed road works of Wanyambo -Githunguri Gwa Chief Wamuhuti & Mwireri Access roads -Muthithi Ward | Proposed road works of Wanyambo -Githunguri Gwa Chief Wamuhuti & Mwireri Access roads -Muthithi Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | MUTHITHI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
476 | Proposed road works of Karuri -Njora - Kiara & Ngaburi Access roads -Muthithi Ward | Proposed road works of Karuri -Njora - Kiara & Ngaburi Access roads -Muthithi Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | MUTHITHI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
477 | Proposed Opening of Muthithi Ward Access roads - Muthithi Ward | Proposed Opening of Muthithi Ward Access roads - Muthithi Ward | To improve accessibility | No. of KMs done |  |  | KIGUMO | MUTHITHI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
478 | Proposed road Woks of Mithini Access roads - Makuyu Ward | Proposed road Woks of Mithini Access roads - Makuyu Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | MAKUYU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
479 | Proposed road Woks of Mutithi Access roads - Makuyu Ward | Proposed road Woks of Mutithi Access roads - Makuyu Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | MAKUYU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
480 | Proposed road Woks of Kirimiri Access roads - Makuyu Ward | Proposed road Woks of Kirimiri Access roads - Makuyu Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | MAKUYU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
481 | Proposed road Woks of Gakungu Access roads - Makuyu Ward | Proposed road Woks of Gakungu Access roads - Makuyu Ward | To improve accessibility | No. of KMs done |  |  | MARAGUA | MAKUYU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
482 | Proposed road Works of Wanjengi - Rural Access road - Wangu Ward | Proposed road Works of Wanjengi - Rural Access road - Wangu Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
483 | Proposed road Works of Gituto - Iganjo Access road - Wangu Ward | Proposed road Works of Gituto - Iganjo Access road - Wangu Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
484 | Proposed road Works of Koimbi -Rukui Access road - Wangu Ward | Proposed road Works of Koimbi -Rukui Access road - Wangu Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
485 | Proposed road Works of Gitui -Gatheru Jct Access road - Wangu Ward | Proposed road Works of Gitui -Gatheru Jct Access road - Wangu Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
486 | Proposed road Works of Gatheru - Rianda Access road - Wangu Ward | Proposed road Works of Gatheru - Rianda Access road - Wangu Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
487 | Proposed road Works of Kahuhia - Gikwa-ini Access road - Wangu Ward | Proposed road Works of Kahuhia - Gikwa-ini Access road - Wangu Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
488 | Proposed road Works of Kianderi -Gaturi Access road - Wangu Ward | Proposed road Works of Kianderi -Gaturi Access road - Wangu Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
489 | Proposed road Works of Kahuti -Iria Access road - Wangu Ward | Proposed road Works of Kahuti -Iria Access road - Wangu Ward | To improve accessibility | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
490 | Proposed Grading of Various Access roads - Muguru Ward | Proposed Grading of Various Access roads - Muguru Ward | To improve accessibility | No. of KMs done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
491 | Proposed road works of Ihiga Pry Access roads - Muguru Ward | Proposed road works of Ihiga Pry Access roads - Muguru Ward | To improve accessibility | No. of KMs done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
492 | Proposed Excavation ,Loading,& Supply of Quarry Waste / Laterite Gravel , Drainage Works Across Muguru Ward Access roads | Proposed Excavation ,Loading,& Supply of Quarry Waste / Laterite Gravel , Drainage Works Across Muguru Ward Access roads | To improve connectivity | No. of KMs done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
493 | Proposed drilling ,Installation & Commissioning of Nganga-ini Borehole to include water dispensing Kiosk- Mugumo-ini Ward. | Proposed drilling ,Installation & Commissioning of Nganga-ini Borehole to include water dispensing Kiosk- Mugumo-ini Ward. | To upgrade community service infrastructure | No. of KMs done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
494 | Proposed Supply of Solar Streetlighting & Floodlighting Across Mugumo-ini Ward | Proposed Supply of Solar Streetlighting & Floodlighting Across Mugumo-ini Ward | To ensure all shopping centers,markets and major town are lighted | No. of KMs done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
495 | Proposed Supply & Installation of domestic Water Pipes - Kahumbu Ward. | Proposed Supply & Installation of domestic Water Pipes - Kahumbu Ward. | To improve connectivity | No. of KMs done |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
496 | Proposed Supply of Solar Floodlighting to Various Sites Within - Kanyenya-ini Ward | Proposed Supply of Solar Floodlighting to Various Sites Within - Kanyenya-ini Ward |  | No. of KMs done |  |  | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
497 | Proposed Construction of Footbridges at Kiawanduma-Kiuru ,Nyumba Ithatu, Kiangoma Footbridges -3No - Gitugi Ward | Proposed Construction of Footbridges at Kiawanduma-Kiuru ,Nyumba Ithatu, Kiangoma Footbridges -3No - Gitugi Ward | To improve connectivity | No. of KMs done |  |  | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
498 | Proposed Construction of Kairungi & Hawamihari Footbridges - Kiru Ward. | Proposed Construction of Kairungi & Hawamihari Footbridges - Kiru Ward. | To improve connectivity | No. of KMs done |  |  | MATHIOYA | KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
499 | Proposed Construction of Footbridges of Kahuri Kwa Joeli, Kagumo-ini - Muthitha & Kibiku -Turuturu - Gaichanjiru Ward | Proposed Construction of Footbridges of Kahuri Kwa Joeli, Kagumo-ini - Muthitha & Kibiku -Turuturu - Gaichanjiru Ward | To improve connectivity | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
500 | Proposed Construction of footbridges at Meso, Kaihungu, Kiaguthu & Kiria - Mugoiri Ward | Proposed Construction of footbridges at Meso, Kaihungu, Kiaguthu & Kiria - Mugoiri Ward | To improve connectivity | No. of KMs done |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
501 | Proposed Construction of Footbridges at Kioru - Gichichi (2No.) ,Keni - Mutheru ,Kwa garachu - Kahiga , Kiganjo - Kairini Ruchu Ward | Proposed Construction of Footbridges at Kioru - Gichichi (2No.) ,Keni - Mutheru ,Kwa garachu - Kahiga , Kiganjo - Kairini Ruchu Ward | To improve connectivity | No. of KMs done |  |  | KANDARA | RUCHU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
502 | Proposed Construction of Maragua & Kionjo-ini Footbridges - Murarandia Ward | Proposed Construction of Maragua & Kionjo-ini Footbridges - Murarandia Ward | To improve connectivity | No. of KMs done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
503 | Proposed Construction of 1No. Footbridge & 3No. Boda Boda sheds - Mbiri Ward. | Proposed Construction of 1No. Footbridge & 3No. Boda Boda sheds - Mbiri Ward. | To improve connectivity | No. of KMs done |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
504 | Proposed Construction of Matongu ,Gakobo ,Geitwa & Wathenge Footbidges - Gaturi ward | Proposed Construction of Matongu ,Gakobo ,Geitwa & Wathenge Footbidges - Gaturi ward | To improve connectivity | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
505 | Proposed Construction of Nginyi & Githioro footbridges - Kakuzi Ward | Proposed Construction of Nginyi & Githioro footbridges - Kakuzi Ward | To improve connectivity | No. of KMs done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
506 | Proposed construction of Kwawagathere Footbridge - Kangari Ward | Proposed construction of Kwawagathere Footbridge - Kangari Ward | To improve connectivity | No. of KMs done |  |  | KIGUMO | KANGARI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
507 | Proposed Supply of Solar streeghtlighting & Floodlighting Materials | Proposed Supply of Solar streeghtlighting & Floodlighting Materials | To improve community infrastructure | no. of KMs maintained |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
508 | Proposed Construction of Simple Footbridges at Kiairathe ,Gikui, Kiangunyi,& Kiamara - Muguru Ward | Proposed Construction of Simple Footbridges at Kiairathe ,Gikui, Kiangunyi,& Kiamara - Muguru Ward | To improve connectivity | No. of KMS done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
509 | Proposed construction of Bodaboda Sheds at Gatunyu (2) ,Ithangarari,Kigio,& Gakurari - Mugumo-ini Ward | Proposed construction of Bodaboda Sheds at Gatunyu (2) ,Ithangarari,Kigio,& Gakurari - Mugumo-ini Ward | provide citizens with conducive business enviroment . | No. done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
510 | Proposed Construction of Bodaboda Sheds at Gakarati & Jam city - Kahumbu Ward | Proposed Construction of Bodaboda Sheds at Gakarati & Jam city - Kahumbu Ward | provide citizens with conducive business enviroment . | No. done |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
511 | Proposed Construction of Bodaboda Sheds at Kabati Flyover,Kenol, Kangangu , Trotters & Open retail Market Shed at Kabati Town - Kimorori Wempa | Proposed Construction of Bodaboda Sheds at Kabati Flyover,Kenol, Kangangu , Trotters & Open retail Market Shed at Kabati Town - Kimorori Wempa | provide citizens with conducive business enviroment . | No. done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
512 | Proposed Construction of Bodaboda Sheds at Ngurwe-ini,Kamuchii & Kariua - Ruchu Ward. | Proposed Construction of Bodaboda Sheds at Ngurwe-ini,Kamuchii & Kariua - Ruchu Ward. | provide citizens with conducive business enviroment . | No. done |  |  | KANDARA | RUCHU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
513 | Proposed Construction of Bodaboda sheds at Gatundu, Kahuro, Githagara & Kiria - Mugoiri Ward | Proposed Construction of Bodaboda sheds at Gatundu, Kahuro, Githagara & Kiria - Mugoiri Ward | provide citizens with conducive business enviroment . | No. done |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
514 | Proposed Construction of Kihoya & Wanjerere Bodaboda Sheds - Rwathia Ward | Proposed Construction of Kihoya & Wanjerere Bodaboda Sheds - Rwathia Ward | provide citizens with conducive business enviroment . | No. done |  |  | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
515 | Proposed construction of 4 No. bodaboda Sheds - Muthithi Ward | Proposed construction of 4 No. bodaboda Sheds - Muthithi Ward | provide citizens with conducive business enviroment . | No. done |  |  | KIGUMO | MUTHITHI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
516 | Proposed Construction of Classroom & Toilet block at Gikono Polytechnic - Kimorori Ward. | Proposed Construction of Classroom & Toilet block at Gikono Polytechnic - Kimorori Ward. | provide learners with conducive learning enviroment . | No. done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
517 | Proposed levelling of Mihango Polytechnic Playing Ground - Kambiti Ward | Proposed levelling of Mihango Polytechnic Playing Ground - Kambiti Ward | provide learners with conducive learning enviroment . | No.of KMs done. |  |  | MARAGUA | KAMBITI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
518 | Proposed Improvement of Gitugu & Githiga Shopping Centres - Kanyenya-ini Ward. | Proposed Improvement of Gitugu & Githiga Shopping Centres - Kanyenya-ini Ward. | provide citizens with conducive business enviroment . | No. done |  |  | KANGEMA | KANYENYAINI |  | TRADE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
519 | Proposed Construction of 1No. Class at Kamutungi Polytecnic - Ngararia Ward | Proposed Construction of 1No. Class at Kamutungi Polytecnic - Ngararia Ward | provide learners with conducive learning enviroment . | No. of classrooms done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
520 | Proposed improvement of Ngelelya Market - Ithanga Ward | Proposed improvement of Ngelelya Market - Ithanga Ward | provide citizens with conducive business enviroment . | No. done |  |  | GATANGA | ITHANGA |  | TRADE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
521 | Proposed Construction of Kirathani Market - Ithanga Ward | Proposed Construction of Kirathani Market - Ithanga Ward | provide citizens with conducive business enviroment . | No. done |  |  | GATANGA | ITHANGA |  | TRADE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
522 | Proposed improvement & Construction of Ablution block at Wanjerere Market - Rwathia Ward. | Proposed improvement & Construction of Ablution block at Wanjerere Market - Rwathia Ward. | provide citizens with conducive business enviroment . | No. done |  |  | KANGEMA | RWATHIA |  | TRADE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
523 | Proposed levelling of Mukumu, Murarandia , Theri & Kahatia Playgrounds - Murarandia Ward | Proposed levelling of Mukumu, Murarandia , Theri & Kahatia Playgrounds - Murarandia Ward | provide citizens with conducive business enviroment . | No. of KMS done |  |  | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
524 | Proposed improvement of Githambo & Kahatia Markets - Murarandia Ward | Proposed improvement of Githambo & Kahatia Markets - Murarandia Ward | provide citizens with conducive business enviroment . | No. done |  |  | KIHARU | MURARANDIA |  | TRADE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
525 | Proposed Construction of Kahithe & Mathariti Social Halls - Murarandia Ward | Proposed Construction of Kahithe & Mathariti Social Halls - Murarandia Ward | To upgrade community service infrastructure | No. done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
526 | Proposed Construction of Various Boda Boda Sheds & Waiting Bay - Township ward | Proposed Construction of Various Boda Boda Sheds & Waiting Bay - Township ward | provide citizens with conducive business enviroment . | No. done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
527 | Proposed construction of Kongo-ini social Hall - Township | Proposed construction of Kongo-ini social Hall - Township | provide citizens with conducive business enviroment . | No. done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
528 | Proposed Improvement of Kigetu-ini & Geitwa Markets - Gaturi ward | Proposed Improvement of Kigetu-ini & Geitwa Markets - Gaturi ward | provide citizens with conducive business enviroment . | No. done |  |  | KIHARU | GATURI |  | TRADE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
529 | Proposed Construction of Boda Boda Sheds at Kimathi,Gakonya,Kigetu-ini,Mahua-ini,Kaweru,Hakamama,Kiambugi,Ha-Kiduma,Gaitheri,Geitwa,& Mwirua - Gaturi Ward | Proposed Construction of Boda Boda Sheds at Kimathi,Gakonya,Kigetu-ini,Mahua-ini,Kaweru,Hakamama,Kiambugi,Ha-Kiduma,Gaitheri,Geitwa,& Mwirua - Gaturi Ward | provide citizens with conducive business enviroment . | No. done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
530 | Proposed Construction of Boda Boda Sheds (3No.) - Muguru Ward | Proposed Construction of Boda Boda Sheds (3No.) - Muguru Ward | provide citizens with conducive business enviroment . | No. done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
531 | Proposed Construction of Kiganjo Boda Boda Sheds - Kariara Ward. | Proposed Construction of Kiganjo Boda Boda Sheds - Kariara Ward. | provide citizens with conducive business enviroment . | No. done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
532 | Proposed construction of Boda Boda Sheds at Maragua Town, Nginda Jct & Kiangoma Jct & Construction of Ablution Blocks at Gikindu ECDE Centre & Irembu Shopping Centre - Nginda Ward. | Proposed construction of Boda Boda Sheds at Maragua Town, Nginda Jct & Kiangoma Jct & Construction of Ablution Blocks at Gikindu ECDE Centre & Irembu Shopping Centre - Nginda Ward. | provide citizens with conducive business enviroment . | No. done |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
533 | Proposed Renovation of Kangema Social Hall - Muguru Ward | Proposed Renovation of Kangema Social Hall - Muguru Ward | To upgrade community service infrastructure | No. done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
534 | Proposed roadworks of Kimatus - Rwaitira Access road - Mugumo-ini Ward | Proposed roadworks of Kimatus - Rwaitira Access road - Mugumo-ini Ward | To improve accessibility | No.of KMs done. |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
535 | Proposed of Kwa Jack -Mahethere - Mbogo-ini -Sabasaba River Acccess road - Kahumbu Ward | Proposed of Kwa Jack -Mahethere - Mbogo-ini -Sabasaba River Acccess road - Kahumbu Ward | To improve accessibility | No.of KMs done. |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
536 | Proposed road Works of Ichichi - Mahiga-ini Access Road - Kanyenya-ini Ward | Proposed road Works of Ichichi - Mahiga-ini Access Road - Kanyenya-ini Ward | To improve accessibility | No.of KMs done. |  |  | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
537 | Proposed road Works of Mahutia - Ndiara-ini Access road - Ngararia Ward | Proposed road Works of Mahutia - Ndiara-ini Access road - Ngararia Ward | To improve accessibility | No.of KMs done. |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
538 | Proposed road Works of Wakomo - Kiuu Pry - Kiawanduma Access road - Gitugi Ward. | Proposed road Works of Wakomo - Kiuu Pry - Kiawanduma Access road - Gitugi Ward. | To improve accessibility | No.of KMs done. |  |  | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
539 | Proposed road works of Gituri - Makuti - Muraguri - Marion - Ndegwa - Njira ya Kware Access road - Muruka Ward | Proposed road works of Gituri - Makuti - Muraguri - Marion - Ndegwa - Njira ya Kware Access road - Muruka Ward | To improve accessibility | No.of KMs done. |  |  | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
540 | Proposed road Works of Kangangu Access road - Kimorori Wempa Ward. | Proposed road Works of Kangangu Access road - Kimorori Wempa Ward. | To improve accessibility | No.of KMs done. |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
541 | Proposed road Works of Kamunyaka - Karembu-ini -Ikamba Access road - Ithiru Ward | Proposed road Works of Kamunyaka - Karembu-ini -Ikamba Access road - Ithiru Ward | To improve accessibility | No.of KMs done. |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
542 | Proposed road works of Maa-ini - Machegecha Access road - Kagundu-ini Ward. | Proposed road works of Maa-ini - Machegecha Access road - Kagundu-ini Ward. | To improve accessibility | No.of KMs done. |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
543 | Proposed road works of Ngurwe-ini Sec. Access road - Gaichanjiru Ward. | Proposed road works of Ngurwe-ini Sec. Access road - Gaichanjiru Ward. | To improve accessibility | No.of KMs done. |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
544 | Proposed road Works of Rugaita Access road - Mugoiri Ward. | Proposed road Works of Rugaita Access road - Mugoiri Ward. | To improve accessibility | No.of KMs done. |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
545 | Proposed road Works of Karuri - Mukangu Access road - Ruchu Ward. | Proposed road Works of Karuri - Mukangu Access road - Ruchu Ward. | To improve accessibility | No.of KMs done. |  |  | KANDARA | RUCHU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
546 | Proposed road Works of 3Post - Kiria-ini - Thithi River Access road - Gatanga Ward. | Proposed road Works of 3Post - Kiria-ini - Thithi River Access road - Gatanga Ward. | To improve accessibility | No.of KMs done. |  |  | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
547 | Proposed road works of Gakoe-ini -Marumi - Kaimiri -Seveni - Kirere Access road - Kigumo Ward | Proposed road works of Gakoe-ini -Marumi - Kaimiri -Seveni - Kirere Access road - Kigumo Ward | To improve accessibility | No.of KMs done. |  |  | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
548 | Proposed Roadworks of Karagia C Access road - Karia-ra Ward | Proposed Roadworks of Karagia C Access road - Karia-ra Ward | To improve accessibility | No.of KMs done. |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
549 | Proposed Roadworks of Rwathe- Ndune Access road - Kinyona Ward | Proposed Roadworks of Rwathe- Ndune Access road - Kinyona Ward | To improve accessibility | No.of KMs done. |  |  | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
550 | Proposed road works of Gichobo Access road - Rwathia Ward | Proposed road works of Gichobo Access road - Rwathia Ward | To improve accessibility | No.of KMs done. |  |  | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
551 | Proposed road works of Kionjo-ini Access road - Murarandia Ward | Proposed road works of Kionjo-ini Access road - Murarandia Ward | To improve accessibility | No.of KMs done. |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
552 | Proposed Supply & Installation of Cabro Paving Slabs at Muranga Town - Township Ward | Proposed Supply & Installation of Cabro Paving Slabs at Muranga Town - Township Ward | To improve accessibility | No.of KMs done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
553 | Proposed Road Works of Kirungu - Maisha Mathi - Kianjiru-ini - Itheru - Plateau Access road - Ichagaki Ward | Proposed Road Works of Kirungu - Maisha Mathi - Kianjiru-ini - Itheru - Plateau Access road - Ichagaki Ward | To improve accessibility | No.of KMs done. |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
554 | Proposed Roads Muchunga - Kayahwe River Falls - Naindu Pri School Access roads - | Proposed Roads Muchunga - Kayahwe River Falls - Naindu Pri School Access roads - | To improve accessibility | No.of KMs done. |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
555 | Proposed road works of Baraka Shop - Mweru Pry Access road - Gaturi Ward | Proposed road works of Baraka Shop - Mweru Pry Access road - Gaturi Ward | To improve accessibility | No.of KMs done. |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
556 | Proposed road Works of Kiru Boys - Ndiara Factory Access roads - Kiru Ward. | Proposed road Works of Kiru Boys - Ndiara Factory Access roads - Kiru Ward. | To improve accessibility | No.of KMs done. |  |  | MATHIOYA | KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
557 | Proposed road Works of Kaharati - Mumbu - Wairuri Access road - Kamahuha Ward. | Proposed road Works of Kaharati - Mumbu - Wairuri Access road - Kamahuha Ward. | To improve accessibility | No.of KMs done. |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
558 | Proposed road Works of Ikundu - Ititu - Iregi Access road - Nginda Ward. | Proposed road Works of Ikundu - Ititu - Iregi Access road - Nginda Ward. | To improve accessibility | No.of KMs done. |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
559 | Proposed road Works of Silanga Pry - Kwa Jimi access road - Kakuzi/Mitubiri Ward | Proposed road Works of Silanga Pry - Kwa Jimi access road - Kakuzi/Mitubiri Ward | To improve accessibility | No.of KMs done. |  |  | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
560 | Proposed road Works of Kambiti - Kitune - Kaseve Access road - Kambiti Ward. | Proposed road Works of Kambiti - Kitune - Kaseve Access road - Kambiti Ward. | To improve accessibility | No.of KMs done. |  |  | MARAGUA | KAMBITI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
561 | Proposed road Works of Mariira Farm - Kahuti - Irati - Karega Access road - Kangari Ward. | Proposed road Works of Mariira Farm - Kahuti - Irati - Karega Access road - Kangari Ward. | To improve accessibility | No.of KMs done. |  |  | KIGUMO | KANGARI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
562 | Proposed road Works of Gatuhi - Kiawathia - Nduro Access Road - Kamacharia Ward. | Proposed road Works of Gatuhi - Kiawathia - Nduro Access Road - Kamacharia Ward. | To improve accessibility | No.of KMs done. |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
563 | Proposed Supply & Installation of Cabro paving Slabs at Wamahiga Shopping Centre - Muthithi Ward | Proposed Supply & Installation of Cabro paving Slabs at Wamahiga Shopping Centre - Muthithi Ward | To improve accessibility | No.of KMs done. |  |  | KIGUMO | MUTHITHI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
564 | Proposed road works of Soweto Access road - Makuyu Ward | Proposed road works of Soweto Access road - Makuyu Ward | To improve accessibility | No.of KMs done. |  |  | MARAGUA | MAKUYU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
565 | Proposed road Works of Iyego Sec-Kahiti Pry -Njii-Ithatu - Nyakahura Access road - Muguru Ward. | Proposed road Works of Iyego Sec-Kahiti Pry -Njii-Ithatu - Nyakahura Access road - Muguru Ward. | To improve accessibility | No.of KMs done. |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
566 | Proposed Upgrading to Bitumen Standard of EPZ Access roads | Proposed Upgrading to Bitumen Standard of EPZ Access roads | To improve accessibility | No.of KMs done. |  |  | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
567 | Proposed Supply & Installation of Cabro paving Slabs at kandara Town - Kandara Subcounty | Proposed Supply & Installation of Cabro paving Slabs at kandara Town - Kandara Subcounty | To improve accessibility | No.of KMs done. |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
568 | Proposed Supply & Installation of Cabro paving Slabs at kaha-ini Town - Kandara Subcounty | Proposed Supply & Installation of Cabro paving Slabs at kaha-ini Town - Kandara Subcounty | To improve accessibility | No.of KMs done. |  |  | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
569 | Proposed Supply & Installation of Cabro paving Slabs at Githembe Shoppping Centre - Kigumo Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Githembe Shoppping Centre - Kigumo Subcounty | To improve accessibility | No.of KMs done. |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
570 | Proposed Supply & Installation of Cabro paving Slabs at Kahuro Shoppping Centre - Kiharu Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Kahuro Shoppping Centre - Kiharu Subcounty | To improve accessibility | No.of KMs done. |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
571 | Proposed Supply & Installation of Cabro paving Slabs at Kambirwa Shoppping Centre - Kiharu Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Kambirwa Shoppping Centre - Kiharu Subcounty | To improve accessibility | No.of KMs done. |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
572 | Proposed Supply & Installation of Cabro paving Slabs at Ndikwe Shoppping Centre - Kiharu Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Ndikwe Shoppping Centre - Kiharu Subcounty | To improve accessibility | No.of KMs done. |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
573 | Proposed Supply & Installation of Cabro paving Slabs at Maragwa Town - Maragwa Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Maragwa Town - Maragwa Subcounty | To improve accessibility | No.of KMs done. |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
574 | Proposed Supply & Installation of Cabro paving Slabs at Juction Shopping Centre - Gatanga Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Juction Shopping Centre - Gatanga Subcounty | To improve accessibility | No.of KMs done. |  |  | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
575 | Proposed Supply & Installation of Cabro paving Slabs at Kagaa Shopping Centre - Maragwa Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Kagaa Shopping Centre - Maragwa Subcounty | To improve accessibility | No.of KMs done. |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
576 | Proposed Supply & Installation of Cabro paving Slabs for Muranga Town - Kiharu Subcounty | Proposed Supply & Installation of Cabro paving Slabs for Muranga Town - Kiharu Subcounty | To improve accessibility | No.of KMs done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
577 | Proposed Supply & Installation of Cabro paving Slabs at Karugia Shopping Centre - Kandara Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Karugia Shopping Centre - Kandara Subcounty | To improve accessibility | No.of KMs done. |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
578 | Proposed roadworks of Kongo-ini - Mumbi estate Access road - Kiharu Subcounty | Proposed roadworks of Kongo-ini - Mumbi estate Access road - Kiharu Subcounty | To improve accessibility | No.of KMs done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
579 | Proposed roadworks of Gathinja - ACK Church & Gathinja pry Access road - Kiharu Subcounty | Proposed roadworks of Gathinja - ACK Church & Gathinja pry Access road - Kiharu Subcounty | To improve accessibility | No.of KMs done. |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
580 | Proposed roadworks of JCT Hakamama - Gathairu river Access road - Kiharu Subcounty | Proposed roadworks of JCT Hakamama - Gathairu river Access road - Kiharu Subcounty | To improve accessibility | No.of KMs done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
581 | Proposed Supply & Installation of Cabro paving Slabs at Githima Shopping Centre - Maragwa Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Githima Shopping Centre - Maragwa Subcounty | To improve accessibility | No.of KMs done. |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
582 | Proposed Supply & Installation of Cabro paving Slabs at Kihumbu-ini Shopping Centre - Gatanga Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Kihumbu-ini Shopping Centre - Gatanga Subcounty | To improve accessibility | No.of KMs done. |  |  | GATANGA | KIHUMBUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
583 | Proposed Supply & Installation of Cabro paving Slabs at Kambi Shopping Centre - Kigumo Subcounty | Proposed Supply & Installation of Cabro paving Slabs at Kambi Shopping Centre - Kigumo Subcounty | To improve accessibility | No.of KMs done. |  |  | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
584 | Proposed Supply, repair and installation of streetlights in Muranga town- | Proposed Supply, repair and installation of streetlights in Muranga town- | To improve accessibility | No.of KMs done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
585 | Proposed Supply, repair and installation of streetlights in Kenol town | Proposed Supply, repair and installation of streetlights in Kenol town | To improve accessibility | No.of KMs done. |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
586 | Proposed Supply, repair and installation of streetlights in Maragwa town | Proposed Supply, repair and installation of streetlights in Maragwa town | To improve accessibility | No.of KMs done. |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
587 | Framework for Repair and relocation of 20 meters and meters floodlights in Muranga county | Framework for Repair and relocation of 20 meters and meters floodlights in Muranga county | To improve accessibility | No.of KMs done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
588 | Framework for suppy and installation of concrete pole floodlights and streetlights in muranga county. 10,12,15 metres- | Framework for suppy and installation of concrete pole floodlights and streetlights in muranga county. 10,12,15 metres- | To improve accessibility | No.of KMs done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
589 | Proposed Supply and delivery of two fabricated 40ft containers ( BQ to include construction of platforms)- | Proposed Supply and delivery of two fabricated 40ft containers ( BQ to include construction of platforms)- | To improve accessibility | No. done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
590 | Framework for supply and delivery of streetlights and floodlights lamps and electrical maintenance materials in Muranga county. | Framework for supply and delivery of streetlights and floodlights lamps and electrical maintenance materials in Muranga county. | To improve accessibility | No.of KMs done. |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  |  | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
591 | Proposed Maintenance of roads in Towns across Muranga County | Proposed Maintenance of roads in Towns across Muranga County | To improve accessibility | No.of KMs done. |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
592 | Proposed Maintenance of roads in Shopping Centres across Muranga County | Proposed Maintenance of roads in Shopping Centres across Muranga County | To improve accessibility | No.of KMs done. |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
593 | Proposed refurbishment of Muranga County Headquarters | Proposed refurbishment of Muranga County Headquarters | To upgrade and construct housing which is safe and secure |  |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
594 | Upgrading to Cabro-Paving of frontages withing Maragwa Town | Upgrading to Cabro-Paving of frontages withing Maragwa Town | To improve accessibility | No.of KMs done. |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Murang'a Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
595 | Rehabilitation of Murang'a Social Hall | Rehabilitation of Murang'a Social Hall | To upgrade and construct housing which is safe and secure | No. done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Murang'a Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
596 | Proposed beautification of Murang'a equity Roundabout | Proposed beautification of Murang'a equity Roundabout | To upgrade community service infrastructure | No. done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Murang'a Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
597 | Partitioning of Murang'a Municipality office block | Partitioning of Murang'a Municipality office block | To upgrade and construct housing which is safe and secure | No. done |  |  | KIHARU | TOWNSHIP |  | MURANG'A MUNICIPALITY | Murang'a Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
598 | Proposed Installation and supply of Cabro Paving blocks of Kagaa Shopping Centre | Proposed Installation and supply of Cabro Paving blocks of Kagaa Shopping Centre | To improve accessibility | No.of KMs done. |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Kenol Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
599 | Proposed construction of Kenol Municipality offices-Maragua Subcounty | Proposed construction of Kenol Municipality offices-Maragua Subcounty | To upgrade and construct housing which is safe and secure | No. done |  |  | MARAGUA | KIMORORI WEMPA |  | KENOL MUNICIPALITY | Kenol Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
600 | Cabro Paving of KWFT-Posta Area | Cabro Paving of KWFT-Posta Area | To improve accessibility | No.of KMs done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Kenol Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
601 | Upgrade to Cabro Standard of Kathangi estate-Githanji primary school | Upgrade to Cabro Standard of Kathangi estate-Githanji primary school | To improve accessibility | No.of KMs done. |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Kenol Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
602 | Upgrade to Cabro standard of Jerusalem road(Chief's camp-Proto)Gas | Upgrade to Cabro standard of Jerusalem road(Chief's camp-Proto)Gas | To improve accessibility | No.of KMs done. |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Kenol Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | NO
603 | Upgrading to Bitumen Standards of Murang'a PCEA-Kayole Market JCT | Upgrading to Bitumen Standards of Murang'a PCEA-Kayole Market JCT | To improve accessibility | No.of KMs done. |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Murang'a Municipality | [8 empty] | DEVELOPMENT PATNER | KUSP | [7 empty] | PLANNED | [6 empty] | NO |  |  | NO | YES | NO | YES | YES
604 | Cabro paving of Kangari town and drainage system rehabilitation | Cabro paving of Kangari town and drainage system rehabilitation | To improve connectivity and accessibility | No.of KMs done. |  |  | KIGUMO | KANGARI |  | INFRASTRUCTURE | Kangari Municipality | [8 empty] | MCG | [8 empty] | PLANNED | [6 empty] | YES |  |  | NO | YES | NO | YES | YES
605 | Construction of classrooms for Kahumbu polytechnic | Construction of classrooms | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-10 |  |  | 2025-04-10 | 5448175 | 5448175 |  | MCG |  |  |  | 5448175 | 100% | 5448175 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
606 | construction of St. John Primary School Kiruri ECDE centre- Kanyenyaini Ward | construction of classrooms | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-23 |  |  | 2025-06-23 | 1910385 | 1910385 |  | MCG |  |  |  | 1910385 | 100% | 1910385 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
607 | construction of toilet, kitchen, fencing and landscaping of Kieni ECDE centre- Kanyenyaini Ward | improvement of ECDE facilities | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-04 |  |  | 2025-06-04 | 4078335 | 4078335 |  | MCG |  |  |  | 4078335 | 100% | 4078335 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
608 | construction of toilet, kitchen, fencing and landscaping of Kawariuwa ECDE centre- Kanyenyaini Ward | improvement of ECDE facilities | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-12 |  |  | 2025-06-12 | 4226715 | 4226715 |  | MCG |  |  |  | 4226715 | 100% | 4226715 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
609 | construction of Mahutia and Kaburugi ECDE classroom- Ngararia Ward | Construction of classrooms | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-25 |  |  | 2025-06-25 | 3430585 | 3430585 |  | MCG |  |  |  | 3430585 | 100% | 3430585 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
610 | Construction of 2no. Classrooms and toilet block at Kamutungi polytechnic-Ng'araria ward. | Construction of 2no. Classrooms | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-25 |  |  | 2025-06-25 | 3697660 | 3697660 |  | MCG |  |  |  | 3697660 | 100% | 3697660 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
611 | construction of classroom of Waitua ECDE centre- Ngararia Ward | construction of classroom | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-26 |  |  | 2025-06-26 | 3430585 | 3430585 |  | MCG |  |  |  | 3430585 | 100% | 3430585 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
612 | renovation of Kirimiga and Njumbi ECDE classrooms- Gitugi Ward | renovation of ECDE classrooms | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-07-21 |  |  | 2025-07-21 | 2700100 | 2700100 |  | MCG |  |  |  | 2700100 | 100% | 2700100 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
613 | renovation of Gataragwa and Karunge ECDE centres- Gitugi Ward | renovation of ECDE centres | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-04 |  |  | 2025-04-04 | 3173980 | 3173980 |  | MCG |  |  |  | 3173980 | 100% | 3173980 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
614 | renovation of Ngutu, Chui ECDE classrooms and construction of toilet block at Gakambura ECDE centre- Gitugi Ward | renovation of ECDE ECDE centre | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-04 |  |  | 2025-06-04 | 3722665 | 3722665 |  | MCG |  |  |  | 3722665 | 100% | 3722665 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
615 | renovation of Kambara ECDE centre- Gitugi Ward | renovation of ECDE centre | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-04 |  |  | 2025-04-04 | 1743970 | 1743970 |  | MCG |  |  |  | 1743970 | 100% | 1743970 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
616 | construction of Kiuu ECDE classrooms- Gitugi Ward | construction of classrooms | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-13 |  |  | 2025-05-13 | 3050630 | 3050630 |  | MCG |  |  |  | 3050630 | 100% | 3050630 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
617 | RENOVATION OF MURUKA PRIMARY SCHOOL ECDE CLASSROOMS-MURUKA WARD | renovation of ECDE centre | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-19 |  |  | 2025-03-19 | 2597250 | 2597250 |  | MCG |  |  |  | 2597250 | 100% | 2597250 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
618 | renovation of Kariko ECDE classroom and construction of a toilet block- Muruka Ward | renovation of ECDE classroom | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-13 |  |  | 2025-05-13 | 1526770 | 1526770 |  | MCG |  |  |  | 1526770 | 100% | 1526770 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
619 | renovation of Kanyiri-ini ECDE centre and construction of toilet block- Muruka Ward | renovation of ECDE centre | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-13 |  |  | 2025-05-13 | 2935190 | 2935190 |  | MCG |  |  |  | 2935190 | 100% | 2935190 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
620 | renovation of Mathuithi ECDE centre, office and store and construction of toilet block- Muruka Ward | renovation of Mathuithi ECDE centre, office and store and construction of toilet block- Muruka Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-23 |  |  | 2025-05-23 | 2843475 | 2843475 |  | MCG |  |  |  | 2843475 | 100% | 2843475 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
621 | construction of Athaara ECDE classrooms- Kimorori Wempa Ward | construction of Athaara ECDE classrooms- Kimorori Wempa Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-10 |  |  | 2025-03-10 | 1705390 | 1705390 |  | MCG |  |  |  | 1705390 | 100% | 1705390 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
622 | renovation of 2 no. classrom, construction of 1 no. classroom and 4 no. door toilet block at Kimorori ECDE Centre | renovation of 2 no. classrom, construction of 1 no. classroom and 4 no. door toilet block at Kimorori ECDE Centre | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-10 |  |  | 2025-04-10 | 4373305 | 4373305 |  | MCG |  |  |  | 4373305 | 100% | 4373305 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
623 | construction of classrooms at Githanji and Karugu ECDE centres- Kimorori Wempa Ward | construction of classrooms at Githanji and Karugu ECDE centres- Kimorori Wempa Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-10 |  |  | 2025-03-10 | 4020872 | 4020872 |  | MCG |  |  |  | 4020872 | 100% | 4020872 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
624 | renovation of Mianyani ECDE centre- Ithanga Ward | renovation of Mianyani ECDE centre- Ithanga Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | ITHANGA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-27 |  |  | 2025-03-27 | 1709740 | 1709740 |  | MCG |  |  |  | 1709740 | 100% | 1709740 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
625 | construction of Mugumo ECDE centre- Ithanga Ward | construction of Mugumo ECDE centre- Ithanga Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | ITHANGA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-23 |  |  | 2025-04-23 | 1725325 | 1725325 |  | MCG |  |  |  | 1725325 | 100% | 1725325 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
626 | construction of Kagoro ECDE centre- Ithiru Ward | construction of Kagoro ECDE centre- Ithiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-28 |  |  | 2025-04-28 | 2263901 | 2263901 |  | MCG |  |  |  | 2263901 | 100% | 2263901 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
627 | renovation of Kandara ECDE centre- Ithiru Ward | renovation of Kandara ECDE centre- Ithiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-28 |  |  | 2025-04-28 | 1514500 | 1514500 |  | MCG |  |  |  | 1514500 | 100% | 1514500 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
628 | renovation of Kagongo Primary ECDE centre- Ithiru Ward | renovation of Kagongo Primary ECDE centre- Ithiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-13 |  |  | 2025-05-13 | 1389510 | 1389510 |  | MCG |  |  |  | 1389510 | 100% | 1389510 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
629 | renovation of Kirigithu Primary ECDE centre- Ithiru Ward | renovation of Kirigithu Primary ECDE centre- Ithiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-04 |  |  | 2025-04-04 | 1442235 | 1442235 |  | MCG |  |  |  | 1442235 | 100% | 1442235 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
630 | construction and renovation of classrooms at Gathige Primary ECDE centre- Kagunduini Ward | construction and renovation of classrooms at Gathige Primary ECDE centre- Kagunduini Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-06 |  |  | 2025-03-06 | 1629255 | 1629255 |  | MCG |  |  |  | 1629255 | 100% | 1629255 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
631 | renovation of classrooms at Mukerenju ECDE centre- Kagunduini Ward | renovation of classrooms at Mukerenju ECDE centre- Kagunduini Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-06 |  |  | 2025-03-06 | 2990350 | 2990350 |  | MCG |  |  |  | 2990350 | 100% | 2990350 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
632 | renovation of classrooms at Githigi ECDE centre- Gaichanjiru Ward | renovation of classrooms at Githigi ECDE centre- Gaichanjiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-24 |  |  | 2025-04-24 | 2075620 | 2075620 |  | MCG |  |  |  | 2075620 | 100% | 2075620 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
633 | construction and renovation of classrooms at Gakoigo ECDE centre- Gaichanjiru Ward | construction and renovation of classrooms at Gakoigo ECDE centre- Gaichanjiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-19 |  |  | 2025-03-19 | 2296215 | 2296215 |  | MCG |  |  |  | 2296215 | 100% | 2296215 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
634 | renovation of Karugi, Kariua and Wangai ECDE centres- Gaichanjiru Ward | renovation of Karugi, Kariua and Wangai ECDE centres- Gaichanjiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-24 |  |  | 2025-04-24 | 2568710 | 2568710 |  | MCG |  |  |  | 2568710 | 100% | 2568710 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
635 | construction and renovation of Muthiria and Kagumo ECDE centre- Mugoiri Ward | construction and renovation of Muthiria and Kagumo ECDE centre- Mugoiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-20 |  |  | 2025-05-20 | 2946230 | 2946230 |  | MCG |  |  |  | 2946230 | 100% | 2946230 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
636 | renovation of Ndutumi and Gitaro ECDE centres- Mugoiri Ward | renovation of Ndutumi and Gitaro ECDE centres- Mugoiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-02-12 |  |  | 2025-02-12 | 2066790 | 2066790 |  | MCG |  |  |  | 2066790 | 100% | 2066790 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
637 | construction of Githagara Primary ECDE centre- Mugoiri Ward | construction of Githagara Primary ECDE centre- Mugoiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-10 |  |  | 2025-04-10 | 1565090 | 1565090 |  | MCG |  |  |  | 1565090 | 100% | 1565090 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
638 | renovation of Ruona ECDE centre- Ruchu Ward | renovation of Ruona ECDE centre- Ruchu Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | RUCHU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-19 |  |  | 2025-03-19 | 3050410 | 3050410 |  | MCG |  |  |  | 3050410 | 100% | 3050410 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
639 | renovation of Chomo Highway ECDE centre and construction of kitchen, food eating shed, ablution block and chain link- Gatanga Ward | renovation of Chomo Highway ECDE centre and construction of kitchen, food eating shed, ablution block and chain link- Gatanga Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | GATANGA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-04 |  |  | 2025-06-04 | 4432677 | 4432677 |  | MCG |  |  |  | 4432677 | 100% | 4432677 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
640 | renovation of Gakare ECDE centre and fencing and gate- Kigumo Ward | renovation of Gakare ECDE centre and fencing and gate- Kigumo Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIGUMO | KIGUMO |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-01-28 |  |  | 2025-01-28 | 1328700 | 1328700 |  | MCG |  |  |  | 1328700 | 100% | 1328700 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
641 | renovation and construction of ablution block at Kigumo and Kirere ECDE centre- Kigumo Ward | renovation and construction of ablution block at Kigumo and Kirere ECDE centre- Kigumo Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIGUMO | KIGUMO |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-24 |  |  | 2025-04-24 | 2808185 | 2808185 |  | MCG |  |  |  | 2808185 | 100% | 2808185 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
642 | renovation of Githima Pry and Turuturu ECDE classrooms and construction of ablution block- Kigumo Ward | renovation of Githima Pry and Turuturu ECDE classrooms and construction of ablution block- Kigumo Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIGUMO | KIGUMO |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-01-28 |  |  | 2025-01-28 | 1328700 | 1328700 |  | MCG |  |  |  | 1328700 | 100% | 1328700 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
643 | Renovation of Gatunguru ECDE Centre - Kariara Ward | Renovation of Gatunguru ECDE Centre - Kariara Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KARIARA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-23 |  |  | 2025-04-23 | 1720360 | 1720360 |  | MCG |  |  |  | 1720360 | 100% | 1720360 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
644 | Construction of Wandahi Pry ECDE Centre - Kariara Ward | Construction of Wandahi Pry ECDE Centre - Kariara Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KARIARA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-02-12 |  |  | 2025-02-12 | 1386100 | 1386100 |  | MCG |  |  |  | 1386100 | 100% | 1386100 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
645 | construction of Ndugamano and Muiria ECDE classrooms- Kinyona Ward | construction of Ndugamano and Muiria ECDE classrooms- Kinyona Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-24 |  |  | 2025-04-24 | 2295730 | 2295730 |  | MCG |  |  |  | 2295730 | 100% | 2295730 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
646 | construction of Kiamaingi ECDE classroom- Kinyona Ward | construction of Kiamaingi ECDE classroom- Kinyona Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-03 |  |  | 2025-06-03 | 1443285 | 1443285 |  | MCG |  |  |  | 1443285 | 100% | 1443285 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
647 | renovation of ECDE classrooms at Kanguro ECDE centre- Rwathia Ward | renovation of ECDE classrooms at Kanguro ECDE centre- Rwathia Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANGEMA | RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-10 |  |  | 2025-03-10 | 1716720 | 1716720 |  | MCG |  |  |  | 1716720 | 100% | 1716720 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
648 | construction of classroom and toilet block at Mukumu and Kionjo-ini ECDE centres- Murarandia Ward | construction of classroom and toilet block at Mukumu and Kionjo-ini ECDE centres- Murarandia Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-04 |  |  | 2025-06-04 | 3469985 | 3469985 |  | MCG |  |  |  | 3469985 | 100% | 3469985 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
649 | renovation of Gatuya ECDE classrooms and construction of toilet block at Thengeini and Kahatia ECDE centres- Murarandia Ward | renovation of Gatuya ECDE classrooms and construction of toilet block at Thengeini and Kahatia ECDE centres- Murarandia Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-02-26 |  |  | 2025-02-26 | 2138070 | 2138070 |  | MCG |  |  |  | 2138070 | 100% | 2138070 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
650 | renovation and cabro works at Mukuyu ECDE centre- Township Ward | renovation and cabro works at Mukuyu ECDE centre- Township Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-01-17 |  |  | 2025-01-17 | 2661960 | 2661960 |  | MCG |  |  |  | 2661960 | 100% | 2661960 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
651 | renovation of Mutundu B ECDE centre- Ichagaki Ward | renovation of Mutundu B ECDE centre- Ichagaki Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-19 |  |  | 2025-03-19 | 1273830 | 1273830 |  | MCG |  |  |  | 1273830 | 100% | 1273830 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
652 | Construction of 2no. Classrooms at Maragua Township ECDE | Construction of 2no. Classrooms at Maragua Township ECDE | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-24 |  |  | 2025-06-24 | 2920020 | 2920020 |  | MCG |  |  |  | 2920020 | 100% | 2920020 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
653 | construction of a classroom at Gathunguri ECDE centre and ablution block- Ichagaki Ward | construction of a classroom at Gathunguri ECDE centre and ablution block- Ichagaki Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-27 |  |  | 2025-03-27 | 1961660 | 1961660 |  | MCG |  |  |  | 1961660 | 100% | 1961660 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
654 | construction of classrooms at Gaitega ECDE centre- Mbiri Ward | construction of classrooms at Gaitega ECDE centre- Mbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-04 |  |  | 2025-04-04 | 2967044 | 2967044 |  | MCG |  |  |  | 2967044 | 100% | 2967044 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
655 | conversion of existing hall to classrooms at Gikandu Primary ECDE centre- Mbiri Ward | conversion of existing hall to classrooms at Gikandu Primary ECDE centre- Mbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-10 |  |  | 2025-04-10 | 2548270 | 2548270 |  | MCG |  |  |  | 2548270 | 100% | 2548270 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
656 | renovation of Mirira Pry ECDE classrooms- Mbiri Ward | renovation of Mirira Pry ECDE classrooms- Mbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-23 |  |  | 2025-05-23 | 1149420 | 1149420 |  | MCG |  |  |  | 1149420 | 100% | 1149420 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
657 | renovation of 2 no classrooms and offices at Ndikwe Pry ECDE centre- Mbiri Ward | renovation of 2 no classrooms and offices at Ndikwe Pry ECDE centre- Mbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-02-11 |  |  | 2025-02-11 | 945800 | 945800 |  | MCG |  |  |  | 945800 | 100% | 945800 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
658 | renovation of Kayuyu Pry ECDE centre- Mbiri Ward | renovation of Kayuyu Pry ECDE centre- Mbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-01-23 |  |  | 2025-01-23 | 2977016 | 2977016 |  | MCG |  |  |  | 2977016 | 100% | 2977016 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
659 | renovation & Construction of Kambirwa Pry ECDE centre- Mbiri Ward | renovation & Construction of Kambirwa Pry ECDE centre- Mbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-18 |  |  | 2025-06-18 | 3139400 | 3139400 |  | MCG |  |  |  | 3139400 | 100% | 3139400 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
660 | renovation of classrooms and construction of toilet block at Thangathi and Gikuu ECDE centre- Mbiri Ward | renovation of classrooms and construction of toilet block at Thangathi and Gikuu ECDE centre- Mbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-17 |  |  | 2025-03-17 | 4787575 | 4787575 |  | MCG |  |  |  | 4787575 | 100% | 4787575 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
661 | renovation of Namumbu ECDE centre- Mbiri Ward | renovation of Namumbu ECDE centre- Mbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-23 |  |  | 2025-05-23 | 1971105 | 1971105 |  | MCG |  |  |  | 1971105 | 100% | 1971105 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
662 | Construction of Matongu ECDE centre- Gaturi Ward | Construction of Matongu ECDE centre- Gaturi Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-28 |  |  | 2025-03-28 | 1790665 | 1790665 |  | MCG |  |  |  | 1790665 | 100% | 1790665 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
663 | renovation of Upper Nyakihai ECDE centre- Gaturi Ward | renovation of Upper Nyakihai ECDE centre- Gaturi Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-10 |  |  | 2025-04-10 | 2902708 | 2902708 |  | MCG |  |  |  | 2902708 | 100% | 2902708 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
664 | renovation of Githanga and Construction of Kabwe ECDE centres- Gaturi Ward | renovation of Githanga and Construction of Kabwe ECDE centres- Gaturi Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-13 |  |  | 2025-05-13 | 5088680 | 5088680 |  | MCG |  |  |  | 5088680 | 100% | 5088680 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
665 | renovation & Construction of Muthangari, Kihari ,Gititu ECDE centre- Kiru Ward | renovation & Construction of Muthangari, Kihari ,Gititu ECDE centre- Kiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-10 |  |  | 2025-04-10 | 4059195 | 4059195 |  | MCG |  |  |  | 4059195 | 100% | 4059195 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
666 | renovation & Construction of Umbui ,Gachiriro & Nguru-ini ECDE centres- Kiru Ward | renovation & Construction of Umbui ,Gachiriro & Nguru-ini ECDE centres- Kiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-01-21 |  |  | 2025-01-21 | 4573155 | 4573155 |  | MCG |  |  |  | 4573155 | 100% | 4573155 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
667 | renovation & Construction of Mananga ,Kiriko and Muiri-ini ECDE centres- Kiru Ward | renovation & Construction of Mananga ,Kiriko and Muiri-ini ECDE centres- Kiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-15 |  |  | 2025-04-15 | 6108280 | 6108280 |  | MCG |  |  |  | 6108280 | 100% | 6108280 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
668 | Construction & Renovation of Classrooms , Ablution Block,& Fencing at Kiawanjumbi & Mirichu ECDE centre- Kiru Ward | Construction & Renovation of Classrooms , Ablution Block,& Fencing at Kiawanjumbi & Mirichu ECDE centre- Kiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-02-05 |  |  | 2025-02-05 | 5723470 | 5723470 |  | MCG |  |  |  | 5723470 | 100% | 5723470 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
669 | construction of Kaharo ECDE centres- Kiru Ward | construction of Kaharo ECDE centres- Kiru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-06 |  |  | 2025-03-06 | 2975610 | 2975610 |  | MCG |  |  |  | 2975610 | 100% | 2975610 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
670 | construction of Wathiani and Igikiro Pry ECDE centres- Kamahuha Ward | construction of Wathiani and Igikiro Pry ECDE centres- Kamahuha Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | KAMAHUHA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-23 |  |  | 2025-04-23 | 3050670 | 3050670 |  | MCG |  |  |  | 3050670 | 100% | 3050670 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
671 | construction of Iganjo and Kaharati Pry ECDE centres- Kamahuha Ward | construction of Iganjo and Kaharati Pry ECDE centres- Kamahuha Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | KAMAHUHA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-04 |  |  | 2025-04-04 | 4083680 | 4083680 |  | MCG |  |  |  | 4083680 | 100% | 4083680 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
672 | renovation of Ikundu and renovation of Kirundu and construction of ablution block gate and fencing of ECDE centres- Nginda Ward | renovation of Ikundu and renovation of Kirundu and construction of ablution block gate and fencing of ECDE centres- Nginda Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | NGINDA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-13 |  |  | 2025-05-13 | 2149275 | 2149275 |  | MCG |  |  |  | 2149275 | 100% | 2149275 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
673 | construction of Nyagachugu ECDE centre- Nginda Ward | construction of Nyagachugu ECDE centre- Nginda Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | NGINDA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-14 |  |  | 2025-03-14 | 1481430 | 1481430 |  | MCG |  |  |  | 1481430 | 100% | 1481430 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
674 | construction of Kibaaka ECDE centre- Kihumbu-ini Ward | construction of Kibaaka ECDE centre- Kihumbu-ini Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-12 |  |  | 2025-05-12 | 4669928 | 4669928 |  | MCG |  |  |  | 4669928 | 100% | 4669928 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
675 | renovation of Mukarara and Thuita Pry ECDE centres- Kihumbu-ini Ward | renovation of Mukarara and Thuita Pry ECDE centres- Kihumbu-ini Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-15 |  |  | 2025-04-15 | 2304300 | 2304300 |  | MCG |  |  |  | 2304300 | 100% | 2304300 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
676 | renovation and construction of classrooms at Kihunguro Pry ECDE centre- Kakuzi/Mitumbiri Ward | renovation and construction of classrooms at Kihunguro Pry ECDE centre- Kakuzi/Mitumbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KAKUZI/MITUMBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-18 |  |  | 2025-03-18 | 2463610 | 2463610 |  | MCG |  |  |  | 2463610 | 100% | 2463610 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
677 | construction of classroom, ablution block and fencing of Mt. Olive ECDE centre- Kakuzi/Mitumbiri Ward | construction of classroom, ablution block and fencing of Mt. Olive ECDE centre- Kakuzi/Mitumbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KAKUZI/MITUMBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-18 |  |  | 2025-06-18 | 2899290 | 2899290 |  | MCG |  |  |  | 2899290 | 100% | 2899290 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
678 | renovation of Nanga ECDE centre and construction of ablution block- Kakuzi/Mitumbiri Ward | renovation of Nanga ECDE centre and construction of ablution block- Kakuzi/Mitumbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KAKUZI/MITUMBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-27 |  |  | 2025-03-27 | 2825255 | 2825255 |  | MCG |  |  |  | 2825255 | 100% | 2825255 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
679 | Renovation of Muti ECDE centres- Kakuzi/Mitumbiri Ward | Renovation of Muti ECDE centres- Kakuzi/Mitumbiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KAKUZI/MITUMBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-21 |  |  | 2025-03-21 | 1798360 | 1798360 |  | MCG |  |  |  | 1798360 | 100% | 1798360 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
680 | construction of Kambiti Pry ECDE Classroom - Kambiti Ward. | construction of Kambiti Pry ECDE Classroom - Kambiti Ward. | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | KAMBITI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-02-25 |  |  | 2025-02-25 | 1572902 | 1572902 |  | MCG |  |  |  | 1572902 | 100% | 1572902 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
681 | Construction of Matharite Primary ECDE Classroom - Murarandia ward | Construction of Matharite Primary ECDE Classroom - Murarandia ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-06 |  |  | 2025-03-06 | 1708370 | 1708370 |  | MCG |  |  |  | 1708370 | 100% | 1708370 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
682 | Renovation & Fencing of ECDE Classrooms at Gakeu & Kagurumo - Muthithi Ward | Renovation & Fencing of ECDE Classrooms at Gakeu & Kagurumo - Muthithi Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIGUMO | MUTHITHI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-02 |  |  | 2025-05-02 | 3982835 | 3982835 |  | MCG |  |  |  | 3982835 | 100% | 3982835 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
683 | Renovation & Construction of Toilet Block & Fencing of Ngombe ECDE Centre - Muthithi Ward | Renovation & Construction of Toilet Block & Fencing of Ngombe ECDE Centre - Muthithi Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIGUMO | MUTHITHI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-02-05 |  |  | 2025-02-05 | 2704115 | 2704115 |  | MCG |  |  |  | 2704115 | 100% | 2704115 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
684 | Construction of College Pry ECDE Centre - Makuyu Ward | Construction of College Pry ECDE Centre - Makuyu Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | MARAGUA | MAKUYU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-05 |  |  | 2025-06-05 | 1878980 | 1878980 |  | MCG |  |  |  | 1878980 | 100% | 1878980 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
685 | construction & Renovation of Wanjengi & Kahuhia ECDE Centre - Wangu Ward. | construction & Renovation of Wanjengi & Kahuhia ECDE Centre - Wangu Ward. | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | WANGU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-26 |  |  | 2025-05-26 | 3410700 | 3410700 |  | MCG |  |  |  | 3410700 | 100% | 3410700 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
686 | Renovation of Nyakahura Pry & Gatundu-ini Pry ECDE Centre - Muguru Ward. | Renovation of Nyakahura Pry & Gatundu-ini Pry ECDE Centre - Muguru Ward. | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-23 |  |  | 2025-05-23 | 1329475 | 1329475 |  | MCG |  |  |  | 1329475 | 100% | 1329475 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
687 | renovation of Iyego Pry & Karuri Pry ECDE Centres - Muguru Ward. | renovation of Iyego Pry & Karuri Pry ECDE Centres - Muguru Ward. | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-03-06 |  |  | 2025-03-06 | 1214842.5 | 1214842.5 |  | MCG |  |  |  | 1214842.5 | 100% | 1214842.5 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
688 | Renovation of Ihiga Pry & Construction of Classroom at Thirikwa Pry ECDE Centres - Muguru Ward. | Renovation of Ihiga Pry & Construction of Classroom at Thirikwa Pry ECDE Centres - Muguru Ward. | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-04 |  |  | 2025-04-04 | 2372715 | 2372715 |  | MCG |  |  |  | 2372715 | 100% | 2372715 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
689 | Construction of Ablution Block at Kiawairegi & Ngoro ECDE Centres & Renovation of Watuha ECDE Centre - Muguru Ward. | Construction of Ablution Block at Kiawairegi & Ngoro ECDE Centres & Renovation of Watuha ECDE Centre - Muguru Ward. | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-15 |  |  | 2025-04-15 | 1247440 | 1247440 |  | MCG |  |  |  | 1247440 | 100% | 1247440 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
690 | Renovation of Kiunyu Nyaga ECDE Centre - Kihumbu-ini Ward. | Renovation of Kiunyu Nyaga ECDE Centre - Kihumbu-ini Ward. | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-04-24 |  |  | 2025-04-24 | 3735420 | 3735420 |  | MCG |  |  |  | 3735420 | 100% | 3735420 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
691 | Construction of Ablution Block at Wangai ECDE Centre, Kagumo-ini and Ngurwe-ini Market-Gaichanjiri Ward | Construction of Ablution Block at Wangai ECDE Centre, Kagumo-ini and Ngurwe-ini Market-Gaichanjiri Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-03 |  |  | 2025-06-03 | 2544970 | 2544970 |  | MCG |  |  |  | 2544970 | 100% | 2544970 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
692 | renovation and construction of classrooms at Kihumbu-ini Pry ECDE centres- Kihumbu-ini Ward | renovation and construction of classrooms at Kihumbu-ini Pry ECDE centres- Kihumbu-ini Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-18 |  |  | 2025-06-18 | 2988530 | 2988530 |  | MCG |  |  |  | 2988530 | 100% | 2988530 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
693 | renovation at Muguru Pry ECDE 4No. Classroom-Muguru Ward | renovation at Muguru Pry ECDE 4No. Classroom-Muguru Ward | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-05-26 |  |  | 2025-05-26 | 1957570 | 1957570 |  | MCG |  |  |  | 1957570 | 100% | 1957570 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
694 | renovation & construction of classrooms at Kamui-ru primary ECDE centre | renovation & construction of classrooms at Kamui-ru primary ECDE centre | provide learners with conducive learning enviroment . | no. of classrooms done |  | Development | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-06-12 |  |  | 2025-06-12 | 3281585 | 3281585 |  | MCG |  |  |  | 3281585 | 100% | 3281585 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
695 | construction of Ngoe-ini Dispensary-Kanyenyaini Ward | construction of Ngoe-ini Dispensary-Kanyenyaini Ward | To improve healthcare | no. of Health centers done |  | Development | KANGEMA | KANYENYAINI |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2025-04-10 |  |  | 2025-04-10 | 4801071 | 4801071 |  | MCG |  |  |  | 4801071 | 100% | 4801071 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
696 | Construction of Maternity at Kiunyu Dispensary -Kihumbu-ini Ward | Construction of Maternity at Kiunyu Dispensary -Kihumbu-ini Ward | To improve healthcare | no. of Health centers done |  | Development | GATANGA | KIHUMBUINI |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2025-06-03 |  |  | 2025-06-03 | 7700560.8 | 7700560.8 |  | MCG |  |  |  | 7700560.8 | 100% | 7700560.8 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
697 | Construction of Kangangu Dispensary -Kimorori Wempa Ward. | Construction of Kangangu Dispensary -Kimorori Wempa Ward. | To improve healthcare | no. of Health centers done |  | Development | MARAGUA | KIMORORI WEMPA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2025-03-27 |  |  | 2025-03-27 | 4753280 | 4753280 |  | MCG |  |  |  | 4753280 | 100% | 4753280 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
698 | Conversion of Mukyu Social Hall to a Dispensary -Township Ward | Conversion of Mukyu Social Hall to a Dispensary -Township Ward | To improve healthcare | no. of Health centers done |  | Development | KIHARU | TOWNSHIP |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2025-01-17 |  |  | 2025-01-17 | 2585344 | 2585344 |  | MCG |  |  |  | 2585344 | 100% | 2585344 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
699 | construction of Gathunya Dispensary - Kamacharia ward | construction of Gathunya Dispensary - Kamacharia ward | To improve healthcare | no. of Health centers done |  | Development | MATHIOYA | KAMACHARIA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2025-04-23 |  |  | 2025-04-23 | 8907750 | 8907750 |  | MCG |  |  |  | 8907750 | 100% | 8907750 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
700 | completion of Mabae dispensary and construction of ablution block- Gatanga Ward | completion of Mabae dispensary and construction of ablution block- Gatanga Ward | To improve healthcare | no. of Health centers done |  | Development | GATANGA | GATANGA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2025-06-03 |  |  | 2025-06-03 | 2644832.34 | 2644832.34 |  | MCG |  |  |  | 2644832.34 | 100% | 2644832.34 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
701 | Construction of Iruri Dispensary Ablution block-Kamacharia Ward | Construction of Iruri Dispensary Ablution block-Kamacharia Ward | To improve healthcare | no. of Health centers done |  | Development | MATHIOYA | KAMACHARIA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2025-02-26 |  |  | 2025-02-26 | 1112319 | 1112319 |  | MCG |  |  |  | 1112319 | 100% | 1112319 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
702 | Roadworks for Makindi Access Roads-Ithiru Ward | Roadworks for Makindi Access Roads-Ithiru Ward | To improve accessibility | no. of KM covered |  | Development | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-05-13 |  |  | 2025-05-13 | 1537978 | 1537978 |  | MCG |  |  |  | 1537978 | 100% | 1537978 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
703 | roadworks of Gaichaniru Catholic Church-Kahuho Access Road-Kakuzi Ward | roadworks of Gaichaniru Catholic Church-Kahuho Access Road-Kakuzi Ward | To improve accessibility | no. of KM covered |  | Development | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-04-15 |  |  | 2025-04-15 | 6207605 | 6207605 |  | MCG |  |  |  | 6207605 | 100% | 6207605 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
704 | road works of Kaharati Stage-Kaharati plots Access Road-Kamahuha Ward | road works of Kaharati Stage-Kaharati plots Access Road-Kamahuha Ward | To improve accessibility | no. of KM covered |  | Development | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-07-09 |  |  | 2025-07-09 | 2811174.84 | 2811174.84 |  | MCG |  |  |  | 2811174.84 | 100% | 2811174.84 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
705 | grading & gravelling works of Gathuku-Rukira Pry- Makuti Access Road-Muruka Ward | grading & gravelling works of Gathuku-Rukira Pry- Makuti Access Road-Muruka Ward | To improve accessibility | no. of KM covered |  | Development | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-16 |  |  | 2025-06-16 | 4184042 | 4184042 |  | MCG |  |  |  | 4184042 | 100% | 4184042 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
706 | roadworks of Lenana Access Road at Githingiri Estate-Mugumoini ward | roadworks of Lenana Access Road at Githingiri Estate-Mugumoini ward | To improve accessibility | no. of KM covered |  | Development | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-05-23 |  |  | 2025-05-23 | 4148308 | 4148308 |  | MCG |  |  |  | 4148308 | 100% | 4148308 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
707 | road works of Ha-Gitika-Gichia Access Road-Mugoiri Ward | road works of Ha-Gitika-Gichia Access Road-Mugoiri Ward | To improve accessibility | no. of KM covered |  | Development | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-19 |  |  | 2025-06-19 | 2832988 | 2832988 |  | MCG |  |  |  | 2832988 | 100% | 2832988 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
708 | road works of Gatumbi-Githima Access Road-Kinyona Ward | road works of Gatumbi-Githima Access Road-Kinyona Ward | To improve accessibility | no. of KM covered |  | Development | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-04-23 |  |  | 2025-04-23 | 2927552.93 | 2927552.93 |  | MCG |  |  |  | 2927552.93 | 100% | 2927552.93 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
709 | Road Works of Kiahiti Acess Road -Kanyenya-ini Ward | Road Works of Kiahiti Acess Road -Kanyenya-ini Ward | To improve accessibility | no. of KM covered |  | Development | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-03-06 |  |  | 2025-03-06 | 3043582.93 | 3043582.93 |  | MCG |  |  |  | 3043582.93 | 100% | 3043582.93 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
710 | Road works of Kigoro-Kiyo Access roads -Kambiti Ward | Road works of Kigoro-Kiyo Access roads -Kambiti Ward | To improve accessibility | no. of KM covered |  | Development | MARAGUA | KAMBITI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-03-14 |  |  | 2025-03-14 | 3624347 | 3624347 |  | MCG |  |  |  | 3624347 | 100% | 3624347 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
711 | road works of Nanga -Kimutii-ini Access road-Kakuzi Mitubiri Ward | road works of Nanga -Kimutii-ini Access road-Kakuzi Mitubiri Ward | To improve accessibility | no. of KM covered |  | Development | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-19 |  |  | 2025-02-19 | 3088718.6 | 3088718.6 |  | MCG |  |  |  | 3088718.6 | 100% | 3088718.6 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
712 | Road Works of Mahuria Access roads -Kagundu-ini Ward | Road Works of Mahuria Access roads -Kagundu-ini Ward | To improve accessibility | no. of KM covered |  | Development | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-19 |  |  | 2025-02-19 | 3134460 | 3134460 |  | MCG |  |  |  | 3134460 | 100% | 3134460 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
713 | road works for Kamoro -Kagono Access roads -Ithiru Ward | road works for Kamoro -Kagono Access roads -Ithiru Ward | To improve accessibility | no. of KM covered |  | Development | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-01-29 |  |  | 2024-01-29 | 2843663 | 2843663 |  | MCG |  |  |  | 2843663 | 100% | 2843663 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
714 | road works of Kiaro -Ndirii-ni -Mukoe access road -Kinyona ward | road works of Kiaro -Ndirii-ni -Mukoe access road -Kinyona ward | To improve accessibility | no. of KM covered |  | Development | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-01-24 |  |  | 2025-01-24 | 4449982.56 | 4449982.56 |  | MCG |  |  |  | 4449982.56 | 100% | 4449982.56 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
715 | Road Works of Kariti Access roads -Kagundu-ini Ward | Road Works of Kariti Access roads -Kagundu-ini Ward | To improve accessibility | no. of KM covered |  | Development | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-24 |  |  | 2025-02-24 | 3581846.1 | 3581846.1 |  | MCG |  |  |  | 3581846.1 | 100% | 3581846.1 |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
716 | road Work for Gitindima Access road | road Work for Gitindima Access road | To improve accessibility | no. of KM covered |  | Development | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-01-17 |  |  | 2025-01-17 | 3578600 | 3578600 |  | MCG |  |  |  | 3578600 | 100% | 3578600 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
717 | Grading of access roads- Wangu Ward | Grading of access roads- Wangu Ward | To improve accessibility | no. of KM covered |  | Development | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-05 |  |  | 2025-06-05 | 2397850 | 2397850 |  | MCG |  |  |  | 2397850 | 100% | 2397850 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
718 | road works of Mbari ya Kiiru -Mirichu & Mwea - Ndutumi Access road - Mugoiri Ward. | road works of Mbari ya Kiiru -Mirichu & Mwea - Ndutumi Access road - Mugoiri Ward. | To improve accessibility | no. of KM covered |  | Development | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-04-04 |  |  | 2025-04-04 | 2862752.57 | 2862752.57 |  | MCG |  |  |  | 2862752.57 | 100% | 2862752.57 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
719 | Improvement of Sand Harvesting Access roads - Gaturi Ward. | Improvement of Sand Harvesting Access roads - Gaturi Ward. | To improve accessibility | no. of KM covered |  | Development | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-12 |  |  | 2025-02-12 | 3447251.3 | 3447251.3 |  | MCG |  |  |  | 3447251.3 | 100% | 3447251.3 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
720 | road works for Kibiriri Access road - Ichagaki Ward | road works for Kibiriri Access road - Ichagaki Ward | To improve accessibility | no. of KM covered |  | Development | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-09 |  |  | 2025-06-09 | 5448910 | 5448910 |  | MCG |  |  |  | 5448910 | 100% | 5448910 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
721 | road works at Kagaa Access road | road works at Kagaa Access road | To improve accessibility | no. of KM covered |  | Development | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-01-17 |  |  | 2025-01-17 | 4193324 | 4193324 |  | MCG |  |  |  | 4193324 | 100% | 4193324 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
722 | road works - Makuyu Ward | road works - Makuyu Ward | To improve accessibility | no. of KM covered |  | Development | MARAGUA | MAKUYU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-24 |  |  | 2025-02-24 | 2900750 | 2900750 |  | MCG |  |  |  | 2900750 | 100% | 2900750 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
723 | road works for Gachomo -Kariaini -Kirurumo & Kiawambutu -Kiriti Acess roads - Muruka Ward | road works for Gachomo -Kariaini -Kirurumo & Kiawambutu -Kiriti Acess roads - Muruka Ward | To improve accessibility | no. of KM covered |  | Development | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-25 |  |  | 2025-06-25 | 6185559 | 6185559 |  | MCG |  |  |  | 6185559 | 100% | 6185559 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
724 | road works of Mutheru -Wakamiri access road | road works of Mutheru -Wakamiri access road | To improve accessibility | no. of KM covered |  | Development | KANDARA | RUCHU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-04 |  |  | 2025-02-04 | 3864669 | 3864669 |  | MCG |  |  |  | 3864669 | 100% | 3864669 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
725 | road works of Mathare-ini -ithanji & Kirere -Kindiri Access road - Kigumo ward | road works of Mathare-ini -ithanji & Kirere -Kindiri Access road - Kigumo ward | To improve accessibility | no. of KM covered |  | Development | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-19 |  |  | 2025-02-19 | 3623616.9 | 3623616.9 |  | MCG |  |  |  | 3623616.9 | 100% | 3623616.9 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
726 | road works of Mungetho -Huho-ini & Mihango dispensary - Mataka Access roads - Kambiti ward | road works of Mungetho -Huho-ini & Mihango dispensary - Mataka Access roads - Kambiti ward | To improve accessibility | no. of KM covered |  | Development | MARAGUA | KAMBITI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-01-17 |  |  | 2025-01-17 | 3091039 | 3091039 |  | MCG |  |  |  | 3091039 | 100% | 3091039 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
727 | road Works - Ithanga Ward | road Works - Ithanga Ward | To improve accessibility | no. of KM covered |  | Development | GATANGA | ITHANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-26 |  |  | 2025-06-26 | 2985452 | 2985452 |  | MCG |  |  |  | 2985452 | 100% | 2985452 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
728 | Road works of Ngararia - Gitiri Access road -Ngararia Ward | Road works of Ngararia - Gitiri Access road -Ngararia Ward | To improve accessibility | no. of KM covered |  | Development | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-01-23 |  |  | 2025-01-23 | 3110764.3 | 3110764.3 |  | MCG |  |  |  | 3110764.3 | 100% | 3110764.3 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
729 | Road works- Kinyona ward | Road works- Kinyona ward | To improve accessibility | no. of KM covered |  | Development | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-01-17 |  |  | 2025-01-17 | 1546280 | 1546280 |  | MCG |  |  |  | 1546280 | 100% | 1546280 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
730 | Road works - Kangari ward | Road works - Kangari ward | To improve accessibility | no. of KM covered |  | Development | KIGUMO | KANGARI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-26 |  |  | 2025-02-26 | 1659809 | 1659809 |  | MCG |  |  |  | 1659809 | 100% | 1659809 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
731 | road works at ACK Kandundu Church & Turbo Hill Access road - Township ward | road works at ACK Kandundu Church & Turbo Hill Access road - Township ward | To improve accessibility | no. of KM covered |  | Development | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-03-06 |  |  | 2025-03-06 | 5508176.15 | 5508176.15 |  | MCG |  |  |  | 5508176.15 | 100% | 5508176.15 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
732 | Road works of Gathama- Thuita access and Rurii- Kiunyu access road Kihumbuini Ward | road works of Gathama- Thuita access and Rurii- Kiunyu access road Kihumbuini Ward | To improve accessibility | no. of KM covered |  | Development | GATANGA | KIHUMBUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-03 |  |  | 2025-06-03 | 3186451.85 | 3186451.85 |  | MCG |  |  |  | 3186451.85 | 100% | 3186451.85 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
733 | road works of Mathingira access road Kamahuha Ward | road works of Mathingira access road Kamahuha Ward | To improve accessibility | no. of KM covered |  | Development | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-03-27 |  |  | 2025-03-27 | 2943565 | 2943565 |  | MCG |  |  |  | 2943565 | 100% | 2943565 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
734 | road works of Kiangenye access road -Kanyenyaini Ward | road works of Kiangenye access road -Kanyenyaini Ward | To improve accessibility | no. of KM covered |  | Development | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-05-09 |  |  | 2025-05-09 | 4200000 | 4200000 |  | MCG |  |  |  | 4200000 | 100% | 4200000 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
735 | road works of Kairi-ini access road Gitugi Ward | road works of Kairi-ini access road Gitugi Ward | To improve accessibility | no. of KM covered |  | Development | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-05 |  |  | 2025-06-05 | 2894745.45 | 2894745.45 |  | MCG |  |  |  | 2894745.45 | 100% | 2894745.45 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
736 | road works of Karii- Kayahwe and Inoi- Ihigaini access road Murarandia Ward | road works of Karii- Kayahwe and Inoi- Ihigaini access road Murarandia Ward | To improve accessibility | no. of KM covered |  | Development | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-11 |  |  | 2025-02-11 | 3092258 | 3092258 |  | MCG |  |  |  | 3092258 | 100% | 3092258 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
737 | road works of Kenyanjeru Karima and Wathani access road Rwathia Ward | road works of Kenyanjeru Karima and Wathani access road Rwathia Ward | To improve accessibility | no. of KM covered |  | Development | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-04 |  |  | 2025-02-04 | 3000999.92 | 3000999.92 |  | MCG |  |  |  | 3000999.92 | 100% | 3000999.92 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
738 | road works of Mananga Posta Kianjoma- Gikoe access roads and Construction of Gitereki- Kandara stairs Kiru Ward | road works of Mananga Posta Kianjoma- Gikoe access roads and Construction of Gitereki- Kandara stairs Kiru Ward | To improve accessibility | no. of KM covered |  | Development | MATHIOYA | KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-12-17 |  |  | 2024-12-17 | 5367084 | 5367084 |  | MCG |  |  |  | 5367084 | 100% | 5367084 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
739 | road works of River Nyumbo- Ndonga JCT access road Kahumbu Ward | road works of River Nyumbo- Ndonga JCT access road Kahumbu Ward | To improve accessibility | no. of KM covered |  | Development | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-01-23 |  |  | 2025-01-23 | 2951107 | 2951107 |  | MCG |  |  |  | 2951107 | 100% | 2951107 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
740 | road works of Kimiri access road and Kiguoya access road Ithiru Ward | road works of Kimiri access road and Kiguoya access road Ithiru Ward | To improve accessibility | no. of KM covered |  | Development | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-05-15 |  |  | 2025-05-15 | 2850393 | 2850393 |  | MCG |  |  |  | 2850393 | 100% | 2850393 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
741 | road works of Kiratu JCT- Kigio JCT access road Mugumoini Ward | road works of Kiratu JCT- Kigio JCT access road Mugumoini Ward | To improve accessibility | no. of KM covered |  | Development | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-18 |  |  | 2025-06-18 | 2938628 | 2938628 |  | MCG |  |  |  | 2938628 | 100% | 2938628 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
742 | road works of White gate- Gitige access road and Gatwariga- Gitiri access roads- Kariara Ward | road works of White gate- Gitige access road and Gatwariga- Gitiri access roads- Kariara Ward | To improve accessibility | no. of KM covered |  | Development | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-12 |  |  | 2025-02-12 | 2896979 | 2896979 |  | MCG |  |  |  | 2896979 | 100% | 2896979 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
743 | road works of Isabela Farm- Silanga Bridge and Hawamungura- Mama Iddi access road- Kakuzi Ward | road works of Isabela Farm- Silanga Bridge and Hawamungura- Mama Iddi access road- Kakuzi Ward | To improve accessibility | no. of KM covered |  | Development | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-07-23 |  |  | 2025-07-23 | 3530212.75 | 3530212.75 |  | MCG |  |  |  | 3530212.75 | 100% | 3530212.75 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
744 | road works of Kanyore access road- Kangari Ward | road works of Kanyore access road- Kangari Ward | To improve accessibility | no. of KM covered |  | Development | KIGUMO | KANGARI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-12 |  |  | 2025-02-12 | 2904114.87 | 2904114.87 |  | MCG |  |  |  | 2904114.87 | 100% | 2904114.87 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
745 | road works of Nguruweini Sec and Githaiti Primary access road- Gaichanjiru Ward | road works of Nguruweini Sec and Githaiti Primary access road- Gaichanjiru Ward | To improve accessibility | no. of KM covered |  | Development | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-26 |  |  | 2025-06-26 | 3186256 | 3186256 |  | MCG |  |  |  | 3186256 | 100% | 3186256 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
746 | Supply & Installation of Cabro Paving Slabs at Gatunyu Shopping Centre-Gatanga Subcounty | Supply & Installation of Cabro Paving Slabs | To improve accessibility | no. of KM covered |  | Development | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-06-24 |  |  | 2025-06-24 | 3396198 | 3396198 |  | MCG |  |  |  | 3396198 | 100% | 3396198 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
747 | Supply & Installation of Cabro paving Slabs at Sabasaba Shopping Center-Maragua Subcounty | Supply & Installation of Cabro paving Slabs | To improve accessibility | no. of KM covered |  | Development | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-12 |  |  | 2025-02-12 | 24894306 | 24894306 |  | MCG |  |  |  | 24894306 | 100% | 24894306 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
748 | Supply & Installation of Cabro Paving Slabs at Gitugi Shopping Center-Mathioya Subcounty | Supply & Installation of Cabro Paving | To improve accessibility | no. of KM covered |  | Development | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-19 |  |  | 2025-02-19 | 18927394 | 18927394 |  | MCG |  |  |  | 18927394 | 100% | 18927394 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
749 | Supply & Installation of Cabro Paving Slabs at Kirere Shopping Center-Kigumo Sucounty | Supply & Installation of Cabro Paving Slabs | To improve accessibility | no. of KM covered |  | Development | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-03-11 |  |  | 2025-03-11 | 16434779 | 16434779 |  | MCG |  |  |  | 16434779 | 100% | 16434779 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
750 | Supply & Installation of Cabro Paving Slabs at Kihoya Shopping Centre-Kangema Subcounty | Supply & Installation of Cabro Paving Slabs at Kihoya Shopping Centre-Kangema Subcounty | To improve accessibility | no. of KM covered |  | Development | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-03-12 |  |  | 2025-03-12 | 15734828 | 15734828 |  | MCG |  |  |  | 15734828 | 100% | 15734828 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
751 | Supply & Installation of Cabro Paving Slabs at Muruka Shopping Centre-Kandara Subcounty | Supply & Installation of Cabro Paving Slabs at Muruka Shopping Centre-Kandara Subcounty | To improve accessibility | no. of KM covered |  | Development | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-03-11 |  |  | 2025-03-11 | 13438014 | 13438014 |  | MCG |  |  |  | 13438014 | 100% | 13438014 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
752 | Supply & Installation of Cabro Paving Slabs at Kirogo & Wanjengi Shopping Center-Kiharu Subcounty | Supply & Installation of Cabro Paving Slabs at Kirogo & Wanjengi Shopping Center-Kiharu Subcounty | To improve accessibility | no. of KM covered |  | Development | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-03-12 |  |  | 2025-03-12 | 14064344 | 14064344 |  | MCG |  |  |  | 14064344 | 100% | 14064344 |  |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
753 | Upgrading to Concrete Standards of Shell Petrol Station-Mjini Mosque JCT | Upgrading to Concrete Standards of Shell Petrol Station-Mjini Mosque JCT | To improve accessibility | no. of KM covered |  | Development | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Murang'a Municipality | [8 empty] | DONOR | [8 empty] | PLANNED | [13 empty] | NO
754 | Installation of Cabro Paving blocks in Kenol Municipality | Installation of Cabro Paving blocks in Kenol Municipality | To improve accessibility | no. of KM covered |  | Development | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Kenol Municipality | [8 empty] | DONOR | [8 empty] | PLANNED | [13 empty] | NO
755 | Installation of Cabro Paving blocks in Kangari Municipality | Installation of Cabro | To improve accessibility | no. of KM covered |  | Development | KIGUMO | KANGARI |  | INFRASTRUCTURE | Kangari Municipality | [8 empty] | DONOR | [8 empty] | PLANNED | [13 empty] | NO
757 | Renovation of Nguthuru ECDE Centre-Muruka Ward | Renovation of Nguthuru ECDE Centre-Muruka Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-16 |  |  | 2024-02-16 | 2389730 | 2389730 |  | MCG |  |  |  | 2389730 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
758 | renovation of Ikuyu & Muirini ECDE Classroom-Ichagaki Ward. | renovation of Ikuyu & Muirini ECDE Classroom | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-16 |  |  | 2024-02-16 | 1738501 | 1738501 |  | MCG |  |  |  | 1738501 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
759 | construction of 2no. ECDE classrooms at Githiga-Ruchu Ward. | construction of 2no. ECDE classrooms at Githiga | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | RUCHU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-16 |  |  | 2024-02-16 | 2807820 | 2807820 |  | MCG |  |  |  | 2807820 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
760 | renovation of Rukira ECDE Centre-Muruka Ward. | renovation of Rukira ECDE Centre-Muruka Ward. | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-19 |  |  | 2024-02-19 | 2031990 | 2031990 |  | MCG |  |  |  | 2031990 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
761 | Renovation of AIC Gitare & Mungaria ECDE Centre-Ruchu Ward | Renovation of AIC Gitare & Mungaria ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | RUCHU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-19 |  |  | 2024-02-19 | 3388265 | 3388265 |  | MCG |  |  |  | 3388265 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
762 | Construction of Mathengeta and Kiambaa ECDE-Kambiti Ward. | Construction of Mathengeta and Kiambaa ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KAMBITI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-10-08 |  |  | 2024-10-08 | 2847100 | 2847100 |  | MCG |  |  |  | 2847100 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
763 | Earthworks,fencing & Construction of an ablution block at Kanyai ECDE-Ichagaki Ward. | Earthworks,fencing & Construction of an ablution block at Kanyai ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-14 |  |  | 2024-02-14 | 1499965 | 1499965 |  | MCG |  |  |  | 1499965 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
764 | Construction of Kamuiru and Huhoini ECDE Centres-Kambiti Ward. | Construction of Kamuiru and Huhoini ECDE Centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KAMBITI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-03 |  |  | 2024-04-03 | 3000116.06 | 3000116.06 |  | MCG |  |  |  | 3000116.06 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
765 | Renovation of Kariti,Maragwa-Nyakaguma & completion of Kiangoma ECDE Centres-Nginda Ward | Renovation of Kariti,Maragwa-Nyakaguma & completion of Kiangoma ECDE Centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | NGINDA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-03 |  |  | 2024-04-03 | 1726497.5 | 1726497.5 |  | MCG |  |  |  | 1726497.5 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
766 | Construction of Kihara ECDE Classroom-Makuyu Ward | Construction of Kihara ECDE Classroom | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | MAKUYU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-03 |  |  | 2024-04-03 | 1570058 | 1570058 |  | MCG |  |  |  | 1570058 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
767 | Renovation of Makuyu and Molwem ECDE Centres-Makuyu Ward | Renovation of Makuyu and Molwem ECDE Centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | MAKUYU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-03 |  |  | 2024-04-03 | 2452940 | 2452940 |  | MCG |  |  |  | 2452940 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
768 | Renovation of Maganjo & Thaara ECDE Classrooms-Kamahuha Ward. | Renovation of Maganjo & Thaara ECDE Classrooms | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KAMAHUHA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-03 |  |  | 2024-04-03 | 2518700 | 2518700 |  | MCG |  |  |  | 2518700 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
769 | Construction of Kiambamba & Gathanga ECDE Centre-Kambiti Ward. | Construction of Kiambamba & Gathanga ECDE Centre-Kambiti Ward. | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KAMBITI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-03 |  |  | 2024-04-03 | 3000109.1 | 3000109.1 |  | MCG |  |  |  | 3000109.1 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
770 | construction of 1 no. ECDE Classroom and toilet block at Gatangara ECDE-Kanyenya-ini Ward. | construction of 1 no. ECDE Classroom and toilet block at Gatangara ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-04 |  |  | 2024-04-04 | 1756065 | 1756065 |  | MCG |  |  |  | 1756065 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
771 | Renovation of Kirimaini,Gathathi & Gikindu primary ECDE Centres-Nginda Ward | Renovation of Kirimaini,Gathathi & Gikindu primary ECDE Centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | NGINDA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-03 |  |  | 2024-04-03 | 2153915.5 | 2153915.5 |  | MCG |  |  |  | 2153915.5 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
772 | renovation of Mithandukuini & Ngangaini ECDE Centre-Mugumoini Ward | renovation of Mithandukuini & Ngangaini ECDE Centre-Mugumoini Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | MUGUMOINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-04 |  |  | 2024-04-04 | 2476580 | 2476580 |  | MCG |  |  |  | 2476580 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
773 | renovation of Gikomora and Itaara ECDE Centre-Ichagaki Ward | renovation of Gikomora and Itaara ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-22 |  |  | 2024-04-22 | 1709900 | 1709900 |  | MCG |  |  |  | 1709900 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
774 | construction of Karuri ECDE-Murarandia Ward | construction of Karuri ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-16 |  |  | 2024-02-16 | 1448050 | 1448050 |  | MCG |  |  |  | 1448050 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
775 | Renovation works of Kiamuri ECDE Centre-Gaturi Ward | Renovation works of Kiamuri ECDE Centre-Gaturi Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-22 |  |  | 2024-04-22 | 2187515 | 2187515 |  | MCG |  |  |  | 2187515 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
776 | construction of Kiameni ECDE-Ichagaki Ward | construction of Kiameni ECDE-Ichagaki Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-22 |  |  | 2024-04-22 | 1343700 | 1343700 |  | MCG |  |  |  | 1343700 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
777 | renovation of Mahuria ECDE-Kagunduini Ward | renovation of Mahuria ECDE-Kagunduini Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-22 |  |  | 2024-04-22 | 3698910 | 3698910 |  | MCG |  |  |  | 3698910 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
778 | renovation of Machengecha ECDE & Githuguya-Kagunduini Ward | renovation of Machengecha ECDE & Githuguya-Kagunduini Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-10-03 |  |  | 2024-10-03 | 2377130 | 2377130 |  | MCG |  |  |  | 2377130 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
779 | Construction of Toilet block at Maruingi ECDE and Construction of one Mahuria ECDE-Kagunduini Ward | Construction of Toilet block at Maruingi ECDE and Construction of one Mahuria ECDE-Kagunduini Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-22 |  |  | 2024-04-22 | 1763352 | 1763352 |  | MCG |  |  |  | 1763352 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
780 | Construction of Their and Maria-ini ECDE-Murarandia Ward | Construction of Their and Maria-ini ECDE-Murarandia Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-16 |  |  | 2024-04-16 | 2569785 | 2569785 |  | MCG |  |  |  | 2569785 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
781 | Renovation of Rwathe and Kangui ECDE-Ruchu ward | Renovation of Rwathe and Kangui ECDE-Ruchu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | RUCHU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-28 |  |  | 2024-05-28 | 2574380 | 2574380 |  | MCG |  |  |  | 2574380 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
782 | Construction of Classroom & Toilet Block at Kaburungi ECDE-Ngararia Ward | Construction of Classroom & Toilet Block at Kaburungi ECDE-Ngararia Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-28 |  |  | 2024-05-28 | 1860470 | 1860470 |  | MCG |  |  |  | 1860470 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
783 | Construction & Renovation of Classrooms,Cabro and Gate at Vidhu Ramji ECDE-Township Ward | Construction & Renovation of Classrooms,Cabro and Gate at Vidhu Ramji ECDE-Township Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-28 |  |  | 2024-05-28 | 4992820 | 4992820 |  | MCG |  |  |  | 4992820 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
784 | Renovation of Karindundu & Mjini ECDE Centres & Constrruction of Technology ECDE Classroom-Township | Renovation of Karindundu & Mjini ECDE Centres & Constrruction of Technology ECDE Classroom-Township | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-28 |  |  | 2024-05-28 | 3799030 | 3799030 |  | MCG |  |  |  | 3799030 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
785 | Renovation of Naaro Primary ECDE-Ngararia Ward | Renovation of Naaro Primary ECDE-Ngararia Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-28 |  |  | 2024-05-28 | 1347870 | 1347870 |  | MCG |  |  |  | 1347870 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
786 | Renovation of Kawendo and Mugecha ECDE-Ngararia Ward | Renovation of Kawendo and Mugecha ECDE-Ngararia Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-28 |  |  | 2024-05-28 | 2436730 | 2436730 |  | MCG |  |  |  | 2436730 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
787 | Construction of Rurii ECDE Classroom | Construction of Rurii ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-28 |  |  | 2024-05-28 | 1432850 | 1432850 |  | MCG |  |  |  | 1432850 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
788 | Construction of Ngemu and Kagaa ECDE Classroom | Construction of Ngemu and Kagaa ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 3374050 | 3374050 |  | MCG |  |  |  | 3374050 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
789 | Fencing and Construction of Toilet Block at Kagira and Mugomoini ECDE Centres and Construction of a Generator Shed at Kagumoini Dispensary | Fencing and Construction of Toilet Block at Kagira and Mugomoini ECDE Centres and Construction of a Generator Shed at Kagumoini Dispensary | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-14 |  |  | 2024-05-14 | 2397755 | 2397755 |  | MCG |  |  |  | 2397755 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
790 | Construction of Githuya ECDE classrooms | Construction of Githuya ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-04-24 |  |  | 2024-04-24 | 1318500 | 1318500 |  | MCG |  |  |  | 1318500 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
791 | Renovation of Kirimiga ECDE classrooms | Renovation of Kirimiga ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-20 |  |  | 2024-05-20 | 1525660 | 1525660 |  | MCG |  |  |  | 1525660 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
792 | Renovation of Gathimaini & Mbogoini ECDE Centre | Renovation of Gathimaini & Mbogoini ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 3774160 | 3774160 |  | MCG |  |  |  | 3774160 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
793 | Renovation of Gathage and Gacharage ECDE - Ruchu Ward | Renovation of Gathage and Gacharage ECDE - Ruchu Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | RUCHU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-21 |  |  | 2024-05-21 | 3255150 | 3255150 |  | MCG |  |  |  | 3255150 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
794 | Renovation of Matunda and construction of Gaichanjiru ECDE centres - Kakuzi/Mitumbiri ward | Renovation of Matunda and construction of Gaichanjiru ECDE centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 2933512 | 2933512 |  | MCG |  |  |  | 2933512 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
795 | Renovation of Kariua and Wangai Pry ECDE Centres - Gaichanjiru Ward | Renovation of Kariua and Wangai Pry ECDE Centres - Gaichanjiru Ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 2216965 | 2216965 |  | MCG |  |  |  | 2216965 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
796 | Renovation of Gakoe-ini,Mutunguru and Nguku Primary Schools | Renovation of Gakoe-ini,Mutunguru and Nguku Primary Schools | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KIGUMO |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 5917095 | 5917095 |  | MCG |  |  |  | 5917095 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
797 | Renovation of Kiawambogo ECDE,Fencing of Matara & Karima ECDE | Renovation of Kiawambogo ECDE,Fencing of Matara & Karima ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-28 |  |  | 2024-05-28 | 1889780 | 1889780 |  | MCG |  |  |  | 1889780 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
798 | Earthworks,Fencing and Construction of an ablution block at Kanyai ECDE Centre | Earthworks,Fencing and Construction of an ablution block at Kanyai ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-28 |  |  | 2024-05-28 | 1499965 | 1499965 |  | MCG |  |  |  | 1499965 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
799 | Construction of 2No. Classrooms at Thagari ECDE Centre | Construction of 2No. Classrooms at Thagari ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 3094140 | 3094140 |  | MCG |  |  |  | 3094140 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
800 | Construction of 1 No. Classroom at Majuu ECDE Centre and Renovtion of 1 No. Classroom at Kahuruini ECDE Centre | Construction of 1 No. Classroom at Majuu ECDE Centre and Renovtion of 1 No. Classroom at Kahuruini ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 2413720 | 2413720 |  | MCG |  |  |  | 2413720 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
801 | Renovation of Murai Primary & Gathiru ECDE Centers | Renovation of Murai Primary & Gathiru ECDE Centers | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 1849660 | 1849660 |  | MCG |  |  |  | 1849660 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
802 | Renovation of Mbari ya Hiti and Kamaguta Primary ECDE Centers | Renovation of Mbari ya Hiti and Kamaguta Primary ECDE Centers | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 2615280 | 2615280 |  | MCG |  |  |  | 2615280 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
803 | Renovation of Ablution Block,Construction of a Shed and of Cabro works at Mukuyu ECDE | Renovation of Ablution Block,Construction of a Shed and of Cabro works at Mukuyu ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 1617290 | 1617290 |  | MCG |  |  |  | 1617290 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
804 | Renovation of Watuku,Kibaka and Fencing at Kahethu ECDE | Renovation of Watuku,Kibaka and Fencing at Kahethu ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 2237210 | 2237210 |  | MCG |  |  |  | 2237210 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
805 | Renovation of Rwathia ECDE and Kihoya ECDE | Renovation of Rwathia ECDE and Kihoya ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 2896130 | 2896130 |  | MCG |  |  |  | 2896130 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
806 | Construction of 1 No. ECDE Classroom at Gachogi ECDE and Renovation of Kayu Primary ECDE Centre | Construction of 1 No. ECDE Classroom at Gachogi ECDE and Renovation of Kayu Primary ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 2213254 | 2213254 |  | MCG |  |  |  | 2213254 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
807 | Renovation of Gaichanjiru & Githaiti ECDE Centres | Renovation of Gaichanjiru & Githaiti ECDE Centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 2992490 | 2992490 |  | MCG |  |  |  | 2992490 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
808 | Construction of a classroom and toilet block at Kieni ECDE | Construction of a classroom and toilet block at Kieni ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-18 |  |  | 2024-05-18 | 2252360 | 2252360 |  | MCG |  |  |  | 2252360 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
809 | Renovation of Githiga Primary ECDE and Kanyenyaini Primary ECDE | Renovation of Githiga Primary ECDE and Kanyenyaini Primary ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-18 |  |  | 2024-05-18 | 2124580 | 2124580 |  | MCG |  |  |  | 2124580 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
810 | Renovation of Munyatha & Kiayatta Pry ECDE Centres | Renovation of Munyatha & Kiayatta Pry ECDE Centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 1124440 | 1124440 |  | MCG |  |  |  | 1124440 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
811 | Renovation of Kiamiri and Renovation and Fencing of Rugaita ECDE | Renovation of Kiamiri and Renovation and Fencing of Rugaita ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 2224450 | 2224450 |  | MCG |  |  |  | 2224450 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
812 | Construction of Gakurari and Renovation of Gatunyu ECDE Center | Construction of Gakurari and Renovation of Gatunyu ECDE Center | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | MUGUMOINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 3135100 | 3135100 |  | MCG |  |  |  | 3135100 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
813 | Construction of Gichuka and Renovation of Boro ECDE | Construction of Gichuka and Renovation of Boro ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 2303824 | 2303824 |  | MCG |  |  |  | 2303824 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
814 | Renovation works for Ithiringa and Gatheru ECDE Center | Renovation works for Ithiringa and Gatheru classrooms | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | WANGU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-19 |  |  | 2024-06-19 | 1671580 | 1671580 |  | MCG |  |  |  | 1671580 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
815 | Renovation of Mukangu and Gitie ECDE/Construction of footpath for Wanjengi Coffee Factory | Renovation of Mukangu and Gitie ECDE/Construction of footpath for Wanjengi Coffee Factory | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | WANGU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 2837980 | 2837980 |  | MCG |  |  |  | 2837980 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
816 | Renovation of Karuri ECDE Centre and Nyakahura ECDE Center | Renovation of Karuri ECDE Centre and Nyakahura ECDE Center | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 2647490 | 2647490 |  | MCG |  |  |  | 2647490 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
817 | Construction of Ngecha and Hingu ECDE | Construction of Ngecha and Hingu ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KANGARI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 2929970 | 2929970 |  | MCG |  |  |  | 2929970 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
818 | Construction of Nguruini & Gatitu ECDE Classrooms | Construction of Nguruini & Gatitu ECDE Classrooms | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 3772308 | 3772308 |  | MCG |  |  |  | 3772308 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
819 | Renovation of Ruru,Kiambuthia and Construction of Mioro ECDE Toilet Block | Renovation of Ruru,Kiambuthia and Construction of Mioro ECDE Toilet Block | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 4239077 | 4239077 |  | MCG |  |  |  | 4239077 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
820 | Renovation of Njogu-ini & Kairi Pry ECDE Classrooms | Renovation of Njogu-ini & Kairi Pry ECDE Classrooms | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 2801485 | 2801485 |  | MCG |  |  |  | 2801485 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
821 | Renovations of Kagumoini & Warugara ECDE Classrooms | Renovations of Kagumoini & Warugara ECDE Classrooms | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 3862800 | 3862800 |  | MCG |  |  |  | 3862800 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
822 | Renovation of Kaguthi,Gathugu & Kandara orphanage ECDE Classrooms | Renovation of Kaguthi,Gathugu & Kandara orphanage ECDE Classrooms | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 2600202 | 2600202 |  | MCG |  |  |  | 2600202 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
823 | Construction of Nyagatugu ECDE Classroom | Construction of Nyagatugu ECDE Classroom | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 2813848 | 2813848 |  | MCG |  |  |  | 2813848 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
824 | Renovation of Mwema and Ndonga Primary ECDE | Renovation of Mwema and Ndonga Primary ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 3718346 | 3718346 |  | MCG |  |  |  | 3718346 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
825 | Renovation of 2 No. Classroms at Kiugu ECDE Centre | Renovation of 2 No. Classroms at Kiugu ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | MUTHITHI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 1568990 | 1568990 |  | MCG |  |  |  | 1568990 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
826 | Construction of a Classroom,Renovation of a Classroom,Fencing and Construction of an Ablution Block at Njora-Kiariki ECDE Centre | Construction of a Classroom,Renovation of a Classroom,Fencing and Construction of an Ablution Block at Njora-Kiariki ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | MUTHITHI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 2822355 | 2822355 |  | MCG |  |  |  | 2822355 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
827 | Renovation & Fencing of Paul Mbiu,Kiawaihiga ECDE Cenres | Renovation & Fencing of Paul Mbiu,Kiawaihiga ECDE Cenres | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | MAKUYU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 3300015 | 3300015 |  | MCG |  |  |  | 3300015 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
828 | Construction of Gaichanjiru and construction of mbogo & rurai E.C.D.E | Construction of Gaichanjiru and construction of mbogo & rurai E.C.D.E | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 3002700 | 3002700 |  | MCG |  |  |  | 3002700 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
829 | Construction of John the Baptist (Kairi) & Riakindu E.C.D.E Centres | Construction of John the Baptist (Kairi) & Riakindu E.C.D.E Centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-11-05 |  |  | 2024-11-05 | 3002700 | 3002700 |  | MCG |  |  |  | 3002700 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
830 | Renovation of classroom at Gikoe & Wambwe ECDE centres | Renovation of classroom at Gikoe & Wambwe ECDE centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 2967999.14 | 2967999.14 |  | MCG |  |  |  | 2967999.14 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
831 | Renovation of Githendu & muiri-ini ECDE centres | Renovation of Githendu & muiri-ini ECDE centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 2802236 | 2802236 |  | MCG |  |  |  | 2802236 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
832 | Construction of wempa ECDE and renovation of Methi CCF ECDE classroom | Construction of wempa ECDE and renovation of Methi CCF ECDE classroom | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-11 |  |  | 2024-06-11 | 2934475 | 2934475 |  | MCG |  |  |  | 2934475 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
833 | Renovation of Mwanawikio and rubiru ECDE centres | Renovation of classrooms for Mwanawikio and rubiru ECDE centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 2852160 | 2852160 |  | MCG |  |  |  | 2852160 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
834 | Renovation of karura and kiruri pry ECDE centre | Renovation of karura and kiruri classrooms ECDE centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 3073933 | 3073933 |  | MCG |  |  |  | 3073933 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
835 | Construction of Matandara and Renovation of Kamukabi ECDE | Construction of Matandara and Renovation of Kamukabi ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 3545285 | 3545285 |  | MCG |  |  |  | 3545285 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
836 | Construction of Gitungano ECDE Centre | Construction of Gitungano ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 1354220 | 1354220 |  | MCG |  |  |  | 1354220 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
837 | Construction of Njoguini Primary ECDE | Construction of Njoguini Primary ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 1459755 | 1459755 |  | MCG |  |  |  | 1459755 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
838 | Renovation of Gituto Mumbi & Kirogo ECDE Center | Renovation of Gituto Mumbi & Kirogo ECDE Center | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | WANGU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 4064765 | 4064765 |  | MCG |  |  |  | 4064765 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
839 | Renovation of Giteme & Karangi Primary ECDE | Renovation of Giteme & Karangi Primary ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KARIARA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-12 |  |  | 2024-06-12 | 2938060 | 2938060 |  | MCG |  |  |  | 2938060 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
840 | Renovations and Construction of an Ablution Block at Kamunyaka ECDE | Renovations and Construction of an Ablution Block at Kamunyaka ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KARIARA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-07-01 |  |  | 2024-07-01 | 1872465 | 1872465 |  | MCG |  |  |  | 1872465 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
841 | Renovation and construction of Kangangu ECDE classrooms and construction of Magoto ECDE | Renovation and construction of Kangangu ECDE classrooms and construction of Magoto ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 4140850 | 4140850 |  | MCG |  |  |  | 4140850 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
842 | Construction of Kagarie ECDE Centre and Pit Latrine Block at Mwea | Construction of Kagarie ECDE Centre and Pit Latrine Block at Mwea | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KARIARA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 1840500 | 1840500 |  | MCG |  |  |  | 1840500 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
843 | Construction and renovation of Iruini Primary | Construction and renovation of Iruini Primary | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KANGARI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 2362790 | 2362790 |  | MCG |  |  |  | 2362790 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
844 | Construction of Kahuti Primary ECDE | Construction of Kahuti Primary ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KANGARI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 1464985 | 1464985 |  | MCG |  |  |  | 1464985 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
845 | Construction of Gaturi(Mugeka) ECDE Center | Construction of Gaturi(Mugeka) ECDE Center | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 1480660 | 1480660 |  | MCG |  |  |  | 1480660 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
846 | Construction of a classroom and a toilet block at Mugaaini ECDE Centre | Construction of a classroom and a toilet block at Mugaaini ECDE Centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 2297140 | 2297140 |  | MCG |  |  |  | 2297140 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
847 | Construction of classroom & Toilet block & Renovation at Githuri ECDE | Construction of classroom & Toilet block & Renovation at Githuri ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-10-14 |  |  | 2024-10-14 | 1655275 | 1655275 |  | MCG |  |  |  | 1655275 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
848 | Construction of classroom & Ablution block & Renovation works of Maragi ECDE | Construction of classroom & Ablution block & Renovation works of Maragi ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-10-14 |  |  | 2024-10-14 | 4845015 | 4845015 |  | MCG |  |  |  | 4845015 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
849 | Construction of classroom and fencing for Upendo ECDE | Construction of classroom and fencing for Upendo ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-10-14 |  |  | 2024-10-14 | 2999580 | 2999580 |  | MCG |  |  |  | 2999580 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
850 | Renovation of Kiaruguru and Mabanda ECDE | Renovation of Kiaruguru and Mabanda ECDE classrooms | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | GATANGA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-09-30 |  |  | 2024-09-30 | 3190066 | 3190066 |  | MCG |  |  |  | 3190066 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
851 | Construction of 1no. ECDE classroom at Kaliala & Katooni ECDE centres | Construction of 1no. ECDE classroom at Kaliala & Katooni ECDE centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | ITHANGA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2025-07-28 |  |  | 2025-07-28 | 2793720 | 2793720 |  | MCG |  |  |  | 2793720 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
852 | Construction of Thuita dispensary-Kamacharia | Construction of Thuita dispensary-Kamacharia | To improve healthcare | No. of health centers done |  |  | MATHIOYA | KAMACHARIA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-02-19 |  |  | 2024-02-19 | 7976838.6 | 7976838.6 |  | MCG |  |  |  | 7976838.6 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
853 | Renovation of Murarandia Health Centre | Renovation of Murarandia Health Centre | To improve healthcare | No. of health centers done |  |  | KIHARU | MURARANDIA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-02-16 |  |  | 2024-02-16 | 3437445.4 | 3437445.4 |  | MCG |  |  |  | 3437445.4 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
854 | Completion of Kagongo dispensary-Kiru | Completion of Kagongo dispensary-Kiru | To improve healthcare | No. of health centers done |  |  | MATHIOYA | KIRU |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-02-16 |  |  | 2024-02-16 | 2274640 | 2274640 |  | MCG |  |  |  | 2274640 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
855 | renovation of Gatitu Dispensary -Kagunduini | renovation of Gatitu Dispensary -Kagunduini | To improve healthcare | No. of health centers done |  |  | KANDARA | KAGUNDUINI |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-03-26 |  |  | 2024-03-26 | 3641638 | 3641638 |  | MCG |  |  |  | 3641638 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
856 | extension, renovation dispensary ablution block, Construction of walkways to gates and incenerator - Muguru Ward in Muranga County | extension, renovation dispensary ablution block, Construction of walkways to gates and incenerator - Muguru Ward in Muranga County | To improve healthcare | No. of health centers done |  |  | KANGEMA | MUGURU |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-04-30 |  |  | 2024-04-30 | 3057887.6 | 3057887.6 |  | MCG |  |  |  | 3057887.6 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
857 | Completion works for Kiangage Dispensary-Township | Completion works for Kiangage Dispensary-Township | To improve healthcare | No. of health centers done |  |  | KIHARU | TOWNSHIP |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 1244590 | 1244590 |  | MCG |  |  |  | 1244590 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
858 | Renovation of Mungaria & Ruona dispensary-Ruchu | Renovation of Mungaria & Ruona dispensary-Ruchu | To improve healthcare | No. of health centers done |  |  | KANDARA | RUCHU |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 852760 | 852760 |  | MCG |  |  |  | 852760 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
859 | Completion of Boro Dispensary-Kinyona | Completion of Boro Dispensary-Kinyona | To improve healthcare | No. of health centers done |  |  | KIGUMO | KINYONA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-09-02 |  |  | 2024-09-02 | 1170718.4 | 1170718.4 |  | MCG |  |  |  | 1170718.4 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
860 | Renovation of Gathimaini dispensary-Kahumbu | Renovation of Gathimaini dispensary-Kahumbu | To improve healthcare | No. of health centers done |  |  | KIGUMO | KAHUMBU |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-05-31 |  |  | 2024-05-31 | 3774160 | 3774160 |  | MCG |  |  |  | 3774160 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
861 | Renovation of Kambirwa Health Centre-Mbiri | Renovation of Kambirwa Health Centre-Mbiri | To improve healthcare | No. of health centers done |  |  | KIHARU | MBIRI |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-09-02 |  |  | 2024-09-02 | 2075048.6 | 2075048.6 |  | MCG |  |  |  | 2075048.6 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
862 | Construction of Laboratory at Mukumu dispensary | Construction of Laboratory at Mukumu dispensary | To improve healthcare | No. of health centers done |  |  | KIHARU | MURARANDIA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 543230 | 543230 |  | MCG |  |  |  | 543230 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
863 | Renovation of Mabae Dispensary-Gatanga | Renovation of Mabae Dispensary-Gatanga | To improve healthcare | No. of health centers done |  |  | GATANGA | GATANGA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-10-14 |  |  | 2024-10-14 | 1839222 | 1839222 |  | MCG |  |  |  | 1839222 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
864 | Ndakaini Maternity Renovation-Kariara | Ndakaini Maternity Renovation-Kariara | To improve healthcare | No. of health centers done |  |  | GATANGA | KARIARA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 2066450 | 2066450 |  | MCG |  |  |  | 2066450 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
865 | Construction of Kamacharia & Kairi Laboratory Phase 1 | Construction of Kamacharia & Kairi Laboratory Phase 1 | To improve healthcare | No. of health centers done |  |  | MATHIOYA | KAMACHARIA |  | HEALTH | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 4951130 | 4951130 |  | MCG |  |  |  | 4951130 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
866 | Poposed works in various ECDE centres -Gatanga Subcounty | Construction works for varoius facilities | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-16 |  |  | 2024-02-16 | 300000 | 300000 |  | MCG |  |  |  | 300000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
867 | Poposed works for various ECDE centres-Kangema Subcounty | Construction works for various ECDE centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | KANYENYAINI, MUGURU, RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-19 |  |  | 2024-02-19 | 297000 | 297000 |  | MCG |  |  |  | 297000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
868 | Poposed works for various ECDE centres-Kiharu Subcounty | Construction works for various ECDE centres | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  | 2024-02-16 |  |  | 2024-02-16 | 297000 | 297000 |  | MCG |  |  |  | 297000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
869 | Construction of Warimwe Footbridge-Kinyona | Construction of Warimwe Footbridge | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-19 |  |  | 2024-06-19 | 1617352 | 1617352 |  | MCG |  |  |  | 1617352 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
870 | Construction of Footbridges Karega-Warutara,Ngerechi-Pluto & Nduka Moja-Njunu-Kariara | Construction of Footbridges Karega-Warutara,Ngerechi-Pluto & Nduka Moja-Njunu-Kariara | To improve accessibilty | No. of KMs done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 1939140 | 1939140 |  | MCG |  |  |  | 1939140 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
871 | Construction of S.K footbridge-Kanyenyaini | Construction of S.K footbridge | To improve accessibilty | No. of KMs done |  |  | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-10-11 |  |  | 2024-10-11 | 1715640 | 1715640 |  | MCG |  |  |  | 1715640 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
872 | Construction of Geitwa-Kiambugi,Kibuu-Mukurweini Footbridges-Gaturi | Construction of Geitwa-Kiambugi,Kibuu-Mukurweini Footbridges | To improve accessibilty | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-12-02 |  |  | 2024-12-02 | 1178068 | 1178068 |  | MCG |  |  |  | 1178068 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
873 | Grading & graveling of Ngurwe-ini Access Road-Gaichanjiru | Grading & graveling of Ngurwe-ini Access Road | To improve accessibilty | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 3735780 | 3735780 |  | MCG |  |  |  | 3735780 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
874 | Grading of Access Roads-Kakuzi | Grading of Access Roads | To improve accessibilty | No. of KMs done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-20 |  |  | 2024-06-20 | 1798000 | 1798000 |  | MCG |  |  |  | 1798000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
875 | Grading and gravelling of Kiamathanji and Karugia access road - Gaichanjiru Ward | Grading and gravelling of Kiamathanji and Karugia access road - Gaichanjiru Ward | To improve accessibilty | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 3527800 | 3527800 |  | MCG |  |  |  | 3527800 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
876 | Grading & gravelling works of Kibiko-Gitie-Gachibi Access Road-Kamacharia | Grading & gravelling works of Kibiko-Gitie-Gachibi Access Road-Kamacharia | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 3738390 | 3738390 |  | MCG |  |  |  | 3738390 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
877 | Grading & gravelling works of Gituamba-Kabuere-Gathangari Access Road-Muruka | Grading & gravelling works of Gituamba-Kabuere-Gathangari Access Road-Muruka | To improve accessibilty | No. of KMs done |  |  | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 3289180 | 3289180 |  | MCG |  |  |  | 3289180 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
878 | Grading & gravelling of Sunset - Thumba - Gachamba access road-Ithiru | Grading & gravelling of Sunset - Thumba - Gachamba access road-Ithiru | To improve accessibilty | No. of KMs done |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-19 |  |  | 2024-06-19 | 4749156 | 4749156 |  | MCG |  |  |  | 4749156 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
879 | Grading & gravelling works of Ndiara-ini Access road-Ng'araria | Grading & gravelling works of Ndiara-ini Access road-Ng'araria | To improve accessibilty | No. of KMs done |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 2822164 | 2822164 |  | MCG |  |  |  | 2822164 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
880 | Road works for Kangari - Umoja - Ngurwe-ini Catholic Church - Kirichiungu access Road- Kangari | Road works for Kangari - Umoja - Ngurwe-ini Catholic Church - Kirichiungu access Road- Kangari | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KANGARI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 6605040 | 6605040 |  | MCG |  |  |  | 6605040 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
881 | Grading & gravelling works of Machengecha - kagundu-ini market - Kamunyaka access road-Kagunduni | Grading & gravelling works of Machengecha - kagundu-ini market - Kamunyaka access road-Kagunduni | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 3466080 | 3466080 |  | MCG |  |  |  | 3466080 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
882 | Grading & gravelling works of orphanage - mayor - mihali - kamunyaka - karobi access road -Ithiru | Grading & gravelling works of orphanage - mayor - mihali - kamunyaka - karobi access road -Ithiru | To improve accessibilty | No. of KMs done |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-19 |  |  | 2024-06-19 | 4821656 | 4821656 |  | MCG |  |  |  | 4821656 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
883 | Grading & gravelling works of mahuti-ini - mai-ini - gathige shopping centre access road-Kagunduini | Grading & gravelling works of mahuti-ini - mai-ini - gathige shopping centre access road-Kagunduini | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 2837505 | 2837505 |  | MCG |  |  |  | 2837505 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
884 | Grading & gravelling works of maganjo - wanjihi, rwanguno - manyatta, kaharati - wamunderu, kiranga - araeli, aiagikiro - kabogoro - ihoero ndorome & mathingira - karugiro access road-Kamahuha | Grading & gravelling works of maganjo - wanjihi, rwanguno - manyatta, kaharati - wamunderu, kiranga - araeli, aiagikiro - kabogoro - ihoero ndorome & mathingira - karugiro access road-Kamahuha | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 4192240 | 4192240 |  | MCG |  |  |  | 4192240 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
885 | Grading & gravelling works of Three in one access road | Grading & gravelling works of Three in one access road | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 1610515 | 1610515 |  | MCG |  |  |  | 1610515 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
886 | Grading & gravelling works of kabwe - CFF Church access road | Grading & gravelling works of kabwe - CFF Church access road | To improve accessibilty | No. of KMs done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 1839760 | 1839760 |  | MCG |  |  |  | 1839760 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
887 | Grading & gravelling works of kiamuhu - kwa ngeneri access road | Grading & gravelling works of kiamuhu - kwa ngeneri access road | To improve accessibilty | No. of KMs done |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 2822048 | 2822048 |  | MCG |  |  |  | 2822048 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
888 | Grading & gravelling of Kanyiyi-ini Catholic Church - kagenyo - Gatumbu shopping centre | Grading & gravelling of Kanyiyi-ini Catholic Church - kagenyo - Gatumbu shopping centre | To improve accessibilty | No. of KMs done |  |  | KANDARA | MURUKA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 7165900 | 7165900 |  | MCG |  |  |  | 7165900 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
889 | Grading & gravelling of kagio-ini - Thuruthuru access road | Grading & gravelling of kagio-ini - Thuruthuru access road | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 5594680 | 5594680 |  | MCG |  |  |  | 5594680 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
890 | Renovation of kahero and soronge E.C.D.E Centres | Renovation of kahero and soronge E.C.D.E Centres | To improve accessibilty | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 2445295 | 2445295 |  | MCG |  |  |  | 2445295 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
891 | Grading & gravelling works of githunguri - thithi, hamza - giatunyu - gaciani - kamathare - ngano - bembe access road | Grading & gravelling works of githunguri - thithi, hamza - giatunyu - gaciani - kamathare - ngano - bembe access road | To improve accessibilty | No. of KMs done |  |  | GATANGA | KIHUMBUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 3596928 | 3596928 |  | MCG |  |  |  | 3596928 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
892 | Grading & gravelling works of kahumbu polytechnic - muthithi access road | Grading & gravelling works of kahumbu polytechnic - muthithi access road | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KAHUMBU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 3123400.92 | 3123400.92 |  | MCG |  |  |  | 3123400.92 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
893 | Grading & gravelling works of old tarmac road - kwa Njanju - kabati coffee factory - tosheka access road | Grading & gravelling works of old tarmac road - kwa Njanju - kabati coffee factory - tosheka access road | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2025-02-24 |  |  | 2025-02-24 | 3010925 | 3010925 |  | MCG |  |  |  | 3010925 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
894 | Opening of Rwathia Access | Opening of Rwathia Access | To improve accessibilty | No. of KMs done |  |  | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 2648280 | 2648280 |  | MCG |  |  |  | 2648280 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
895 | Grading & gravelling works of Riambara coffee factory-Kibaaka-Gatuta-Kwa Mbuthia Access road | Grading & gravelling works of Riambara coffee factory-Kibaaka-Gatuta-Kwa Mbuthia Access road | To improve accessibilty | No. of KMs done |  |  | GATANGA | KIHUMBUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 3801784 | 3801784 |  | MCG |  |  |  | 3801784 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
896 | Grading & gravelling works of Manyaga Access road | Grading & gravelling works of Manyaga Access road | To improve accessibilty | No. of KMs done |  |  | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 2478920 | 2478920 |  | MCG |  |  |  | 2478920 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
897 | Construction of kasoo-ni vented drift | Construction of kasoo-ni vented drift | To improve accessibilty | No. of KMs done |  |  | GATANGA | ITHANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 2186832 | 2186832 |  | MCG |  |  |  | 2186832 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
898 | Grading & gravelling of ihumbu plot - kangethu - mutaraho - kariti - karinga CatholicChurch access road | Grading & gravelling of ihumbu plot - kangethu - mutaraho - kariti - karinga CatholicChurch access road | To improve accessibilty | No. of KMs done |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 4648280 | 4648280 |  | MCG |  |  |  | 4648280 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
899 | Grading of Access Roads | Grading of Access Roads | To improve accessibilty | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 1786400 | 1786400 |  | MCG |  |  |  | 1786400 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
900 | Grading of Access Roads | Grading of Access Roads | To improve accessibilty | No. of KMs done |  |  | GATANGA | ITHANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 3052553.92 | 3052553.92 |  | MCG |  |  |  | 3052553.92 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
901 | Grading & gravelling of kabuku - kingotore access road | Grading & gravelling of kabuku - kingotore access road | To improve accessibilty | No. of KMs done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 5327300 | 5327300 |  | MCG |  |  |  | 5327300 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
902 | Grading & gravelling works of gatumbi - githima access road | Grading & gravelling works of gatumbi - githima access road | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 3045000 | 3045000 |  | MCG |  |  |  | 3045000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
903 | Grading & gravelling (spot improvement) of kandundu - giathuku access | Grading & gravelling (spot improvement) of kandundu - giathuku access | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 1881520 | 1881520 |  | MCG |  |  |  | 1881520 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
904 | Opening & drainage works of Gaichanjiru access roads | Opening & drainage works of Gaichanjiru access roads | To improve accessibilty | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 2984880 | 2984880 |  | MCG |  |  |  | 2984880 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
905 | Grading & gravelling works of JJRoad-Gatundu Pry-Githima & Mugoiri Kadegenye via Wairagu Residence-JCT Kwa Paul Shopping Centre | Grading & gravelling works of JJRoad-Gatundu Pry-Githima & Mugoiri Kadegenye via Wairagu Residence-JCT Kwa Paul Shopping Centre | To improve accessibilty | No. of KMs done |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 3451696 | 3451696 |  | MCG |  |  |  | 3451696 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
906 | Grading & gravelling works of Yamugwezi JCT-Shopping Centre-Kabius JCT-Yamugwe Sec-Catholic church & Ngaru Borehole JCT-Village Tank A ccess Road | Grading & gravelling works of Yamugwezi JCT-Shopping Centre-Kabius JCT-Yamugwe Sec-Catholic church & Ngaru Borehole JCT-Village Tank A ccess Road | To improve accessibilty | No. of KMs done |  |  | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 4733960 | 4733960 |  | MCG |  |  |  | 4733960 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
907 | grading & gravelling works of Wamahiga-Kiawairimu-Kwa mianomiboco-ini-Njora-Kiara Access Roads. | grading & gravelling works of Wamahiga-Kiawairimu-Kwa mianomiboco-ini-Njora-Kiara Access Roads. | To improve accessibilty | No. of KMs done |  |  | KIGUMO | MUTHITHI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 4737440 | 4737440 |  | MCG |  |  |  | 4737440 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
908 | Grading & gravelling of Kiamathanji & Karugia Access Road | Grading & gravelling of Kiamathanji & Karugia Access Road | To improve accessibilty | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 3527800 | 3527800 |  | MCG |  |  |  | 3527800 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
909 | Rehabilitation of Rimui Drift(Kirathani) | Rehabilitation of Rimui Drift(Kirathani) | To improve accessibilty | No. of KMs done |  |  | GATANGA | ITHANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-27 |  |  | 2024-06-27 | 1019350 | 1019350 |  | MCG |  |  |  | 1019350 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
910 | Grading & Gravelling of Kwa Maina Nyerere-PCEA Ha Muguruki-Ha Nduma Gathimu Access Road | Grading & Gravelling of Kwa Maina Nyerere-PCEA Ha Muguruki-Ha Nduma Gathimu Access Road | To improve accessibilty | No. of KMs done |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 4475512 | 4475512 |  | MCG |  |  |  | 4475512 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
911 | Grading & gravelling works of Mutungano Access Road | Grading & gravelling works of Mutungano Access Road | To improve accessibilty | No. of KMs done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 2672872 | 2672872 |  | MCG |  |  |  | 2672872 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
912 | Grading and gravelling works of Zabka-Nginyi-Kabuku access road- Kimorori Ward | Grading and gravelling works of Zabka-Nginyi-Kabuku access road- Kimorori Ward | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-26 |  |  | 2024-06-26 | 2479268 | 2479268 |  | MCG |  |  |  | 2479268 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
913 | Grading and gravelling works of St Joseph Kiangage/Murari and Bishop Residence-Sport Cub-Kambi acess road | Grading and gravelling works of St Joseph Kiangage/Murari and Bishop Residence-Sport Cub-Kambi acess road | To improve accessibilty | No. of KMs done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 2344244 | 2344244 |  | MCG |  |  |  | 2344244 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
914 | Grading & gravelling works of Laini-Kiarie Gatoro Access Road | Grading & gravelling works of Laini-Kiarie Gatoro Access Road | To improve accessibilty | No. of KMs done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-19 |  |  | 2024-06-19 | 1799624 | 1799624 |  | MCG |  |  |  | 1799624 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
915 | Grading & gravelling works of Ndunyuchege Market Access Road | Grading & gravelling works of Ndunyuchege Market Access Road | To improve accessibilty | No. of KMs done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 2067120 | 2067120 |  | MCG |  |  |  | 2067120 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
916 | Drilling,Equiping & commissioning of Ithangarari Borehole | Drilling,Equiping & commissioning of Ithangarari Borehole | To improve community infrastructure | No. done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-07-01 |  |  | 2024-07-01 | 4956070 | 4956070 |  | MCG |  |  |  | 4956070 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
917 | Emergency Intervention at the Kigoro clogged Twin Crossculvert | Emergency Intervention at the Kigoro clogged Twin Crossculvert | To improve community infrastructure | No. done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 209960 | 209960 |  | MCG |  |  |  | 209960 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
918 | Emergency works undertaken to clear soil and other Debris Material after 2 Landslides in Gathinja | Emergency works undertaken to clear soil and other Debris Material after 2 Landslides in Gathinja | To improve accessibilty | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-24 |  |  | 2024-06-24 | 561440 | 561440 |  | MCG |  |  |  | 561440 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
919 | Grading & gravelling works of Kitune Access Road | Grading & gravelling works of Kitune Access Road | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KAMBITI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-19 |  |  | 2024-06-19 | 2716720 | 2716720 |  | MCG |  |  |  | 2716720 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
920 | Grading & gravelling works of Gaaci-Kagenyo & Itara Thagama Access Road | Grading & gravelling works of Gaaci-Kagenyo & Itara Thagama Access Road | To improve accessibilty | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 3168250 | 3168250 |  | MCG |  |  |  | 3168250 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
921 | Construction of Mutithi-Kinoo Waterpan | Construction of Mutithi-Kinoo Waterpan | To improve community infrastructure | No. done |  |  | MARAGUA | MAKUYU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 889720 | 889720 |  | MCG |  |  |  | 889720 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
922 | Grading & gravelling works of Kiabene-Kiawathangati-Githigi-Kiunyu & Startway-Wanjohi & Nduru Main Road Access Road | Grading & gravelling works of Kiabene-Kiawathangati-Githigi-Kiunyu & Startway-Wanjohi & Nduru Main Road Access Road | To improve accessibilty | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 3518164 | 3518164 |  | MCG |  |  |  | 3518164 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
923 | Grading & gravelling works of Wanyoro-Marumi-Mathingira & Karia-ini Access Road | Grading & gravelling works of Wanyoro-Marumi-Mathingira & Karia-ini Access Road | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KIGUMO |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-28 |  |  | 2024-06-28 | 4750780 | 4750780 |  | MCG |  |  |  | 4750780 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
924 | Supply of Pipes & Fittings for Kinoo/Muthini Water Project | Supply of Pipes & Fittings for Kinoo/Muthini Water Project | To improve accessibilty and connectivity | No. of KMs done |  |  | MARAGUA | MAKUYU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [5 empty] | 4564194 | 4564194 |  | MCG |  |  |  | 4564194 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
925 | Pipe supply for Wathia-ini-Manyatta-Rwangunu-Kangita Water Project | Pipe supply for Wathia-ini-Manyatta-Rwangunu-Kangita Water Project | To improve accessibilty and connectivity | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport | [5 empty] | 2468480 | 2468480 |  | MCG |  |  |  | 2468480 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
926 | Construction of Waiting bays at MauMau,NdunyuChege,Kiarutara & Whitegate | Construction of Waiting bays at MauMau,NdunyuChege,Kiarutara & Whitegate | To improve community infrastructure | No. done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-07-02 |  |  | 2024-07-02 | 899080 | 899080 |  | MCG |  |  |  | 899080 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
927 | Emergency works carried out at Karie dumpsite-Murang'a County | Emergency works carried out at Karie dumpsite-Murang'a County | To improve accessibilty | No. of KMs done | [5 empty] | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-09-22 |  |  | 2024-09-22 | 252000 | 252000 |  | MCG |  |  |  | 252000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
928 | Grading and road opening works caried out in Murang'a North region as an emergency intervention-Murang'a County | Grading and road opening works caried out in Murang'a North region as an emergency intervention-Murang'a County | To improve accessibilty | No. of KMs done | [5 empty] | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-09-03 |  |  | 2024-09-03 | 2164000 | 2164000 |  | MCG |  |  |  | 2164000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
929 | Grading & gravelling of Muhuga-stage Access road | Grading & gravelling of Muhuga-stage Access road | To improve accessibilty | No. of KMs done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-09-18 |  |  | 2024-09-18 | 2214672 | 2214672 |  | MCG |  |  |  | 2214672 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
930 | Murang'a County Headquarters Building Renovation,Cabro works,Frontage Perimeter wall,Gate & Sentry | Murang'a County Headquarters Building Renovation,Cabro works,Frontage Perimeter wall,Gate & Sentry | To upgrade and construct housing which is safe and secure | No. done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-04-22 |  |  | 2024-04-22 | 14419960 | 14419960 |  | MCG |  |  |  | 14419960 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
931 | Construction of a Septic Tank for 200 Persons at Kandara Hospital-Murang'a county | Construction of a Septic Tank for 200 Persons at Kandara Hospital-Murang'a county | To improve community infrastructure | No. done |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-04-30 |  |  | 2024-04-30 | 1760270 | 1760270 |  | MCG |  |  |  | 1760270 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
932 | Maintenance of Streetlights and Floodlights within Murang'a County | Maintenance of Streetlights and Floodlights within Murang'a County | To ensure all shopping centers,markets and major town are lighted | No. of KMs done | [5 empty] | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-09-23 |  |  | 2024-09-23 | 1320750 | 1320750 |  | MCG |  |  |  | 1320750 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
933 | Maintenance of Streetlights and Floodlights within Murang'a County | Maintenance of Streetlights and Floodlights within Murang'a County | To ensure all shopping centers,markets and major town are lighted | No. of KMs done | [5 empty] | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-07-19 |  |  | 2024-07-19 | 1320750 | 1320750 |  | MCG |  |  |  | 1320750 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
934 | upgrading to bitumen standard of Kenol access road - Maragwa subcounty, upgrading to bitumen standard of mukuyu access road - kiharu subcounty and upgrading to bitumen standard of muthithi shopping centre access road - Kigumo subcounty | upgrading to bitumen standard of Kenol access road - Maragwa subcounty, upgrading to bitumen standard of mukuyu access road - kiharu subcounty and upgrading to bitumen standard of muthithi shopping centre access road - Kigumo subcounty | To improve accessibilty | No. of KMs done |  |  | KIGUMO |  |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-12-16 |  |  | 2024-12-16 | 62527700 | 62527700 |  | MCG |  |  |  | 62527700 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
935 | upgrading to bitumen standard of ciumbu market access road - maragwa subcounty, upgrading to bitumen standard of Gacharage market loop access road - Kandara subcounty, upgrading to bitumen standard of kaguku market - mentor sacco loop access road - Ithanga subcounty, Upgrading to bitumen standard of kamune shopping centre/Market access road - Mathioya subcounty | upgrading to bitumen standard of ciumbu market access road - maragwa subcounty, upgrading to bitumen standard of Gacharage market loop access road - Kandara subcounty, upgrading to bitumen standard of kaguku market - mentor sacco loop access road - Ithanga subcounty, Upgrading to bitumen standard of kamune shopping centre/Market access road - Mathioya subcounty | To improve accessibilty | No. of KMs done |  |  | MATHIOYA |  |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-02-07 |  |  | 2024-02-07 | 70747560 | 70747560 |  | MCG |  |  |  | 70747560 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
936 | Upgrading to bitumen standard of JCT Forthall Zabka Kabati - County Aggregated Industrial Park loop access road | Upgrading to bitumen standard of JCT Forthall Zabka Kabati - County Aggregated Industrial Park loop access road | To improve accessibilty | No. of KMs done |  |  | MARAGUA |  |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-02-07 |  |  | 2024-02-07 | 56858560 | 56858560 |  | MCG |  |  |  | 56858560 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
937 | Upgrading to bitumen standard of Kanyenyaini market access road | Upgrading to bitumen standard of Kanyenyaini market access road | To improve accessibilty | No. of KMs done |  |  | KANGEMA |  |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  | 2024-06-18 |  |  | 2024-06-18 | 11176800 | 11176800 |  | MCG |  |  |  | 11176800 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
939 | Construction of kagira ECDE classrooms – gaichanjiru ward | Proposed construction of classrooms | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2774450 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
940 | Construction of mugumoini e.c.d.e classrooms – gaichanjiru ward | Proposed construction of mugumoini e.c.d.e classrooms – gaichanjiru ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2700980 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
941 | Grading & gravelling works of kariua police post road - gaichanjiru ward | Proposed grading & gravelling works of kariua police post road - gaichanjiru ward | improve infrustructure | improved infrustructure |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1954948 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
942 | Renovation of thare primary & gathuthu ECDE classrooms - gatanga ward | Proposed renovation of thare primary & gathuthu e.c.d.e classrooms - gatanga ward | Provide learners with conducive learning environment | improved infrustructure |  |  | GATANGA | GATANGA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2302100 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
943 | Renovation of umbui ECDE classrooms and construction of toilet block – gatanga ward | Proposed renovation of umbui e.c.d.e classrooms and construction of toilet block – gatanga ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | GATANGA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1806050 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
944 | Construction of kinyongi ECDE classroom & renovation of gituri primary ECDE classroom – gaturi ward | Proposed construction of kinyongi e.c.d.e classroom & renovation of gituri primary e.c.d.e classroom – gaturi ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2122644 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
945 | renovation of kibuu & gaitheri primary ECDE classrooms – gaturi ward | Proposed renovation of kibuu & gaitheri primary e.c.d.e classrooms – gaturi ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2414890 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
946 | construction of rutune primary ECDE & renovation of kimathi primaryECDE – gaturi ward | Proposed construction of rutune primary e.c.d.e & renovation of kimathi primary e.c.d.e – gaturi ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | GATURI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2432870 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
947 | renovation of gitugi primary ECDE classrooms – gitugi ward | Proposed renovation of gitugi primary e.c.d.e classrooms – gitugi ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1820260 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
948 | renovation of kanjahi & kanooro primary e.c.d.e clasrooms – gitugi ward | Proposed renovation of kanjahi & kanooro primary e.c.d.e clasrooms – gitugi ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2489710 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
949 | renovation of mungu-ini, kanyai & kiriti e.c.d.e classrooms – ichagaki ward | Proposed renovation of mungu-ini, kanyai & kiriti e.c.d.e classrooms – ichagaki ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2308795 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
950 | construction of kyaume e.c.d.e classroom – ithanga ward | Proposed construction of kyaume e.c.d.e classroom – ithanga ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | ITHANGA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1167459 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
951 | construction of kamaro e.c.d.e classroom – ithiru ward | Proposed construction of kamaro e.c.d.e classroom – ithiru ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2409450 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
952 | construction& renovation of matiraini primary e.c.d.e classrooms – ithiru ward | Proposed construction& renovation of matiraini primary e.c.d.e classrooms – ithiru ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1946915 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
953 | construction of githuya primary e.c.d.e classroom – ithiru ward | Proposed construction of githuya primary e.c.d.e classroom – ithiru ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1388827 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
954 | construction & renovation of riandegwa primary e.c.d.e classrooms – kagundu-ini ward | Proposed construction & renovation of riandegwa primary e.c.d.e classrooms – kagundu-ini ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1901458 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
955 | renovation of kagundu primary & mairungi primary e.c.d.e classrooms – kagundu-ini ward | Proposed renovation of kagundu primary & mairungi primary e.c.d.e classrooms – kagundu-ini ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2303106 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
956 | construction of dr. Irungu kang’ata e.c.d.e & toilet block – kahumbu ward | Proposed construction of dr. Irungu kang’ata e.c.d.e & toilet block – kahumbu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1726630 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
957 | construction of mumbu primary e.c.d.e classroom & toilet block – kahumbu ward | Proposed construction of mumbu primary e.c.d.e classroom & toilet block – kahumbu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1735395 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
958 | construction of mwanawikio b, (gatuikira) e.c.d.e classrooms – kakuzi/mitumbiri ward | Proposed construction of mwanawikio b, (gatuikira) e.c.d.e classrooms – kakuzi/mitumbiri ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KAKUZI/MITUMBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2596020 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
959 | renovation works of kamune, wahundura & kirungu primary school e.c.d.e classrooms – kamacharia ward | Proposed renovation works of kamune, wahundura & kirungu primary school e.c.d.e classrooms – kamacharia ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | KAMACHARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3728280 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
960 | construction of ndorome primary e.c.d.e classroom – kamahuha ward | Proposed construction of ndorome primary e.c.d.e classroom – kamahuha ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KAMAHUHA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1377637 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
961 | renovation of kahaini primary e.c.d.e – kamahuha ward | Proposed renovation of kahaini primary e.c.d.e – kamahuha ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KAMAHUHA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1171600 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
962 | construction of kaharati primary e.c.d.e classroom – kamahuha ward | Proposed construction of kaharati primary e.c.d.e classroom – kamahuha ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KAMAHUHA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1377637 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
963 | construction of mihangó, kitune and matanya e.c.d.e – kambiti ward | Proposed construction of mihangó, kitune and matanya e.c.d.e – kambiti ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KAMBITI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 4614510 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
964 | construction of kangari town e.c.d.e classrooms and ablution block – kangari ward | Proposed construction of kangari town e.c.d.e classrooms and ablution block – kangari ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KANGARI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3473116 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
965 | construction of kimotho primary e.c.d.e classroom and ablution block – kangari ward | Proposed construction of kimotho primary e.c.d.e classroom and ablution block – kangari ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KANGARI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2214958 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
966 | construction of mariira farm e.c.d.e clasroom and ablution block – kangari ward | Proposed construction of mariira farm e.c.d.e clasroom and ablution block – kangari ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KANGARI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2053958 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
967 | construction of nduini e.c.d.e classrooms – kanyenya-ini ward | Proposed construction of nduini e.c.d.e classrooms – kanyenya-ini ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | KANYENYAINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2737400 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
968 | construction of wanyaga primary school e.c.d.e classroom – kariara ward | Proposed construction of wanyaga primary school e.c.d.e classroom – kariara ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KARIARA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1400130 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
969 | renovation works of gatakaini primary school e.c.d.e classrooms – kariara ward | Proposed renovation works of gatakaini primary school e.c.d.e classrooms – kariara ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KARIARA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1808020 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
970 | renovation works of karega primary, marumi primary & kaimiri primary e.c.d.e classrooms – kigumo ward | Proposed renovation works of karega primary, marumi primary & kaimiri primary e.c.d.e classrooms – kigumo ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KIGUMO |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2215740 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
971 | grading & gravelling of gicici- kianjogu, cugu - kariga; kagogo-nyaga road– kihumbuini ward | Proposed grading & gravelling of gicici- kianjogu, cugu - kariga; kagogo-nyaga road– kihumbuini ward | improve Accessibility | No. of KMs done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3753470 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
972 | renovation of kiunyu a, kigetho, njaini kahetho e.c.d.e classrooms – kihumbu-ini ward | proposed renovation of kiunyu a, kigetho, njaini kahetho e.c.d.e classrooms – kihumbu-ini ward | improve Accessibility | No. of KMs done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 4295200 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
973 | grading & gravelling works of kagaa access road - kimorori wempa ward | Proposed grading & gravelling works of kagaa access road - kimorori wempa ward | improve Accessibility | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2056777 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
974 | construction of githanji primary e.c.d.e classroom & renovation of karungangi primary e.c.d.e – kimorori/wempa ward | Proposed construction of githanji primary e.c.d.e classroom & renovation of karungangi primary e.c.d.e – kimorori/wempa ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2035800 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
975 | renovation works of senior chief gichohi primary, gangururu primary e.c.d.e classroms – kimorori/wempa ward | Proposed renovation works of senior chief gichohi primary, gangururu primary e.c.d.e classroms – kimorori/wempa ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1959450 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
976 | construction of karugu e.c.d.e classroom and toilet block & renovation of p.k e.c.d.e classroom – kimorori/wempa ward | Proposed construction of karugu e.c.d.e classroom and toilet block & renovation of p.k e.c.d.e classroom – kimorori/wempa ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2623280 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
977 | construction of kinyona primary e.c.d.e classroom – kinyona ward | Proposed construction of kinyona primary e.c.d.e classroom – kinyona ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1897581 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
978 | opening of access roads - kinyona ward | Proposed opening of access roads - kinyona ward | improve Accessibility | No. of KMs done |  |  | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1640240 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
979 | renovation works of rarakwa primary and gachocho primary e.c.d.e classrooms – kinyona ward | Proposed renovation works of rarakwa primary and gachocho primary e.c.d.e classrooms – kinyona ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1416619 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
980 | renovaion of kiriaini primary, kiruru & kora primary e.c.d.e classrooms – kiru ward | Proposed renovaion of kiriaini primary, kiruru & kora primary e.c.d.e classrooms – kiru ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2557120 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
981 | renovation of kairo & kagio-ini e.c.d.e classrooms – kiru ward | Proposed renovation of kairo & kagio-ini e.c.d.e classrooms – kiru ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2266280 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
982 | construction & renovation of kiangima e.c.d.e classrooms – kiru ward | Proposed construction & renovation of kiangima e.c.d.e classrooms – kiru ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2088790 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
983 | construction of kanyururuku e.c.d.e classroom – makuyu ward | Proposed construction of kanyururuku e.c.d.e classroom – makuyu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | MAKUYU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1667820 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
984 | construction of kaseve e.c.d.e classroom and ablution block – makuyu ward | Proposed construction of kaseve e.c.d.e classroom and ablution block – makuyu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | MAKUYU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3081330 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
985 | renovation of maji mazuri e.c.d.e classroom and construction of ablution block – makuyu ward | Proposed renovation of maji mazuri e.c.d.e classroom and construction of ablution block – makuyu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | MAKUYU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2255650 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
986 | renovation of muchungucha & kiangochi primary e.c.d.e classrooms – mbiri ward | Proposed renovation of muchungucha & kiangochi primary e.c.d.e classrooms – mbiri ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1382570 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
987 | construction of rurii e.c.d.e classroom & renovation of githuguya primary e.c.d.e classrooms – mbiri ward | Proposed construction of rurii e.c.d.e classroom & renovation of githuguya primary e.c.d.e classrooms – mbiri ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2086170 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
988 | renovation works of st. Charles lwanga primary, yamugwe primary e.c.d.e classrooms- mugoiri ward | Proposed renovation works of st. Charles lwanga primary, yamugwe primary e.c.d.e classrooms- mugoiri ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2252740 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
989 | renovation works of kiyu primary, gitiri & gatudu primary e.c.d.e classrooms – mugoiri ward | Proposed renovation works of kiyu primary, gitiri & gatudu primary e.c.d.e classrooms – mugoiri ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3442440 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
990 | construction of irewa e.c.d.e classroom – mugoiri ward | Proposed construction of irewa e.c.d.e classroom – mugoiri ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1291520 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
991 | construction of ngate e.c.d.e classroom – mugumoini ward | Proposed construction of ngate e.c.d.e classroom – mugumoini ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | MUGUMOINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1346060 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
992 | renovation works of mugumoini and ithangarare primary school e.c.d.e classrooms – mugumoini ward | Proposed renovation works of mugumoini and ithangarare primary school e.c.d.e classrooms – mugumoini ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | MUGUMOINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1767850 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
993 | construction of giatutu e.c.d.e classroom – mugumoni ward | Proposed construction of giatutu e.c.d.e classroom – mugumoni ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | MUGUMOINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1298010 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
994 | renovation of gatundu-ini primary, gichui primary & karuri primary e.c.d.e classrooms– muguru ward | Proposed renovation of gatundu-ini primary, gichui primary & karuri primary e.c.d.e classrooms– muguru ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1207600 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
995 | renovation works of kahuhu primary, watuha primary & iyego primary e.c.d.e classsrooms – muguru ward | Proposed renovation works of kahuhu primary, watuha primary & iyego primary e.c.d.e classsrooms – muguru ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2396364 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
996 | grading & gravelling works of muhuga-stage road & muringaini watuha road –muguru ward | Proposed grading & gravelling works of muhuga-stage road & muringaini watuha road –muguru ward | improve infrustructure | improved infrustructure |  |  | KANGEMA | MUGURU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1487700 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
997 | renovation of kahatia primary e.c.d.e classrooms & construction of toilet block at karuri-ini primary e.c.d.e – murarandia ward | Proposed renovation of kahatia primary e.c.d.e classrooms & construction of toilet block at karuri-ini primary e.c.d.e | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2039590 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
998 | renovation of kahithe primary & gatara primary e.c.d.e classrooms – murarandia ward | Proposed renovation of kahithe primary & gatara primary e.c.d.e classrooms – murarandia ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2212430 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
999 | renovation of kiranga primary, karumu primary & gatitu primary e.c.d.e – muruka ward | Proposed renovation of kiranga primary, karumu primary & gatitu primary e.c.d.e – muruka ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 4576115 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1000 | construction & renovation of makindi primary e.c.d.e classrooms – muruka ward | Proposed construction & renovation of makindi primary e.c.d.e classrooms – muruka ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2210895 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1001 | completin of ngaburi e.c.d.e classroom and construction of an ablution block and refurbishment works at gachathaini e.c.d.e centre – muthithi ward | completin of ngaburi e.c.d.e classroom and construction of an ablution block and refurbishment works at gachathaini e.c.d.e centre | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | MUTHITHI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2100520 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1002 | renovation works of irigiro primary e.c.d.e classrooms – muthithi ward | Proposed renovation works of irigiro primary e.c.d.e classrooms – muthithi ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | MUTHITHI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1160160 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1003 | construction of waitwa primary school e.c.d.e classroom – ng’araria ward | Proposed construction of waitwa primary school e.c.d.e classroom – ng’araria ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1298010 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1004 | refurbishment of muiri-ini & kifuu e.c.d.e classrooms & construction of ablution block – ng’araria ward | Proposed refurbishment of muiri-ini & kifuu e.c.d.e classrooms & construction of ablution block – ng’araria ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2460370 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1005 | renovation of ng’araria e.c.d.e classrooms – ng’araria ward | Proposed renovation of ng’araria e.c.d.e classrooms – ng’araria ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1581370 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1006 | renovation works of gitumbi, ihigaini & kiamwone e.c.d.e classrooms – nginda ward | Proposed renovation works of gitumbi, ihigaini & kiamwone e.c.d.e classrooms – nginda ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | NGINDA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2282880 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1007 | construction of kiangoma e.c.d.e classroom – nginda ward | Proposed construction of kiangoma e.c.d.e classroom – nginda ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | MARAGUA | NGINDA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1173510 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1008 | Prposed constyruction of wahu primary school e.c.d.e classrooms – ruchu ward | Prposed construction of wahu primary school e.c.d.e classrooms – ruchu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | RUCHU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1386725 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1009 | renovation works of gitiru, kiangari & kahiga primary school e.c.d.e classrooms – ruchu ward | Proposed renovation works of gitiru, kiangari & kahiga primary school e.c.d.e classrooms – ruchu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | RUCHU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2525980 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1010 | renovation works of mutheru & mukuria primary e.c.d.e classrooms – ruchu ward | Proposed renovation works of mutheru & mukuria primary e.c.d.e classrooms – ruchu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | RUCHU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2589750 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1011 | construction of matara e.c.d.e classrooms and toilet block – rwathia ward | Proposed construction of matara e.c.d.e classrooms and toilet block – rwathia ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3746566 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1012 | construction of karima e.c.d.e classrooms and toilet block – rwathia ward | Proposed construction of karima e.c.d.e classrooms and toilet block – rwathia ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3089505 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1013 | renovation works of wanjerere primary e.c.d.e classrooms – rwathia ward | Proposed renovation works of wanjerere primary e.c.d.e classrooms – rwathia ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANGEMA | RWATHIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1160705 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1014 | construction of vidhu ramji primary e.c.d.e classroom & renovation of mbiri primary e.c.d.e classroom – township ward | Proposed construction of vidhu ramji primary e.c.d.e classroom & renovation of mbiri primary e.c.d.e classroom – township ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2033750 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1015 | Proposd construction of wanjengi primary e.c.d.e classroom & renovation of gitweku primary e.c.d.e classrooms – wangu ward | Proposd construction of wanjengi primary e.c.d.e classroom & renovation of gitweku primary e.c.d.e classrooms – wangu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | WANGU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2390540 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1016 | renovation of gathinja, gitui & gitige primary e.c.d.e classrooms – wangu ward | Proposed renovation of gathinja, gitui & gitige primary e.c.d.e classrooms – wangu ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | WANGU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3211080 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1017 | rehabilitation works to convert the existing structure to fire offices - phase 11 | Proposed rehabilitation works to convert the existing structure to fire offices - phase 11 | improve infrustructure | improved infrustructure |  |  | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 4353335 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1018 | construction of maternity ward at wahundura dispensary - kamacharia ward | Proposed construction of maternity ward at wahundura dispensary - kamacharia ward | improve infrustructure | improved infrustructure |  |  | MATHIOYA | KAMACHARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 4036162 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1019 | tiling and renovation works to githagara health center – mugoiri ward | Proposed tiling and renovation works to githagara health center | improve infrustructure | improved infrustructure |  |  | KIHARU | MUGOIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 988473 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1020 | completion of gathaithi social hall, construction of matharite weighing shed, and construction of a toilet block at murarandia health center – murarandia ward | Proposed completion of gathaithi social hall, construction of matharite weighing shed, and construction of a toilet block at murarandia health center | improve infrustructure | improved infrustructure |  |  | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2301860 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1021 | construction of kiangage dispensary – township ward | Proposed construction of kiangage dispensary – township ward | improve infrustructure | improved infrustructure |  |  | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2675785 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1022 | grading & gravellling works of kamuchii-manjuu sec. Access road - gaichanjiru ward | Proposed grading & gravellling works of kamuchii-manjuu sec. Access road | improve Accessibility | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3955600 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1023 | grading & gravelling works of kihitini -gitugi - kambara access road - gitugi ward | Proposed grading & gravelling works of kihitini -gitugi - kambara access road | improve Accessibility | No. of KMs done |  |  | MATHIOYA | GITUGI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3745060 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1024 | grading & gravelling works+d17:d123 of nyerere-kifiriri; kiamakumi-ikuyu roads – ichagaki ward | Proposed grading & gravelling works+d17:d123 of nyerere-kifiriri; kiamakumi-ikuyu roads | improve Accessibility | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3028479 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1025 | grading & gravelling works of kieni - mahinga - kagongo -unjiru-ini access road – ithiru ward | Proposed grading & gravelling works of kieni - mahinga - kagongo -unjiru-ini access road | improve Accessibility | No. of KMs done |  |  | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 7082960 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1026 | grading & gravellling works of of kwa menja -gichagi access road - kagundu-ini ward | Proposed grading & gravellling works of of kwa menja -gichagi access road | improve Accessibility | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3741000 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1027 | grading & gravelling works of jct kihua-ini - riandegwa primary school access road - kagundu-ini ward | Proposed grading & gravelling works of jct kihua-ini - riandegwa primary school access road | improve Accessibility | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2958000 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1028 | grading & gravelling works of githunguri sec. Sch.-githunguri subchief camp road – kagunduini ward | Proposed grading & gravelling works of githunguri sec. Sch.-githunguri subchief camp road | improve Accessibility | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3214824 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1029 | improvement of githembe ap post jct - njora bridge jct access road - kahumbu ward | Proposed improvement of githembe ap post jct - njora bridge jct access road | improve Accessibility | No. of KMs done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1179025 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1030 | grading & gravelling works of rurii-thaara catholic church road, siranga-mutharata-nyati pry.sch road – kamahuha ward | Proposed grading & gravelling works of rurii-thaara catholic church road, siranga-mutharata-nyati pry.sch road | improve Accessibility | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 4073920 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1031 | construction of karega primary e.c.d.e classroom, and renovation of karega dispensary, construction of kimandi foot bridge & construction of gathwariga culverts and gakaringo culverts – kariara ward | Proposed construction of karega primary e.c.d.e classroom, and renovation of karega dispensary, construction of kimandi foot bridge & construction of gathwariga culverts and gakaringo culverts | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KARIARA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3043315 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1032 | grading & gravelling works of pst. Pius muiru road & kigumo-iriguini road – kigumo ward | Proposed grading & gravelling works of pst. Pius muiru road & kigumo-iriguini road – kigumo ward | improve Accessibility | No. of KMs done |  |  | KIGUMO | KIGUMO |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 5669848 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1033 | grading & gravelling works of ndira – gichiru access road – kihumbu-ini ward | Proposed grading & gravelling works of ndira – gichiru access road – kihumbu-ini ward | improve Accessibility | No. of KMs done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3652840 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1034 | construction of zabuka-githanji culverts, bahati-ngemu culverts, gikono- mangoto footbridge & reli kwa thiongo gabions – kimorori ward | Proposed construction of zabuka-githanji culverts, bahati-ngemu culverts, gikono- mangoto footbridge & reli kwa thiongo gabions | improve Accessibility | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1065500 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1035 | grading & gravelling works of ndugamano - karaba access road. – kinyona ward | Proposed grading & gravelling works of ndugamano - karaba access road. – kinyona ward | improve Accessibility | No. of KMs done |  |  | KIGUMO | KINYONA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3426640 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1036 | grading & gravellling works of gatati -gichocho access road -kiru ward | Proposed grading & gravellling works of gatati -gichocho access road -kiru ward | improve Accessibility | No. of KMs done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1809600 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1037 | grading & gravellling works of nyakiunju -thuruthuru - kora access road – kiru ward | Proposed grading & gravellling works of nyakiunju -thuruthuru - kora access road – kiru ward | improve Accessibility | No. of KMs done |  |  | MATHIOYA | KIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3875560 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1038 | supply & installation of culvert – makuyu ward | Proposed supply & installation of culvert – makuyu ward | improve infrustructure |  |  |  | MARAGUA | MAKUYU |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 904800 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1039 | grading & gravelling works of gachuhi - bohano - gikandu pry & gaitega pry access roads - mbiri ward | Proposed grading & gravelling works of gachuhi - bohano - gikandu pry & gaitega pry access roads - mbiri ward | improve Accessibility | No. of KMs done |  |  | KIHARU | MBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3556560 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1040 | grading & gravelling works of kahuho - kyaume access road. Kakuzi/mitumbiri ward | Proposed grading & gravelling works of kahuho - kyaume access road. Kakuzi/mitumbiri ward | improve Accessibility | No. of KMs done |  |  | MARAGUA | KAKUZI/MITUMBIRI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2904640 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1041 | cabro works at gatunyu market – mugumoini ward | Proposed cabro works at gatunyu market – mugumoini ward | improve infrustructure |  |  |  | GATANGA | MUGUMOINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3549280 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1042 | grading & gravelling works of kairichi-gichu; githambo tea factory roads – murarandia ward | Proposed grading & gravelling works of kairichi-gichu; githambo tea factory roads – murarandia ward | improve Accessibility | No. of KMs done |  |  | KIHARU | MURARANDIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 1472620 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1043 | grading & gravelling works of makuti-kiruthi-gataiyu road - muruka ward | Proposed grading & gravelling works of makuti-kiruthi-gataiyu road - muruka ward | improve Accessibility | No. of KMs done |  |  | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 5501184 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1044 | grading & gravelling works of kiranga slaughter house -ngirima jct - a.c.k kiranga -mbuko jct access -muruka ward | Proposed grading & gravelling works of kiranga slaughter house -ngirima jct - a.c.k kiranga -mbuko jct access -muruka ward | improve Accessibility | No. of KMs done |  |  | KANDARA | MURUKA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 4245600 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1045 | grading & gravelling works of njora, gathanji a, ka-mukuru kagurumo -gichichi – kiangari-ini, irigiro machengo access roads – muthithi ward | Proposed grading & gravelling works of njora, gathanji a, ka-mukuru kagurumo -gichichi – kiangari-ini, irigiro machengo access roads – muthithi ward | improve Accessibility | No. of KMs done |  |  | KIGUMO | MUTHITHI |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 4138880 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1046 | grading & gravelling works of kiamuhu-kianjereri access road - ng’araria ward | Proposed grading & gravelling works of kiamuhu-kianjereri access road - ng’araria ward | improve Accessibility | No. of KMs done |  |  | KANDARA | NGARARIA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2324176 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1047 | grading & gravelling works of kirundu road, kiendwa road & kigoru road - nginda ward | Proposed grading & gravelling works of kirundu road, kiendwa road & kigoru road - nginda ward | improve Accessibility | No. of KMs done |  |  | MARAGUA | NGINDA |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 4617844 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1048 | grading & gravelling of st mary -firoze -kamunandaini - karichiungu access road. – township ward | Proposed grading & gravelling of st mary -firoze -kamunandaini - karichiungu access road. – township ward | improve Accessibility | No. of KMs done |  |  | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 3223176 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1049 | renovation of kandundu & kiangage e.c.d.e classrooms – township ward | Proposed renovation of kandundu & kiangage e.c.d.e classrooms – township ward | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport | [5 empty] | 2774450 | 2774450 |  | MCG |  |  |  | 2774450 | 100% | 2361820 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO
1050 | CLASSROOM CONSTRUCTION AT ST.MARY PRIMARY | CLASSROOM CONSTRUCTION AT ST.MARY PRIMARY | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIHARU | TOWNSHIP |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1812331 | 1812331 |  | MCG |  |  |  | 1812331 | 100% | 1812331 | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1051 | KAGONO ECDE TOILET CONSTRUCTION | KAGONO ECDE TOILET CONSTRUCTION | Provide learners with conducive learning environment | No. of classrooms done |  |  | KANDARA | ITHIRU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 500000 | 500000 |  | MCG |  |  |  | 500000 | 100% | 500000 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1052 | REPAIRS OF MWEMA ECDE CLASSROOMMS | REPAIRS OF MWEMA ECDE CLASSROOMMS | Provide learners with conducive learning environment | No. of classrooms done |  |  | KIGUMO | KAHUMBU |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 300000 | 300000 |  | MCG |  |  |  | 300000 | 100% | 300000 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1053 | NGANGAINI ECDE REPAIRS | NGANGAINI ECDE REPAIRS | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | MUGUMOINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 500000 | 500000 |  | MCG |  |  |  | 500000 | 100% | 500000 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1054 | TOILET CONSTRUCTION-WATUKU ECDE | TOILET CONSTRUCTION-WATUKU ECDE | Provide learners with conducive learning environment | No. of classrooms done |  |  | GATANGA | KIHUMBUINI |  | EDUCATION | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 300000 | 300000 |  | MCG |  |  |  | 300000 | 100% | 300000 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1055 | GRADING AND GRAVELLING OF ACCESS ROADS NGINDA | GRADING AND GRAVELLING OF ACCESS ROADS NGINDA | To improve accessibilty | No. of KMs done |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2800367 | 2800367 |  | MCG |  |  |  | 2800367 | 100% | 2800367 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1056 | GRADING AND GRAVELLING OF ACCESS ROADS JCT MUKURIA RUCHU WARD | GRADING AND GRAVELLING OF ACCESS ROADS JCT MUKURIA RUCHU WARD | To improve accessibilty | No. of KMs done |  |  | KANDARA | RUCHU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2020530 | 2020530 |  | MCG |  |  |  | 2020530 | 100% | 2020530 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1057 | LAYING OF CABROS AND DRAINAGE CHANNELS KANGARI WARD | LAYING OF CABROS AND DRAINAGE CHANNELS KANGARI WARD | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KANGARI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1909493 | 1909493 |  | MCG |  |  |  | 1909493 | 100% | 1909493 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1058 | GRADING AND GRAVELLING OF ACCESS ROADS KIMORORI WEMPA WARD | GRADING AND GRAVELLING OF ACCESS ROADS KIMORORI WEMPA WARD | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2051051 | 2051051 |  | MCG |  |  |  | 2051051 | 100% | 2051051 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1059 | GRADING AND GRAVELLING OF ACCESS ROADS GITUGI WARD | GRADING AND GRAVELLING OF ACCESS ROADS GITUGI WARD | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2057327 | 2057327 |  | MCG |  |  |  | 2057327 | 100% | 2057327 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1060 | GRADING AND GRAVELLING OF ACCESS ROADS MUGUMOINI WARD | GRADING AND GRAVELLING OF ACCESS ROADS MUGUMOINI WARD | To improve accessibilty | No. of KMs done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2308848 | 2308848 |  | MCG |  |  |  | 2308848 | 100% | 2308848 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1061 | GRADING AND GRAVELLING OF ACCESS ROADS TOWNSHIP WARD WARD | GRADING AND GRAVELLING OF ACCESS ROADS TOWNSHIP WARD WARD | To improve accessibilty | No. of KMs done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2392241 | 2392241 |  | MCG |  |  |  | 2392241 | 100% | 2392241 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1062 | GRADING AND GRAVELLING OF ACCESS ROADS KAIRICHI MURARANDIA WARD | GRADING AND GRAVELLING OF ACCESS ROADS KAIRICHI MURARANDIA WARD | To improve accessibilty | No. of KMs done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2800000 | 2800000 |  | MCG |  |  |  | 2800000 | 100% | 2800000 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1063 | GRADING AND GRAVELLING OF ACCESS ROADS GATUYA KIGUMO WARD | GRADING AND GRAVELLING OF ACCESS ROADS GATUYA KIGUMO WARD | To improve accessibilty | No. of KMs done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3446329 | 3446329 |  | MCG |  |  |  | 3446329 | 100% | 3446329 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1064 | GRADING OF ACCESS ROAD KIAMUINGI GITHIRU | GRADING OF ACCESS ROAD KIAMUINGI GITHIRU | To improve accessibilty | No. of KMs done |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3518372 | 3518372 |  | MCG |  |  |  | 3518372 | 100% | 3518372 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1065 | GRADING OF ACCESS ROADS GITUYA GAICHANJIRU WARD | GRADING OF ACCESS ROADS GITUYA GAICHANJIRU WARD | To improve accessibilty | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3535687 | 3535687 |  | MCG |  |  |  | 3535687 | 100% | 3535687 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1066 | GRADING AND GRAVELLING OF ACCESS ROADS ACK NGUTU GACHIRI GITUGI WARD | GRADING AND GRAVELLING OF ACCESS ROADS ACK NGUTU GACHIRI GITUGI WARD | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | GITUGI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3570110.4 | 3570110.4 |  | MCG |  |  |  | 3570110.4 | 100% | 3570110.4 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1067 | GRADING WORKS OF ACCESS ROADS JCT SANTAMORE WEMPA | GRADING WORKS OF ACCESS ROADS JCT SANTAMORE WEMPA | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3619530 | 3619530 |  | MCG |  |  |  | 3619530 | 100% | 3619530 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1068 | GRADING OF ACCESS ROAD MBIRI WARD | GRADING OF ACCESS ROAD MBIRI WARD | To improve accessibilty | No. of KMs done |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3622152 | 3622152 |  | MCG |  |  |  | 3622152 | 100% | 3622152 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1069 | GRADING WORKS OF ACCESS ROADS METHI WEMPA | GRADING WORKS OF ACCESS ROADS METHI WEMPA | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3680316 | 3680316 |  | MCG |  |  |  | 3680316 | 100% | 3680316 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1070 | EXCAVATION OF ACCESS ROADS GATURI WARD | EXCAVATION OF ACCESS ROADS GATURI WARD | To improve accessibilty | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1592293 | 1592293 |  | MCG |  |  |  | 1592293 | 100% | 1592293 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1071 | SPOT IMPROVEMENT WORKS OF SMALL EARTH ACCESS ROAD | SPOT IMPROVEMENT WORKS OF SMALL EARTH ACCESS ROAD | To improve accessibilty | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 |  |  |  | MCG | [6 empty] | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1072 | GRADING AND GRAVELLING OF ACCESS ROAD NGARARIA WARD | GRADING AND GRAVELLING OF ACCESS ROAD NGARARIA WARD | To improve accessibilty | No. of KMs done |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3047998 | 3047998 |  | MCG |  |  |  | 3047998 | 100% | 3047998 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1073 | GRADING AND GRAVELLING WORKS OF WAKIBUGI-IRATI ACCESS ROAD-KANGARI WARD | GRADING AND GRAVELLING WORKS OF WAKIBUGI-IRATI ACCESS ROAD-KANGARI WARD | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KANGARI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3283808 | 3283808 |  | MCG |  |  |  | 3283808 | 100% | 3283808 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1074 | Grading works Ndirii-ini - Kagira access roads | Grading works Ndirii-ini - Kagira access roads | To improve accessibilty | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3793200 | 3793200 |  | MCG |  |  |  | 3793200 | 100% | 3793200 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1075 | GRADING WORKS MBIRI WARD | GRADING WORKS MBIRI WARD | To improve accessibilty | No. of KMs done |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3601874.5 | 3601874.5 |  | MCG |  |  |  | 3601874.5 | 100% | 3601874.5 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1076 | Grading works of Wanaruona - Tamabaya access road | Grading works of Wanaruona - Tamabaya access road | To improve accessibilty | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1780240 | 1780240 |  | MCG |  |  |  | 1780240 | 100% | 1780240 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1077 | gravelling works of access road in ithiru ward | gravelling works of access road in ithiru ward | To improve accessibilty | No. of KMs done |  |  | KANDARA | ITHIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2854215 | 2854215 |  | MCG |  |  |  | 2854215 | 100% | 2854215 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1078 | grading and gravelling works of mabae accessroad gatanga ward | grading and gravelling works of mabae accessroad gatanga ward | To improve accessibilty | No. of KMs done |  |  | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3458739 | 3458739 |  | MCG |  |  |  | 3458739 | 100% | 3458739 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1079 | GRADING WORKS OF GIKINDU - KINGARA MARIMERA ACCESS ROAD - KAMACHARIA WARD | GRADING WORKS OF GIKINDU - KINGARA MARIMERA ACCESS ROAD - KAMACHARIA WARD | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3711781 | 3711781 |  | MCG |  |  |  | 3711781 | 100% | 3711781 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1080 | INSTALLATION OF KANGEMA STREET LIGHTS | INSTALLATION OF KANGEMA STREET LIGHTS | To ensure all shopping centers,markets and major town are lighted | No. of KMs done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2502060 | 2502060 |  | MCG |  |  |  | 2502060 | 100% | 2502060 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1081 | GRADING AND GRAVELLING WORKS IREMBU ACCESS ROAD | GRADING AND GRAVELLING WORKS IREMBU ACCESS ROAD | To improve accessibilty | No. of KMs done |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2351865 | 2351865 |  | MCG |  |  |  | 2351865 | 100% | 2351865 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1082 | GRADING AND GRAVELLING OF ACCESS ROAD NGARARIA WARD | GRADING AND GRAVELLING OF ACCESS ROAD NGARARIA WARD | To improve accessibilty | No. of KMs done |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2761094 | 2761094 |  | MCG |  |  |  | 2761094 | 100% | 2761094 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1083 | GRADING AND GRAVELLING OF ACCESS ROAD GAICHANJIRU WARD | GRADING AND GRAVELLING OF ACCESS ROAD GAICHANJIRU WARD | To improve accessibilty | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3001189 | 3001189 |  | MCG |  |  |  | 3001189 | 100% | 3001189 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1084 | GRADING AND GRAVELLING WORKS OF ACCESS ROADS KANORERO GATHIMA MUGURU WARD | GRADING AND GRAVELLING WORKS OF ACCESS ROADS KANORERO GATHIMA MUGURU WARD | To improve accessibilty | No. of KMs done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3163082 | 3163082 |  | MCG |  |  |  | 3163082 | 100% | 3163082 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1085 | GRADING AND GRAVELLING WORKS OF KIHUA-INI KAGUNDUINI WARD | GRADING AND GRAVELLING WORKS OF KIHUA-INI KAGUNDUINI WARD | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3277275 | 3277275 |  | MCG |  |  |  | 3277275 | 100% | 3277275 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1086 | GRADING AND GRAVELLING WORKS OF ACCESS ROADS KAMACHARIA WARD | GRADING AND GRAVELLING WORKS OF ACCESS ROADS KAMACHARIA WARD | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3591900 | 3591900 |  | MCG |  |  |  | 3591900 | 100% | 3591900 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1087 | CONSTRUCTION OF GATANGARA CULVERT KANYENYAINI WARD | CONSTRUCTION OF GATANGARA CULVERT KANYENYAINI WARD | To improve accessibilty | No. of KMs done |  |  | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3749391 | 3749391 |  | MCG |  |  |  | 3749391 | 100% | 3749391 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1088 | CULVERTS INSTALLATION WORKS GATURI WARD | CULVERTS INSTALLATION WORKS GATURI WARD | To improve accessibilty | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1127298.5 | 1127298.5 |  | MCG |  |  |  | 1127298.5 | 100% | 1127298.5 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1089 | GRADING OF ACCESS ROADS RWATHIA WARD | GRADING OF ACCESS ROADS RWATHIA WARD | To improve accessibilty | No. of KMs done |  |  | KANGEMA | RWATHIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3282616.3 | 3282616.3 |  | MCG |  |  |  | 3282616.3 | 100% | 3282616.3 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1090 | GRADING AND GRAVELLING OF ACCESS ROAD KANYENYAINI WARD | GRADING AND GRAVELLING OF ACCESS ROAD KANYENYAINI WARD | To improve accessibilty | No. of KMs done |  |  | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1852668 | 1852668 |  | MCG |  |  |  | 1852668 | 100% | 1852668 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1091 | GRADING OF ACCESS ROADS WANGU | GRADING OF ACCESS ROADS WANGU | To improve accessibilty | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3000793 | 3000793 |  | MCG |  |  |  | 3000793 | 100% | 3000793 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1092 | GRADING AND GRAVELLING OF ACCESS ROAD KAGUNDUINI WARD | GRADING AND GRAVELLING OF ACCESS ROAD KAGUNDUINI WARD | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2354282 | 2354282 |  | MCG |  |  |  | 2354282 | 100% | 2354282 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1093 | GRADING WORKS JCT C71 IRIGIRO ACCESS ROAD MUTHITHI WARD | GRADING WORKS JCT C71 IRIGIRO ACCESS ROAD MUTHITHI WARD | To improve accessibilty | No. of KMs done |  |  | KIGUMO | MUTHITHI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2411983.8 | 2411983.8 |  | MCG |  |  |  | 2411983.8 | 100% | 2411983.8 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1094 | GRADING OF ACCESS ROADS GITAHI MUNUNGA NGINDA WARD | GRADING OF ACCESS ROADS GITAHI MUNUNGA NGINDA WARD | To improve accessibilty | No. of KMs done |  |  | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2924935.5 | 2924935.5 |  | MCG |  |  |  | 2924935.5 | 100% | 2924935.5 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1095 | IMPROVEMENT OF ACCESS ROADS MUGUMOINI | IMPROVEMENT OF ACCESS ROADS MUGUMOINI | To improve accessibilty | No. of KMs done |  |  | GATANGA | MUGUMOINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3106781.85 | 3106781.85 |  | MCG |  |  |  | 3106781.85 | 100% | 3106781.85 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1096 | GRADING OF ACCESS ROADS KAMACHARIA WARD | GRADING OF ACCESS ROADS KAMACHARIA WARD | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3195139.9 | 3195139.9 |  | MCG |  |  |  | 3195139.9 | 100% | 3195139.9 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1097 | GRADING OF ACCESS ROADS WEMPA WARD | GRADING OF ACCESS ROADS WEMPA WARD | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3523140 | 3523140 |  | MCG |  |  |  | 3523140 | 100% | 3523140 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1098 | GRADING AND GRAVELLING OF ACCESS ROAD ICHAGAKI WARD | GRADING AND GRAVELLING OF ACCESS ROAD ICHAGAKI WARD | To improve accessibilty | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3547671 | 3547671 |  | MCG |  |  |  | 3547671 | 100% | 3547671 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1099 | GRADING OF ACCESS ROADS WEMPA WARD | GRADING OF ACCESS ROADS WEMPA WARD | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3798275 | 3798275 |  | MCG |  |  |  | 3798275 | 100% | 3798275 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1100 | QUARRY WASTE MBIRI | QUARRY WASTE MBIRI | To improve accessibilty | No. of KMs done |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1800000 | 1800000 |  | MCG |  |  |  | 1800000 | 100% | 1800000 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1101 | GRADING OF ACCESS ROADS KAMACHARIA | GRADING OF ACCESS ROADS KAMACHARIA | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3391858.8 | 3391858.8 |  | MCG |  |  |  | 3391858.8 | 100% | 3391858.8 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1102 | GRADING WORKS OF KAMACHARIA WARD | GRADING WORKS OF KAMACHARIA WARD | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3383294.45 | 3383294.45 |  | MCG |  |  |  | 3383294.45 | 100% | 3383294.45 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1103 | GRADING OF ACCESS ROADS Gaturi | GRADING OF ACCESS ROADS Gaturi | To improve accessibilty | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3138528 | 3138528 |  | MCG |  |  |  | 3138528 | 100% | 3138528 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1104 | Consruction of Gakarati Open shed at Kamahuha Ward | Consruction of Gakarati Open shed at Kamahuha Ward | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KAMAHUHA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1887568 | 1887568 |  | MCG |  |  |  | 1887568 | 100% | 1887568 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1105 | Construction works of Block - Kanyenyaini Ward | Construction works of Block - Kanyenyaini Ward | To improve accessibilty | No. of KMs done |  |  | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1746787 | 1746787 |  | MCG |  |  |  | 1746787 | 100% | 1746787 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1106 | Grading and Gravelling Works of access road - Kagunduini Ward | Grading and Gravelling Works of access road - Kagunduini Ward | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 |  |  |  | MCG | [6 empty] | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1107 | Grading and Gravelling Works of access road - Kagunduini Ward | Grading and Gravelling Works of access road - Kagunduini Ward | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 |  |  |  | MCG | [6 empty] | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1108 | Grading and Gravelling Works of access road - Kamacharia Ward | Grading and Gravelling Works of access road - Kamacharia Ward | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 |  |  |  | MCG | [6 empty] | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1109 | Grading and Gravelling Works of access road - Kanyenyaini Ward | Grading and Gravelling Works of access road - Kanyenyaini Ward | To improve accessibilty | No. of KMs done |  |  | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 |  |  |  | MCG | [6 empty] | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1110 | Grading and Gravelling Works of access road - Kinyona Ward | Grading and Gravelling Works of access road - Kinyona Ward | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1184499.8 | 1184499.8 |  | MCG |  |  |  | 1184499.8 | 100% | 1184499.8 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1111 | Grading and Gravelling Works of access road - Kinyona Ward | Grading and Gravelling Works of access road - Kinyona Ward | To improve accessibilty | No. of KMs done |  |  | KIGUMO | KINYONA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1184499.8 | 1184499.8 |  | MCG |  |  |  | 1184499.8 | 100% | 1184499.8 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1112 | Grading and Gravelling works of access roads - Kakuzi Ward | Grading and Gravelling works of access roads - Kakuzi Ward | To improve accessibilty | No. of KMs done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 |  |  |  | MCG | [6 empty] | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1113 | CONSTRUCTION OF TWIN WORKSHOP AND A LATRINE Mbiri | CONSTRUCTION OF TWIN WORKSHOP AND A LATRINE Mbiri | To improve accessibilty | No. of KMs done |  |  | KIHARU | MBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2824167 | 2824167 |  | MCG |  |  |  | 2824167 | 100% | 2824167 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1114 | GRADING OF ACCESS ROADS WANGU | GRADING OF ACCESS ROADS WANGU | To improve accessibilty | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 |  |  |  | MCG | [6 empty] | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1115 | Grading of Access Roads ICHAGAKI | Grading of Access Roads ICHAGAKI | To improve accessibilty | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 |  |  |  | MCG | [6 empty] | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1116 | Grading of access roads - kakuzi Ward | Grading of access roads - kakuzi Ward | To improve accessibilty | No. of KMs done |  |  | GATANGA | KAKUZI/MITUMBIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2893858.7 | 2893858.7 |  | MCG |  |  |  | 2893858.7 | 100% | 2893858.7 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1117 | INSTALLATION OF FLOOD LIGHTS IHURA STADIUM | INSTALLATION OF FLOOD LIGHTS IHURA STADIUM | To improve accessibilty | No. of KMs done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3506760 | 3506760 |  | MCG |  |  |  | 3506760 | 100% | 3506760 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1118 | CONSTRUCTION MATERIALS -MUMBI GROUNDS | CONSTRUCTION MATERIALS -MUMBI GROUNDS | To improve accessibilty | No. of KMs done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1965517 | 1965517 |  | MCG |  |  |  | 1965517 | 100% | 1965517 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1119 | GRADING WORKS OF GAICHANJIRU WARD | GRADING WORKS OF GAICHANJIRU WARD | To improve accessibilty | No. of KMs done |  |  | KANDARA | GAICHANJIRU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 |  |  |  | MCG | [6 empty] | 0 |  | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1120 | GRADING WORKS OF JAMCITY KWA WANJERI KWA MUKURINU KWA MBURU ACCESS ROAD - ICHAGAKI WARD | GRADING WORKS OF JAMCITY KWA WANJERI KWA MUKURINU KWA MBURU ACCESS ROAD - ICHAGAKI WARD | To improve accessibilty | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3616214.4 | 3616214.4 |  | MCG |  |  |  | 3616214.4 | 100% | 3616214.4 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1121 | Grading Works of Kandundu ACK - Mathioya access road - Township Ward | Grading Works of Kandundu ACK - Mathioya access road - Township Ward | To improve accessibilty | No. of KMs done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3416200 | 3416200 |  | MCG |  |  |  | 3416200 | 100% | 3416200 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1122 | Grading Works of Ndurumo - Kairi Loop access road - Kamacharia Ward | Grading Works of Ndurumo - Kairi Loop access road - Kamacharia Ward | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3583820 | 3583820 |  | MCG |  |  |  | 3583820 | 100% | 3583820 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1123 | Grading works of Wairatu - Kabithi access - Kamacharia Ward | Grading works of Wairatu - Kabithi access - Kamacharia Ward | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3625056 | 3625056 |  | MCG |  |  |  | 3625056 | 100% | 3625056 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1124 | Grading Works of Kairi - Kaganda - Pakawa access road - Murarandia | Grading Works of Kairi - Kaganda - Pakawa access road - Murarandia | To improve accessibilty | No. of KMs done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3804800 | 3804800 |  | MCG |  |  |  | 3804800 | 100% | 3804800 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1125 | Grading works of Kariti secondary - Gatuikira access road- Kagunduini Ward | Grading works of Kariti secondary - Gatuikira access road- Kagunduini Ward | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3823940 | 3823940 |  | MCG |  |  |  | 3823940 | 100% | 3823940 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1126 | Grading and Gravelling Works of access roads - Kimorori/Wempa Ward | Grading and Gravelling Works of access roads - Kimorori/Wempa Ward | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 996150 | 996150 |  | MCG |  |  |  | 996150 | 100% | 996150 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1127 | Spot Improvement of Kihumbuini access road - Kihumbuini Ward | Spot Improvement of Kihumbuini access road - Kihumbuini Ward | To improve accessibilty | No. of KMs done |  |  | GATANGA | KIHUMBUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 1250800 | 1250800 |  | MCG |  |  |  | 1250800 | 100% | 1250800 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1128 | Grading of access roads kimorori Wempa | Grading of access roads kimorori Wempa | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2658720 | 2658720 |  | MCG |  |  |  | 2658720 | 100% | 2658720 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1129 | Grading Works of Kamundaini - Muiri access road - Wangu Ward | Grading Works of Kamundaini - Muiri access road - Wangu Ward | To improve accessibilty | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3179460 | 3179460 |  | MCG |  |  |  | 3179460 | 100% | 3179460 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1130 | Grading Works of Longonot Avenue - Kwa Kamau Fresh access road - Kimorori/Wempa Ward | Grading Works of Longonot Avenue - Kwa Kamau Fresh access road - Kimorori/Wempa Ward | To improve accessibilty | No. of KMs done |  |  | MARAGUA | KIMORORI WEMPA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3509000 | 3509000 |  | MCG |  |  |  | 3509000 | 100% | 3509000 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1131 | Grading and Gravelling works of Ihiga Ria Ngechu-Ndurumo access road - Kamacharia Ward | Grading and Gravelling works of Ihiga Ria Ngechu-Ndurumo access road - Kamacharia Ward | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3577440 | 3577440 |  | MCG |  |  |  | 3577440 | 100% | 3577440 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1132 | Grading of Access Roads Murarandia | Grading of Access Roads Murarandia | To improve accessibilty | No. of KMs done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3741000 | 3741000 |  | MCG |  |  |  | 3741000 | 100% | 3741000 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1133 | Grading works of Pioneer - Kaharati access road - Ichagaki Ward | Grading works of Pioneer - Kaharati access road - Ichagaki Ward | To improve accessibilty | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3775800 | 3775800 |  | MCG |  |  |  | 3775800 | 100% | 3775800 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1134 | Grading works of Muruthi - Kwa Mburu access road - Ichagaki Ward | Grading works of Muruthi - Kwa Mburu access road - Ichagaki Ward | To improve accessibilty | No. of KMs done |  |  | MARAGUA | ICHAGAKI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3930080 | 3930080 |  | MCG |  |  |  | 3930080 | 100% | 3930080 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1135 | Grading Works of Mbaire - Kiharo Ha Gaitho access road - Ruchu Ward | Grading Works of Mbaire - Kiharo Ha Gaitho access road - Ruchu Ward | To improve accessibilty | No. of KMs done |  |  | KANDARA | RUCHU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3931240 | 3931240 |  | MCG |  |  |  | 3931240 | 100% | 3931240 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1136 | Grading Works of access roads - Gaturi Ward | Grading Works of access roads - Gaturi Ward | To improve accessibilty | No. of KMs done |  |  | KIHARU | GATURI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2253300 | 2253300 |  | MCG |  |  |  | 2253300 | 100% | 2253300 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1137 | Grading Works of Jovister Academy Loop access roads - Kagunduini Ward | Grading Works of Jovister Academy Loop access roads - Kagunduini Ward | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2497500 | 2497500 |  | MCG |  |  |  | 2497500 | 100% | 2497500 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1138 | Culvert Installations Diameter Kagunduini | Culvert Installations Diameter Kagunduini | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2644800 | 2644800 |  | MCG |  |  |  | 2644800 | 100% | 2644800 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1139 | Grading works of Ngararia - Kiararii - Kimathi - Kaburugi - Mokuiri access road - Ngararia Ward | Grading works of Ngararia - Kiararii - Kimathi - Kaburugi - Mokuiri access road - Ngararia Ward | To improve accessibilty | No. of KMs done |  |  | KANDARA | NGARARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3335493.6 | 3335493.6 |  | MCG |  |  |  | 3335493.6 | 100% | 3335493.6 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1140 | GRADING WORKS - KAMACHARIA WARD | GRADING WORKS - KAMACHARIA WARD | To improve accessibilty | No. of KMs done |  |  | MATHIOYA | KAMACHARIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3535680 | 3535680 |  | MCG |  |  |  | 3535680 | 100% | 3535680 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1141 | Grading Works - Muguru Ward | Grading Works - Muguru Ward | To improve accessibilty | No. of KMs done |  |  | KANGEMA | MUGURU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3720910 | 3720910 |  | MCG |  |  |  | 3720910 | 100% | 3720910 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1142 | Grading works of Gatuya Coffee factory - Kaganda Sec. School access road - Murarandia Ward | Grading works of Gatuya Coffee factory - Kaganda Sec. School access road - Murarandia Ward | To improve accessibilty | No. of KMs done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3633345 | 3633345 |  | MCG |  |  |  | 3633345 | 100% | 3633345 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1143 | Grading works kariara | Grading works kariara | To improve accessibilty | No. of KMs done |  |  | GATANGA | KARIARA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3927180 | 3927180 |  | MCG |  |  |  | 3927180 | 100% | 3927180 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1144 | Grading Works of Gatei - Kagongo - Ngaru access road - Gatanga Ward | Grading Works of Gatei - Kagongo - Ngaru access road - Gatanga Ward | To improve accessibilty | No. of KMs done |  |  | GATANGA | GATANGA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3688800 | 3688800 |  | MCG |  |  |  | 3688800 | 100% | 3688800 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1145 | Opening of Access Roads - Murarandia Ward | Opening of Access Roads - Murarandia Ward | To improve accessibilty | No. of KMs done |  |  | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 2365948 | 2365948 |  | MCG |  |  |  | 2365948 | 100% | 2365948 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1146 | Grading Works of Masaku - Kirogo access Road - Wangu Ward | Grading Works of Masaku - Kirogo access Road - Wangu Ward | To improve accessibilty | No. of KMs done |  |  | KIHARU | WANGU |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3229375.35 | 3229375.35 |  | MCG |  |  |  | 3229375.35 | 100% | 3229375.35 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1147 | Grading of works of Gitura - Kwa Chief access road - Kagunduini Ward | Grading of works of Gitura - Kwa Chief access road - Kagunduini Ward | To improve accessibilty | No. of KMs done |  |  | KANDARA | KAGUNDUINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2022-06-15 | 3647083.8 | 3647083.8 |  | MCG |  |  |  | 3647083.8 | 100% | 3647083.8 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | NO |  | NO
1148 | Construction and Upgrading to Bitumen Starndard of jct Amica Bank Building Access Road, jct Road Behind Magunas Wholesalers and jct Brewery Depot – jct Murang’a High School Link Road | Construction and Upgrading to Bitumen Starndard of jct Amica Bank Building Access Road, jct Road Behind Magunas Wholesalers and jct Brewery Depot – jct Murang’a High School Link Road | Improve infrastructure | No.of KMs done |  |  | KIHARU | TOWNSHIP | ROADS & INFRASTRUCTURE | MURANG'A MUNICIPALITY | Murang'a Municipality |  | 2021-07-18 | 2021-11-08 | 2022-04-12 | 2022-04-12 | 33823396 | 33823396 |  | Development Partner | Kenya Urban Support Program(KUSP) |  | 33823396 | 33823396 | 1% | 33823396 | 0 | 0 | COMPLETED | 100% | [7 empty] | NO |  | NO |  | YES
1149 | Proposed grading, gravelling & drainage works of mareka & JCT sammar access road | grading, gravelling & drainage works | Improve infrastructure | No.of KMs done |  |  | MARAGUA | ICHAGAKI | ROADS & INFRASTRUCTURE | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  |  | 2021-12-03 | 3268950 | 3268950 |  | MCG |  |  | 3268950 | 3268950 | 1% | 3268950 | 0 | 0 | COMPLETED | 100% | [7 empty] | NO |  | NO |  | YES
1150 | Upgrading To Bitumen Standards To Junction Hospital Road Stage-KPLC-Lands Offices –Junction Kiria-ini Road and Junction Family Bank backlane Access Roads and Improvement and Upgrading of Mukuyu ECDE School and Social Hall | Upgrading To Bitumen Standards To Junction Hospital Road Stage-KPLC-Lands Offices –Junction Kiria-ini Road and Junction Family Bank backlane Access Roads and Improvement and Upgrading of Mukuyu ECDE School and Social Hall | To promote connectivity and accessibility | No.of KMs done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Murang'a Municipality |  |  | 2020-10-26 | 2021-02-02 | 2020-06-10 | 43374646 | 43374646 |  | Development Partner | Kenya Urban Support Program(KUSP) |  | 43374646 | 43374646 | 1% | 43374646 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | YES | YES | YES
1151 | Rehabilitation works to create Offices for Murang’a Municipality | Rehabilitation works to create Offices for Murang’a Municipality | To upgrade and construct housing which is safe and secure | No. done |  |  | KIHARU | TOWNSHIP |  | INFRASTRUCTURE | Murang'a Municipality |  |  |  |  | 2020-06-10 | 9900000 | 9900000 |  | Development Partner | Kenya Urban Support Program(KUSP) |  | 9900000 | 9900000 | 1% | 9900000 | 0 | 0 | COMPLETED | 100% | [5 empty] | NO |  |  | NO |  | YES | YES | YES
1152 | Grading and gravelling of Kamaguta pry school access road | Earth works to cut and open roads and make road useable | Improve infrastructure | completed works |  | 3538490 | KIHARU | MUGOIRI |  |  | Infrastructure, Roads, Housing and Transport |  |  |  | 2018-12-01 | 2018-09-24 |  | 3538490 |  | MCG |  |  |  | 3538490 | 1% | 3538490 | 0 | 0 | PLANNED | 1% | [8 empty] | YES | YES | YES | YES
1153 | Alterations & refurbishment of Muriranjas hospital to create a staffroom & ablution | demolition,reconstrruction and repainting works | Improve infrastructure | completed works |  | 317282 | KIHARU | MUGOIRI |  | HEALTH | Health and Sanitation |  |  |  | 2018-06-30 | 2018-06-11 | 317282 | 317282 |  | MCG | [5 empty] | 317282 | 0 | 0 | PLANNED | 1% | [8 empty] | NO | NO | NO | NO | NO | YES
1154 | Opening of access roads | Earth works to cut and open roads | Improve infrastructure | No.of kms done |  | 2306034.48 | KIHARU | MURARANDIA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  |  | 2018-06-30 |  | 2306034.48 | 2306034.48 |  | MCG | [5 empty] | 2306034.48 | 0 | 0 | PLANNED | 1% | [8 empty] | NO | NO | NO | NO | NO | YES
1155 | Construction of ablution block at Muriranjas hospital | Construction of ablution block at Muriranjas hospital | Improve infrastructure | completed works |  | 1338937.17 | KIHARU | MUGOIRI |  | HEALTH | Health and Sanitation |  |  |  | 2018-06-30 | 2018-04-23 | 1338937.17 | 1338937.17 |  | MCG | [5 empty] | 1338937.17 | 0 | 0 | PLANNED | 1% | [8 empty] | NO | NO | NO | NO | NO | YES
1156 | Proposed opening /heavy grading of access roads. | Earth works to cut and open roads | Improve infrastructure | No.of kms done |  | 2198253 | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  | 2016-08-01 | 2016-09-30 | 2016-09-22 | 2198253 | 2198253 |  | MCG | [5 empty] | 2198253 | 0 | 0 | PLANNED | 1% | [8 empty] | NO | NO | NO | NO | NO | YES
1157 | Proposed construction of fresh produce & wholesale market at maragwa. | construction works to fresh produce market | improve enevironment for trading | completed works |  | 2020966.57 | MARAGUA | NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  | 2016-08-02 | 2016-09-30 | 2016-09-06 | 2020966.57 | 2020966.57 |  | MCG | [5 empty] | 2020966.57 | 0 | 0 | PLANNED | 1% | [8 empty] | NO | NO | NO | NO | NO | YES
1158 | Proposed drainage work for Kahuro Gatundu and Sabasaba towns. | construction of drainage works for Kahuro Gatundu and Sabasaba towns. | Improve infrastructure | completed works |  | 1676370 | KIHARU, MARAGUA | MUGOIRI, NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  | 2016-08-03 | 2016-09-30 | 2016-09-09 | 1676370 | 1676370 |  | MCG | [5 empty] | 1676370 | 0 | 0 | PLANNED | 1% | [8 empty] | NO | NO | NO | NO | NO | YES
1159 | Proposed drainage works for Kenol, Kabati and Kangari towns. | construction of drainage works for Kenol town and Kangari towns. | Improve infrastructure | completed works |  | 1750320 | KIGUMO, MARAGUA | KIGUMO, NGINDA |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  | 2016-08-04 | 2016-09-30 | 2016-09-12 | 1750320 | 1750320 |  | MCG | [5 empty] | 1750320 | 0 | 0 | PLANNED | 1% | [8 empty] | NO | NO | NO | NO | NO | YES
1160 | Proposed renovation of Kandara childrens home classrooms. | Painting works to classrooms at kandara childrens home | Improve infrastructure | completed works |  | 835941.78 | KANDARA | ITHIRU |  | EDUCATION | Education and Technical Training |  |  | 2016-08-05 | 2016-09-30 | 2016-09-09 | 835941.78 | 835941.78 |  | MCG | [5 empty] | 835941.78 | 0 | 0 | PLANNED | 1% | [8 empty] | NO | NO | NO | NO | NO | YES
1161 | Proposed renovation of Kandara childrens home offices. | Painting works to Facilities at kandara childrens home | Improve infrastructure | completed works |  | 565100.17 | KANDARA | ITHIRU |  | EDUCATION | Education and Technical Training |  |  | 2016-08-06 | 2016-09-30 | 2016-09-09 | 565100.17 | 565100.17 |  | MCG | [5 empty] | 565100.17 | 0 | 0 | PLANNED | 1% | [8 empty] | NO | NO | NO | NO | NO | YES
1162 | Proposed grading and gravelling of Dr. Kiano-gichi access road | Earth works to cut and open roads | Improve infrastructure | completed works |  | 855902.4 | KIHARU | MUGOIRI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  | 2015-08-01 | 2015-09-30 | 2015-08-03 | 855902.4 | 855902.4 |  | MCG |  |  |  | 855902.4 | 100% | 855902.4 | 0 | 0 | COMPLETED | 100% | [8 empty] | NO | NO | NO | NO | NO | YES
1163 | Proposed opening of access roads | Earth works to cut and open roads | Improve infrastructure | completed works |  | 2327603.1 | KANGEMA | KANYENYAINI |  | INFRASTRUCTURE | Infrastructure, Roads, Housing and Transport |  |  | 2016-02-10 | 2016-06-30 | 2016-04-26 | 2327603.1 | 2327603.1 |  | MCG |  |  |  | 2327603.1 | 100% | 2327603.1 | 0 | 0 | COMPLETED | 100% | [8 empty] | NO | NO | NO | NO | NO | YES
1164 | Kimathi-Githuri Irrigation project | Construction of intake ,laying of conveyance pipelines | Irrigation of 150 acres for food security and agribusines | Functional irrigation project | Dev | Irrigation developnet | KIHARU | GATURI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation |  |  | 2014-01-09 |  |  | 200000000 | 200000000 | 200000000 | CGM |  |  |  | 200000000 | 100% |  |  | 200000000 | COMPLETED | 100% | [8 empty] | YES | Reservoir enlargenet to boost storage | YES | Conservation of river riparian areas | YES | 80 acres irrigated Project is functional
1165 | Kairi Irrigation project | Construction of intake , laying of conveyance pipelines | Irrigatioin of 400 acres for food security and agribusiness | Functional irrigation project | Dev | Irrigation developmet | KANGEMA | MUGURU |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation |  |  | 2014-01-09 |  |  | 140000000 | 140000000 | 140000000 | GOK |  |  |  | 140000000 | 100% |  |  | 140000000 | COMPLETED | 100% | [8 empty] | YES | conservation of catchment areas | YES | conservation of river ripatrian areas | YES | 400 acres irrigated | Project is fuctional
1166 | Riakomo Irrigation project | Construction of intake and laying of conveyance mainlines | Irrigatio of 100 acres fro food security and agribussines | Functional irrigation project | Dev | Irrigation Developnet | GATANGA | MUGUMOINI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation |  |  | 2014-01-09 |  |  | 100000000 | 100000000 | 100000000 | GOK |  |  |  | 100000000 | 100% |  |  | 100000000 | COMPLETED | 100% | [8 empty] | YES | installation of water meters | YES | Conservation of river riparian areas | YES | 70 acres irrigated | project is functional
1167 | Drilling and equiping of Gatunduguru B/H | Drilling , installation of water pump, water kiosk , solar power | Supply 200 households with domestic water | Fuctional borehole water project | Dev | Water services | KIGUMO | MUTHITHI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation |  |  | 2014-01-09 |  |  | 5500000 | 5500000 | 5500000 | CGM |  |  |  | 5500000 | 100% |  |  | 5500000 | COMPLETED | 100% | [8 empty] | YES | Installation of demestic water meters /clean energy | YES | Maintemance of solar panel | YES | 200 homesteds benefiting | Project is functional
1168 | Drilling and equiping of Gitura B/H | Drilling and installation of water pump | Supply 150 households with domestic water | Fuctional borehole water project | Dev | Water services | KANDARA | KAGUNDUINI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation |  |  | 2014-01-09 |  |  | 5500000 | 5500000 | 5500000 | CGM |  |  |  | 5500000 | 100% |  |  | 5500000 | COMPLETED | 100% | [8 empty] | YES | Installation of solar power | YES | Installation of solar power | YES | 250 households benefitting | Project si functional
1169 | Extension of domestic water distribution pipes | Supply , delivery and laying of water pipes and testing | Extension of domestic water distribution pipes | Water flowing to targeted beneficiaries | Dev | Water services | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation |  |  | 2014-01-09 |  |  | 52500000 | 52500000 | 52500000 | CGM |  |  |  | 52500000 | 100% |  |  | 52500000 | COMPLETED | 100% | [8 empty] | YES | Adequate backfilling of pipes trenches | YES | Installation of domestic water meters | YES | 2,500 households benefitting | Project si functional
1170 | Supply and installation of water storage tanks to ECDE centres | Installation of tanks and rain water harvesting facilities | Supplying reliable domestic water to ECDE learners | Functioning rainwater harvesting facility | Dev | Water services | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation |  |  | 2014-01-09 |  |  | 8400000 | 8400000 | 8400000 | CGM |  |  |  | 8400000 | 100% |  |  | 8400000 | COMPLETED | 100%
1171 | Drilling and equiping of Muthithi borehole | Drilling of Muthithi borehole ,installation of pump, solar power and water kiosk | To supply 110 households with domestic water | Functioning borehole | Dev. | Water | KIGUMO | MUTHITHI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5000000 | 5000000 | 5000000 | MCG |  |  |  | 5000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Intsallation of power failure relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households be done | Project is functional
1172 | Drilling and equiping of Nanga borehole | Drilling of Nanga borehole ,installation of pump, solar power and water kiosk | To supply 120 households with domestic water | Functioning borehole | Dev. | Water | GATANGA | KAKUZI/MITUMBIRI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5000000 | 5000000 | 5000000 | MCG |  |  |  | 5000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Intsallation of power failure relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households be done | Project is functional
1173 | Drilling and equiping of Thaara borehole | Drilling of Thaara borehole ,installation of pump, solar power and water kiosk | To supply 90 households with domestic water | Functioning borehole | Dev. | Water | MARAGUA | NGINDA |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5000000 | 5000000 | 5000000 | MCG |  |  |  | 5000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Intsallation of power failure relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households be done | Project is functional
1174 | Drilling and equiping of Gatitu borehole | Drilling of Gatitu borehole ,installation of pump, solar power and water kiosk | To supply 100 households with domestic water | Functioning borehole | Dev. | Water | KANDARA | ITHIRU |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5000000 | 5000000 | 5000000 | MCG |  |  |  | 5000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Intsallation of power failure relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households be done | Project is functional
1175 | Drilling and equiping of Mutithi borehole in Makuyu | Drilling of Mutithi borehole ,installation of pump, solar power and water kiosk | To supply 120 households with domestic water | Functioning borehole | Dev. | Water | MARAGUA | MAKUYU |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5000000 | 5000000 | 5000000 | MCG |  |  |  | 5000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of water level relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households be done | Project is functional
1176 | Drilling and equiping of Thanju borehole in Gaturi | Drilling of Thanju borehole ,installation of pump, solar power and water kiosk | To supply 90 households with domestic water | Functioning borehole | Dev. | Water | KIHARU | MBIRI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5000000 | 5000000 | 5000000 | MCG |  |  |  | 5000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of water level relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households be done | Project is functional
1177 | Drilling and equiping of Yakarengo borehole in Gitugi | Drilling of Yakarengo borehole ,installation of pump, solar power and water kiosk | To supply 120 households with domestic water | Functioning borehole | Dev. | Water | MATHIOYA | GITUGI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5000000 | 5000000 | 5000000 | MCG |  |  |  | 5000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of water level relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households be done | Project is functional
1178 | Drilling and equiping of Kangui borehole in Gaturi | Drilling of Kangui borehole ,installation of pump, solar power and water kiosk | To supply 110 households with domestic water | Functioning borehole | Dev. | Water | KIHARU | GATURI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5000000 | 5000000 | 5000000 | MCG |  |  |  | 5000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of water level relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households be done | Project is functional
1179 | Drilling and equiping of Mbogoini borehole in Kahumbu | Drilling of Mbogoini borehole ,installation of pump, solar power and water kiosk | To supply 100 households with domestic water | Functioning borehole | Dev. | Water | KIGUMO | KAHUMBU |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5000000 | 5000000 | 5000000 | MCG |  |  |  | 5000000 | 100% |  |  | 0 | COMPLETED | 100% | [9 empty] | Installation of water level relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households be done | Project is functional
1180 | Rehabilitation of Gatunyu, borehole | Installation of solar power system | To supply 180 households with domestic water | Functioning borehole | Dev. | Water | GATANGA | MUGUMOINI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 3000000 | 3000000 | 3000000 | MCG |  |  |  | 3000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of water meter | YES | water quality analysis be done on quartery basis | YES | installation of water meters | Project is functional
1181 | Rehabilitation of Kagumoini borehole | Installation of solar power system | To supply 120 households with domestic water | Functioning borehole | Dev. | Water | KANDARA | GAICHANJIRU |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 2000000 | 2000000 | 2000000 | MCG |  |  |  | 2000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of water meter | YES | water quality analysis be done on quartery basis | YES | installation of water meters | Project is functional
1182 | Rehabilitation of Gitura Borehole | Installation of solar power system | To supply 120 households with domestic water | Functioning borehole | Dev. | Water | KANDARA | KAGUNDUINI |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 2000000 | 2000000 | 2000000 | MCG |  |  |  | 2000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of water meter | YES | water quality analysis be done on quartery basis | YES | installation of water meters | Project is functional
1183 | Procurement of 2 skip loaders | Supply , delivery and testing of 2 skip loaders | To ease garbage collection in the county | Functional skip loaders | Dev. | Water | KIHARU | TOWNSHIP |  | ENVIRONMENT | Environment, Natural Resources, Water and Irrigation | [5 empty] | 24000000 | 24000000 | 24000000 | MCG |  |  |  | 24000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | continous maintenance | YES | Continous maintenance | YES | Continouse maintenance | Equipment is functional
1184 | Procurement and installation of 12 skip bins | Supply , delivery and installation of 22 skip bins | To enhance solid waste storage and collection | Functional skip bins | Dev. | Water | KIHARU | TOWNSHIP |  | ENVIRONMENT | Environment, Natural Resources, Water and Irrigation | [5 empty] | 36000000 | 36000000 | 36000000 | MCG |  |  |  | 36000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | continous maintenance | YES | Continous maintenance | YES | Continouse maintenance | Equipment is functional
1185 | Extension of domestic water pipelines | Supply, delivery and installation of water distribution pipelines | To supply 3,000 housholds with safe domestic water | Water flowing to targeted communities | Dev. | Water | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 70000000 | 70000000 | 70000000 | MCG |  |  |  | 70000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of water meterS | YES | Continous maintenance | YES | Continouse maintenance | Projects are functional
1186 | Installation of ECDE water storage tanks and rainwater harvesting facilities | Supply , deliver and installation of 40 water tanks and rain water harvesting facilitis | To supply reliable domestic water to ECDE learners | Water stored in installed ECDE water tanks | Dev. | Water | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 8400000 | 8400000 | 8400000 | MCG |  |  |  | 8400000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of water meterS | YES | Continous maintenance | YES | Continouse maintenance | Projects are functional
1187 | Construction of Ititu Ikundu Irrigation project | Construction intake works and laying of conveyance mainlines | To supply irrigation water to 1000 households | Functional irrigation project | Dev. | Water | MARAGUA | NGINDA |  | IRRIGATION | Environment, Natural Resources, Water and Irrigation | [5 empty] | 140000000 | 140000000 | 140000000 | world bank |  |  |  | 140000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | maintenace of reparian areas | YES | Continous maintenance | YES | Continouse maintenance | Projects are functional
1188 | Drilling and equiping of Mukerenju borehole | drilling of borehole at Mukerenju, intallation of water pumps, solar power , water kiosk | to supply domestic water to 150 households | Functional borehole | Dev. | Water | KANDARA | KAGUNDUINI |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 5500000 | 5500000 | 5500000 | MCG |  |  |  | 5500000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of power failure relay | YES | Ensuring that Water is accessed by all | YES | Conitinous maintenanace for sustainablity | Project is functional
1189 | Drilling and equiping of Kenneth Matiba Hospital borehole | drilling of borehole at Kenneth Matiba Hospital borehole, intallation of water pumps, solar power | To supply domestic water to Kenneth Matiba hospital | Functional borehole | Dev. | Water | GATANGA | ITHANGA |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 12000000 | 12000000 | 12000000 | EABL | EABL |  | 12000000 | 12000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Distribution of water to neighboring community | YES | continous maintenance for sustainability | YES | Conitinous maintenanace for sustainablity | Project is functional
1190 | Drilling and equiping of Karung'ang'i hospital borehole | drilling of borehole at Karung'ang;i Hospital borehole, intallation of water pumps, solar power | To supply domestic water to Karung'ang'i community | Functional borehole | Dev. | Water | MARAGUA | KIMORORI WEMPA |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 12000000 | 12000000 | 12000000 | EABL | EABL |  | 12000000 | 12000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Distribution of water to community | YES | continous maiantenace for sustainability | YES | Conitinous maintenanace for sustainablity | Project is functional
1191 | Extension of water distribution pipelines | Supply, delivery , installation and testing of water distribution pipes in all wards | To access domestic water to 2450 households | Functional water pipelines | Dev. | Water | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 105000000 |  | 105000000 | MCG |  |  |  |  | 100% |  |  |  | COMPLETED | 100% | [8 empty] | YES | Continous maintenance for sustainability | YES | Installation of water meters | YES | Conitinous maintenanace for sustainablity | Project is Functional
1192 | Installation of ECDE water storage tanks | Supply , delivery and installation of water tanks to 40 ECDEs and installation of rain water harvesting facilities | To access safe water to EDE learners | Functional water storage tanks | Dev. | Water | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 8000000 | 8000000 | 8000000 | MCG |  |  |  | 8000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | construction of suitable drains and installation of flat valves | YES | Continous maintenance | YES | Conitinous maintenanace for sustainablity | Project is functional
1193 | Procurement of Gabage collection trucks | Supply , delivery and commissioning of 2 No Gabage collection trucks | To ensure a clean environment free from garbage | Fuctional gabage collection trucks | Dev. | Environemnt | KIHARU | TOWNSHIP |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 14000000 | 14000000 | 14000000 | MCG |  |  |  | 14000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Continous maintenance to ensure efficiency in operation | YES | Continous maintenance to ensure efficiency in operation | YES | Continous maintenance to ensure efficiency in operation | Project is operational
1194 | Purchase of skip bins | Procurement, delivery and installation of 10 skip bins | To ensure clean storage of garbage for collection | Functional skip bins | Dev. | Environemnt | KIHARU | TOWNSHIP |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 35000000 | 35000000 | 35000000 | MCG |  |  |  | 35000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Bins to be strategically located for effective usage | YES | Bns to be strategically located for effective usage | YES | Bns to be strategically located for effective usage | Project is operational
1195 | Rehabilitation of Kaigwa Borehole in Gaturi | Installation of solar power system | To supply water to Kaigwa community using clean energy | Functional borehole | Dev. | Water | KIHARU | GATURI |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 2100000 | 2100000 | 2100000 | MCG |  |  |  | 2100000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Continous maintenance for sustainability | YES | Ensuring that Water is accessed by all community members | YES | Conitinous maintenanace for sustainablity | Project is operational
1196 | Rehabilitation of Kagongo Borehole in Gaturi | Installation of solar power system | To supply water to Kaigwa community using clean energy | Functional borehole | Dev. | Water | KIHARU | GATURI |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 2100000 | 2100000 | 2100000 | MCG |  |  |  | 2100000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Continous maintenance for sustainability | YES | Ensuring that Water is accessed by all community members | YES | Conitinous maintenanace for sustainablity | Project is operational
1197 | Rehabilitation of Gitura Borehole in Kagunduini | Installation of solar power system | To supply water to Gitura community using clean energy | Functional borehole | Dev. | Water | KANDARA | KAGUNDUINI |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 2100000 | 2100000 | 2100000 | MCG |  |  |  | 2100000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Continous maintenance for sustainability | YES | Ensuring that Water is accessed by all community members | YES | Conitinous maintenanace for sustainablity | Project is operational
1198 | Rehabilitation of Mumbu Borehole in Kahumbu | Installation of solar power system | To supply water to Mumbu community using clean energy | Functional borehole | Dev. | Water | KIGUMO | KAHUMBU |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 2100000 | 2100000 | 2100000 | MCG |  |  |  | 2100000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Continous maintenance for sustainability | YES | Ensuring that Water is accessed by all community members | YES | Conitinous maintenanace for sustainablity | Project is operational
1199 | Procurement and installation of Water meters | Supply and installation of 4,000 consumer water meters | To reduce water losses in water supply schemes | Reduced water losses | Dev | Water | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  |  | Environment, Natural Resources, Water and Irrigation | [5 empty] | 16000000 | 16000000 | 16000000 | MCG |  |  |  | 16000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Meter installation to be scalled up | YES | Meter installation to be scalled up |  | Conitinous meter maintenanace for sustainablity | Project is operational
1200 | Drilling and equiping of Mihango borehole | Drilling , equipping Mihang'aborehole with water pump, solar system and water kiosk | To supply community Mihang'o community with domestic water | A functional borehole water project | Dev. | Water | MARAGUA | KAMBITI |  |  | Environment, Natural Resources, Water and Irrigation |  |  | 2024-01-09 |  |  | 5250000 |  | 5250000 | MCG |  |  |  |  | 100% |  |  |  | COMPLETED | 100% | [8 empty] | YES | Intsallation of power failure relay | YES | water quality analysis be done on quartery basis | YES | Distribution to households to be done | Project is functional
1201 | Rehabilitation of Gatunyu borehole | Installation of solar power system | To supply domestic water using renewable energy | A functional borehole water project |  |  | GATANGA | MUGUMOINI |  |  | Environment, Natural Resources, Water and Irrigation |  |  | 2024-01-09 |  |  | 2100000 | 2100000 | 2100000 | MCG |  |  |  | 2100000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Water quality analysis be done on a quartery basis | YES | Installation of water meters | YES | Distribution to households to be done | Project is functional
1202 | Rehabilitation of Gatumbu borehole | Installation of solar power system | To supply domestic water using renewable energy | A functional water supply project | Dev. | Water | KANDARA | MURUKA |  |  | Environment, Natural Resources, Water and Irrigation |  |  | 2024-01-09 |  |  | 2100000 | 2100000 | 2100000 | MCG |  |  |  | 2100000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Water quality analysis be done on a quartery basis | YES | Installation of water meters | YES | Distribution to households to be done | Project is functional
1203 | Extension of water supply pipelines | Supply , delivery , installation and testing of of water pipelines | To supply domestic water to unserved communities | A functional water supply project | Dev. | Water | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  |  | Environment, Natural Resources, Water and Irrigation |  |  | 2024-01-09 |  |  | 70000000 | 70000000 | 70000000 | MCG |  |  |  | 70000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Installation of power failure relay | YES | Water quality analysis be doen on a qaurterly basis | YES | Distribution to households to be done | Project is functional
1204 | Procurement of skip loader | supply , delivery , and commissioning of one kip loader | To enhance gabage collection and ensure a clean environment | A functional skip loader | Dev. | Environment | KIHARU | TOWNSHIP |  |  | Environment, Natural Resources, Water and Irrigation |  |  | 2024-01-09 |  |  | 12000000 | 12000000 | 12000000 | MCG |  |  |  | 12000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Continous Maintenance to ensure operational efficiency | YES | Continous Maintenance to ensure operational efficiency | YES | Continous Maintenance to ensure operational efficiency | Project is functional
1205 | Installation of ECDE water storage tanks | Supply , delivery and instaltion of ECDE water tanks and rainwater harvesting facilities | To enhance water storage and conservation in learning institutions | A function water storage facility | Dev. | Water | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  |  | Environment, Natural Resources, Water and Irrigation |  |  | 2024-01-09 |  |  | 8000000 | 8000000 | 8000000 | MCG |  |  |  | 8000000 | 100% |  |  | 0 | COMPLETED | 100% | [8 empty] | YES | Continous Maintenance to ensure operational efficiency | YES | Installation of hand washing facility | YES | Continous Maintenance to ensure operational efficiency | Project is functional
1206 | MIP Construction of Gatehouse& Gate, Fencing | Primary Security Infrastructure | Custom-Controlled Environment essential because the park functions as both a Special Economic Zone (SEZ) and an Export Processing Zone (EPZ). | The park is a legally bonded zone that will increase job creating and increase manufacturing knowledge |  |  | GATANGA | KAKUZI/MITUMBIRI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2024-06-01 | 2024-09-01 | 2025-06-01 | 2025-06-01 | 3000000 | 3000170 | 3000170 | MCG |  |  |  | 3000170 | 100% |  |  | 0 | COMPLETED | 100%
1207 | MIP Grading &Gravelling Works of Access Road from Kenneth Matiba Hospital to Epz A- | Access road into the park from the main road | Infrastructural development for the growth of the park | Accessibility for heavy logistics, and future development for investors. |  |  | GATANGA | KAKUZI/MITUMBIRI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2024-06-01 | 2024-09-01 | 2025-06-01 | 2025-06-01 | 4000000 | 3999700 | 3999700 | MCG | [8 empty] | PLANNED | 1%
1208 | Construction of Market Shade | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | KAHUMBU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2024-06-01 | 2024-09-01 | 2025-06-01 | 2025-06-01 | 5000000 | 4999860 | 4999860 | MCG |  |  |  | 4999860 | 100% |  |  | 0 | COMPLETED | 100%
1209 | Construction of Market Shade | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | TOWNSHIP |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2024-06-01 | 2024-09-01 | 2025-06-01 | 2025-06-01 | 5000000 | 5001369 | 5001369 | MCG | [8 empty] | PLANNED | 1%
1210 | Completion of Pit Latrine | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | GATANGA | ITHANGA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2024-06-01 | 2024-09-01 | 2025-06-01 | 2025-06-01 | 250000 | 355430 | 355430 | MCG |  |  |  | 355430 | 100% |  |  | 0 | COMPLETED | 100%
1211 | Construction of Market Shade | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | GATANGA | KAKUZI/MITUMBIRI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2024-06-01 | 2024-09-01 | 2025-06-01 | 2025-06-01 | 4500000 | 4500140 | 4500140 | MCG | [8 empty] | PLANNED | 1%
1212 | Construction of 4No.Door and Urinal Pit Latrine | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANGEMA | MUGURU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2024-06-01 | 2024-09-01 | 2025-06-01 | 2025-06-01 | 500000 | 500515 | 500515 | MCG |  |  |  | 500515 | 100% |  |  | 0 | COMPLETED | 100%
1213 | Proposed Construction of 12 No. stalls | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MATHIOYA | KAMACHARIA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2024-06-01 | 2024-09-01 | 2025-06-01 | 2025-06-01 | 1200000 | 1201560 | 1201560 | MCG | [8 empty] | PLANNED | 1%
1214 | Investment confrence | Investemnt conference | Highlighting opportunities in agriculture, manufacturing, renewable energy, ICT/BPO in Murang'a | Attracting private capital to drive economic growth and create sustainable employment opportunities. |  |  | GATANGA | MUGUMOINI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2024-08-01 | 2024-08-01 | 2025-06-01 | 2025-06-01 | 120000000 | 15000000 | 15000000 | MCG |  |  |  | 15000000 | 100% |  |  | 0 | COMPLETED | 100%
1215 | County Aggregation and Industrial Park | To reduce post-harvest losses, increase farmers' income through value addition, and create thousands of local jobs. | Increase farmers' livelihoods by providing ready markets and eliminating exploitative middlemen. Transition from exporting raw materials to exporting processed, "Made in Kenya" finished goods to boost foreign exchange | Targeted creation of over direct and indirect jobs focusing on youth and women. |  |  | MARAGUA | KIMORORI WEMPA |  | INDUSTRIALISATION | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-10-01 | 2024-02-01 | 2028-06-01 |  |  | 500000000 | 500000000 | MCG; National government | National Governemnt of Kenya, Ministry of Investments, Trade, and Industry | 250000000 | 250000000 | 100000000 | 0.2% | 0 |  | 100000000 | ONGOING | 0.3% | 0.3% | Ongoing |  |  | 500000000 | YES
1216 | Launch of Murang'a County Tourism Association | A private-sector-led organization formed in early 2025 to represent tourism stakeholders and drive the county's agenda as Kenya's Adventure Capital | To establish the county as Kenya’s premier "Adventure Capital" by leveraging its unique natural resources | It is a coordinated business circuit that converts these attractions into economic growth. |  |  | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU |  | TOURISM | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2025-02-01 | 2025-02-01 | 2026-06-01 |  | 200000 | 200000 | 200000 | MCG | [5 empty] | 0 | 0 | 200000 | ONGOING | 0.45%
1217 | Kihoya open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANGEMA | RWATHIA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 | 3125000 | 3125000 | 5023450 | MCG |  |  |  | 3125000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO
1218 | Ichichi open market shed | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANGEMA | KANYENYAINI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 | 3125000 | 3125000 | 4706315 | MCG |  |  |  | 3125000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO
1219 | Karuri open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | MUTHITHI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 | 3125000 | 3125000 | 4915470 | MCG |  |  |  | 3125000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO
1220 | Mununga open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | KINYONA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 | 3125000 | 3125000 | 6492080 | MCG |  |  |  | 3125000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO
1221 | Kandara open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANDARA | ITHIRU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 | 3125000 | 3125000 | 6517200 | MCG |  |  |  | 3125000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO
1222 | Kihumbu-ini open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | GATANGA | KIHUMBUINI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 | 3125000 | 3125000 | 2501050 | MCG |  |  |  | 3125000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO
1223 | Gitugi open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MATHIOYA | GITUGI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 | 3125000 | 3125000 | 4518134 | MCG |  |  |  | 3125000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO
1224 | Kambiti open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MARAGUA | KAMBITI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 | 3125000 | 3125000 | 5053200 | MCG |  |  |  | 3125000 | 100% |  |  | 0 | COMPLETED | 100% | [5 empty] | NO
1225 | Muthithi open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | MUTHITHI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1226 | Kangari open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | KANGARI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1227 | Gatunyu open market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | GATANGA | MUGUMOINI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1228 | Ngararia Market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANDARA | NGARARIA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1229 | Karugia Market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANGEMA | MUGURU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-08-01 | 2023-10-01 | 2024-06-01 | 2024-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1230 | County Aggregation and Industrial Park | To reduce post-harvest losses, increase farmers' income through value addition, and create thousands of local jobs. | Increase farmers' livelihoods by providing ready markets and eliminating exploitative middlemen. Transition from exporting raw materials to exporting processed, "Made in Kenya" finished goods to boost foreign exchange | Targeted creation of over direct and indirect jobs focusing on youth and women. |  |  | MARAGUA | KIMORORI WEMPA |  | INDUSTRIALISATION | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2023-10-01 | 2024-02-01 | 2028-06-01 |  |  | 500000000 | 500000000 | MCG; National government | National Governemnt of Kenya, Ministry of Investments, Trade, and Industry | 250000000 | 250000000 | 100000000 | 0.2% | 0 | 100000000 | 100000000 | ONGOING | 0.3% | 0.3% | Ongoing |  |  | 500000000 | YES
1232 | Open market shed at Mukuyu | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | TOWNSHIP |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1233 | Market shed maragua market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MARAGUA | ICHAGAKI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1234 | Kambirwa market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | MBIRI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1235 | Horticulture market shed mukuyu market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | TOWNSHIP |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1236 | Construction of toilet block at kabati market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANDARA | NGARARIA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1237 | Renovation of mukuyu market toilet block | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | TOWNSHIP |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1238 | Installation of 13m high light at Karugia & Gacharage market. | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANDARA, KANGEMA | RUCHU, MUGURU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1239 | Open shade at mukuyu market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | TOWNSHIP |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1240 | Bblution block ata ngararia market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANDARA | NGARARIA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1241 | Renovation & construction of charcoal store at marigiti market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MARAGUA | ICHAGAKI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2017-08-01 | 2017-10-01 | 2018-01-01 | 2018-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1243 | Drainage works for ngonda market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MATHIOYA | GITUGI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1244 | Market canopy at kiriaini market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MATHIOYA | KIRU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1245 | Fencing(chainlink) & gravelling of Karuri market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | MUTHITHI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1246 | Construction of fresh produce & wholesale market at maragwa. | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MARAGUA | NGINDA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1247 | Fencing of kagundu-ini livestock market and toilets | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANDARA | KAGUNDUINI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1248 | Construction of 2 boda boda sheds at Kangari market. | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | KANGARI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1249 | Drillng and equipping of borehole at Mugumoini market. | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | GATANGA | MUGUMOINI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1250 | Sheds at Kahatia Market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | MURARANDIA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1251 | Construction of 14 tailoring sheds at Kiriani Market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MATHIOYA | KIRU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1252 | Open air market at Ciumbu open air market shed | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MARAGUA | KAMBITI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2016-08-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | [5 empty] | NO
1254 | Construction of Kandara open air market shed phase 2 | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | MUGOIRI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1255 | Renovation and construction of fresh produce and wholesale market at kahuro | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | TOWNSHIP |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1256 | Renovation of mukuyu market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIHARU | TOWNSHIP |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1257 | Construction of kiriaini open air market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MATHIOYA | KIRU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1258 | Construction of a block toilet at githumu market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANDARA | RUCHU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1259 | Construction of kangari open air market sheds | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | KANGARI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1260 | Construction of fresh produce and wholesale market at ndunyu chege | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | GATANGA | KARIARA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1261 | Renovation of kagunduini market public toilet | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANDARA | KAGUNDUINI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1262 | Construction of market shed at muthithi mkt | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | MUTHITHI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1263 | Levelling, shed & pit latrine at mbombo open air market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MARAGUA | ICHAGAKI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1264 | Gravelling of gitugi market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MATHIOYA | GITUGI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1265 | Construction of a toilet & 10 receptacles for kangari market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | KANGARI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1266 | Concrete at kagunduini open air market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KANDARA | KAGUNDUINI |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1267 | Kenol open air market sheds and drainage works phase 1 | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MARAGUA | KIMORORI WEMPA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1268 | Drainage works for ngonda market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | KIGUMO | KINYONA |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1269 | Market canopy at kiriaini market | Upgrading and renovation of market | Provide a low-entry-cost platform for small-scale traders like "Mama Mbogas" to sell their produce in a conducive environment | A higher number of space for traders st the market leading to reduced losses of produce. |  |  | MATHIOYA | KIRU |  | TRADE | Trade, Industry, Tourism, Agriculture, Livestock and Fisheries |  | 2015-09-01 | 2015-10-01 | 2016-06-01 | 2016-06-01 |  |  |  | MCG | [8 empty] | COMPLETED | 100% | 1% |  |  |  |  | NO
1270 | Preparation & Approval of Local Physical and Land Use Development Plan for Delmonte Land (LR 12157/8 & LR 12157/11 | Development of Delmonte LPLUDP to guide developmnent in the Industrial Park | develop a comprehensive, legally compliant, and sustainable spatial planning framework that guides the orderly development, land use allocation, infrastructure provision, and environmental management of the Delmonte land parcels. | Approved GIS based Delmonte Land Use Plan |  | 20000000 | KANDARA | MURUKA | Makenji | LANDS | Lands, Physical Planning and Urban Development. |  | 2024-02-02 | 2024-03-05 | 2025-03-01 | 2025-05-25 | 100000000 | 70000000 |  | MCG |  |  |  | 30000000 | 0.43% | 65000000 | 5000000 | 5000000 | COMPLETED | 100% | 0% |  | 0 | 0 | 0 | NO |  | None | NO | None | NO | None | NO | None | None
1271 | Development of Land Information Management System (LIMS) | Development of an integrated digital platform designed to collect, store, manage, analyze, and disseminate land-related information to support efficient land administration, planning, and development control. | Establish an integrated, accurate, and efficient digital platform for managing land-related information to support transparent land administration, sustainable land use planning, and informed decision-making. | Fully Functional GIS based LIM and lab |  | 60000000 | GATANGA, KANDARA, KANGEMA, KIGUMO, KIHARU, MARAGUA, MATHIOYA | GATANGA, ITHANGA, KAKUZI/MITUMBIRI, KARIARA, KIHUMBUINI, MUGUMOINI, GAICHANJIRU, ITHIRU, KAGUNDUINI, MURUKA, NGARARIA, RUCHU, KANYENYAINI, MUGURU, RWATHIA, KAHUMBU, KANGARI, KIGUMO, KINYONA, MUTHITHI, GATURI, MBIRI, MUGOIRI, MURARANDIA, TOWNSHIP, WANGU, ICHAGAKI, KAMAHUHA, KAMBITI, KIMORORI WEMPA, MAKUYU, NGINDA, GITUGI, KAMACHARIA, KIRU | Muranga County | LANDS | Lands, Physical Planning and Urban Development. |  | 2024-02-05 | 2024-03-05 | 2024-12-06 | 2025-01-03 | 10000000 | 5000000 |  | FAO | FAO |  |  | 3000000 | 0.6% | 3000000 | 2000000 | 2000000 | ONGOING | 80% | 20% | Inadequate funding | 2025 | 5 | 3000000 | YES |  | None | NO | None | NO | None | NO | None | None
1272 | Upgrading of Kenneth Matiba hospital from level 4 to level 5 | upgrading of Kenneth matiba hospital from level 4 to level 5 | upgrade of Kenneth matiba hospital from level 4 to level 5 | upgrade of Kenneth matiba hospital from level 4 to level 5 |  |  | GATANGA | KAKUZI/MITUMBIRI |  | DEVOLUTION | Devolution and External Linkages | Devolution and External Linkages | [16 empty] | PLANNED
1273 | Water supply to Muranga Investment park (del Monte), construction of an admintraction block and 1km tarmac paving | Water supply to Muranga Investment park (del Monte), construction of an admintraction block and 1km tarmac paving | Water supply to Muranga Investment park (del Monte), construction of an admintraction block and 1km tarmac paving | Water supply to Muranga Investment park (del Monte), construction of an admintraction block and 1km tarmac paving |  |  | MARAGUA | KIMORORI WEMPA |  | DEVOLUTION | Devolution and External Linkages | Devolution and External Linkages | [16 empty] | PLANNED
1274 | Operationalisation of Gikono waste management landfill,fencing and supply of compactor | Operationalisation of Gikono waste management landfill,fencing and supply of compactor | Operationalisation of Gikono waste management landfill,fencing and supply of compactor | Operationalisation of Gikono waste management landfill,fencing and supply of compactor |  |  | MARAGUA | KIMORORI WEMPA |  | DEVOLUTION | [18 empty] | PLANNED
ACKNOWLEDGEMENT
Report prepared by:
Designation:
Signature:
Date:
Report approved by:
Designation:
Signature:
Date: